## Summary
Project Title :70 MW BHADLA SOLAR POWER PLANT BY FORTUM FINNSURYA ENERGY PVT LTD (EKIESL-CDM-APRIL 16-01)
Project Ref No. : 5519
ER Sheet version 03 Dated 01/05/2024
ER Comparison
Start Date of Monitoring Period | 2022-11-06
End Date of Monitoring Period | 2023-09-30
Number of Days for Current Monitoring Period | 329
Annual ER estimation as per Registered PDD version 03 dated 04/01/2023 | 112980
EFgrid,CM,y | 0.9305
ER Estimation for Current Monitoring Period | 101836
Actual ER for Current Monitoring Period | 121511
Change in Emission Reductions | 19.32%
Actual generation for current MP | 130587.5522
Estimated PLF as per Registered PDD version 03 dated 04/01/2023 | 20%
Actual PLF during current Monitoring Period | 23.63%
Change in PLF | 18.13%

## Emission Reduction
Month | Invoice |  |  |  | JMR |  |  | Net Energy (MWh) | Vintage wise break up Net Energy (MWh) | Emission factor (tCO2/MWh) | Emission Reduction tCO2 e | Vintage wise break up tCO2 e
| Export | Import | Transmission Losses | Net Energy (kWh) | Export | Import | Net Energy (kWh)
2022-11-06 | 9378200 | 52150 | 54209.825 | 9271840.175 | 9378200 | 52150 | 9326050 | 9073.6142 | 20416.4654 | 0.9305 | 8442.998 | 18997
2022-12-06 | 11474640 | 64920 | 66868.73 | 11342851.27 | 11474640 | 64920 | 11409720 | 11342.8513 |  | 0.9305 | 10554.5231
2023-01-06 | 11250120 | 66900 | 66445.3 | 11116774.7 | 11250120 | 66900 | 11183220 | 11116.7747 | 110171.0868 | 0.9305 | 10344.1589 | 102514
2023-02-06 | 11784180 | 57060 | 68230.9 | 11658889.1 | 11784180 | 57060 | 11727120 | 11658.8891 |  | 0.9305 | 10848.5963
2023-03-06 | 12715620 | 57180 | 74371.88 | 12584068.12 | 12715620 | 57180 | 12658440 | 12584.0681 |  | 0.9305 | 11709.4754
2023-04-06 | 12588600 | 52680 | 70217.25 | 12465702.75 | 12588600 | 52680 | 12535920 | 12465.7028 |  | 0.9305 | 11599.3364
2023-05-06 | 11977380 | 53220 | 64428.56 | 11859731.44 | 11977380 | 53220 | 11924160 | 11859.7314 |  | 0.9305 | 11035.4801
2023-06-06 | 12568320 | 53520 | 72779.14 | 12442020.86 | 12568320 | 53520 | 12514800 | 12442.0209 |  | 0.9305 | 11577.3004
2023-07-06 | 12204120 | 55680 | 73082.21 | 12075357.79 | 12204120 | 55680 | 12148440 | 12075.3578 |  | 0.9305 | 11236.1204
2023-08-06 | 13562400 | 56400 | 78535.29 | 13427464.71 | 13562400 | 56400 | 13506000 | 13427.4647 |  | 0.9305 | 12494.2559
2023-09-06 | 12671160 | 56100 | 73982.7 | 12541077.3 | 12671160 | 56100 | 12615060 | 12541.0773 |  | 0.9305 | 11669.4724
Total | 132174740 | 625810 |  | 130785778.215 | 132174740 | 625810 | 131548930 | 130587.5522 | 130587.5522 |  |  | 121511
Apportionig has been applied to remove the electricity generation from 01/11/2022 to 05/11/2022, since the billing cycle is from 01/11/2022 and the Monitoring period start date is from 06/11/2022.
Daily Generation Data |  |  |  |  | Generation Data (Unitary Method)
Date | ABT Meter Export (MWh) | ABT Meter Import (MWh) | Net Energy (KWh) |  | Date |  | Export (MWh) | Import (MWh) | Net Energy (KWh)
|  |  | Net Energy (MWh) |  | Start Date | End Date |  |  | Net Energy (MWh)
2022-11-06 | 326.64 | 2.016 | 324624 |  | 2022-11-01 | 2022-11-30 | 11253840 | 62580 | 11191260
2022-11-07 | 317.424 | 2.064 | 315360 |  | 2022-11-06 | 2022-11-30 | 9378200 | 52150 | 9326050
2022-11-08 | 255.456 | 1.968 | 253488
2022-11-09 | 305.28 | 2.16 | 303120
2022-11-10 | 365.712 | 2.016 | 363696 |  | Net Energy (Without Transmission Loss) (kWh) |  |  | 9127824
2022-11-11 | 294.912 | 2.112 | 292800 |  | Transmission Loss (kWh) |  |  | 54209.825
2022-11-12 | 372.96 | 2.064 | 370896 |  | Net Energy (Without Transmission Loss) (kWh) |  |  | 9073614.175
2022-11-13 | 389.328 | 2.112 | 387216
2022-11-14 | 370.368 | 2.064 | 368304
2022-11-15 | 319.632 | 2.064 | 317568
2022-11-16 | 380.016 | 2.064 | 377952
2022-11-17 | 396 | 2.112 | 393888
2022-11-18 | 388.896 | 2.112 | 386784
2022-11-19 | 390.528 | 2.16 | 388368
2022-11-20 | 359.376 | 2.016 | 357360
2022-11-21 | 385.248 | 2.112 | 383136
2022-11-22 | 381.552 | 2.112 | 379440
2022-11-23 | 406.128 | 2.016 | 404112
2022-11-24 | 412.32 | 2.304 | 410016
2022-11-25 | 407.184 | 2.16 | 405024
2022-11-26 | 406.032 | 2.016 | 404016
2022-11-27 | 400.416 | 2.064 | 398352
2022-11-28 | 405.456 | 2.208 | 403248
2022-11-29 | 370.944 | 1.968 | 368976
2022-11-30 | 372.192 | 2.112 | 370080
Total | 918000 | 5217.6 | 9127824

## SDG Summary
S. No. | SDG | SDG Indicator | Values achieved |  |  | Unit
|  |  | 2022 | 2023 | Total
1 | SDG 7: | Affordable and Clean Energy | 20416.4654 | 110171.0868 | 130587.5522 | MWh
2 | SDG 8: | Decent Work and Economic Growth | 1 | 2 | 3 | Number of employees
|  |  | 6 | 29 | 35 | Number of Trainings
3 | SDG 13 | Climate Action | 18997 | 102514 | 121511 | tCO2e

## PLF Data
Current Monitoring Period (06/11/2022 to 30/09/2023) |  |  |  | Yearly PLF Data (Last 3 Years)
Month | Net Energy (MWh) | PLF (Monthly) | PLF (Yearly) | Year | Start Date | End Date | Net Generation (MWh) | PLF (%) | Source
2022-11-06 | 9073.6142 | 21.6% | 21.7% | 2020 | 2020-01-01 | 2020-08-01 | 88186.92 | 23.95% | 2nd Monitoring Period
2022-12-01 | 11342.8513 | 21.78% |  | 2020 | 2020-08-02 | 2020-12-31 | 59055 |  | 3rd Monitoring Period
2023-01-01 | 11116.7747 | 21.35% | 24.02% | 2021 | 2021-01-01 | 2021-06-30 | 76866.54 | 24.07% | 4th Monitoring Period
2023-02-01 | 11658.8891 | 24.79% |  | 2021 | 2021-07-01 | 2021-12-31 | 70758 |  | 5th Monitoring Period
2023-03-01 | 12584.0681 | 24.16% |  | 2022 | 2022-01-01 | 2022-11-05 | 127492.7961 | 22.27% | 5th Monitoring Period
2023-04-01 | 12465.7028 | 24.73% |  | 2022 | 2022-11-06 | 2022-12-31 | 9073.6142 |  | 6th Monitoring Period (Current MP)
2023-05-01 | 11859.7314 | 22.77% |  | 2023 | 2023-01-01 | 2023-09-30 | 110171.0868 | 24.02% | 6th Monitoring Period (Current MP)
2023-06-01 | 12442.0209 | 24.69%
2023-07-01 | 12075.3578 | 23.19%
2023-08-01 | 13427.4647 | 25.78%
2023-09-01 | 12541.0773 | 24.88%
Total | 130587.5522 | 23.61% | 23.63%