# Project title:	GS VER- ARAKALAGUDU BIOGAS PROJECT II

Report by: 			GoodPlanet Fondation, France and SKG Sangha, India.

Project start date: 		01/02/2010.

Registration date: 		18th February 2011

Project location: 		Arakalagudu Taluk, Hassan District, Karnataka state, INDIA

Version: 			2

Date				19th February, 2015

Contact Details:          		GoodPlanet Foundation.

ActionCarbone Programme,

1, Carrefour Longchamp,

Paris, FRANCE – 75116.

www.actioncarbone.org

SKG Sangha

Devarayasamudra Village

Mulbagal Taluk, KOLAR District

Karnataka State, INDIA

Postal Code – 563 127

http://www.skgsangha.org

Monitoring Period: 		01/01/2013 – 31/12/2013.

Monitoring survey Team:  	Mr. M Praveen 		(Senior supervisor, SKG Sangha)

Mr. B M Manjunath 	(Senior supervisor, SKG Sangha).

Accompanied by:

Mr. Ashoka 		(SKG Sangha local entity in the villages)

Mr. Narayana 		(SKG Sangha local entity in the villages)

Mr. Somu 		(SKG Sangha local entity in the villages)

# Contents

- Introduction.

- Monitoring –

a) Monitoring survey methodology.

b) Annual monitoring of the project.

- Sustainable development monitoring parameters.

- Emission reduction monitoring parameters.

- Emission Reductions.

- Annexe I - Sample copies of monitoring survey sheets.

1. Introduction:

The project activity aim is to provide a sustainable solution for daily cooking needs of the beneficiaries by providing biogas plants and vermicomposting units in the villages of Arakalagudu Taluk, Karnataka state, India. The project has been funded by GoodPlanet Fondation and was implemented along with its project partner SKG Sangha. The project aimed to completely replace the use of firewood by the biogas units for daily cooking needs of the rural communities. The SKGS team has carried out the monitoring of the project with regular visits to the units during the year. To avoid any double counting of the biogas plants during the monitoring survey, each plant has been provided with a unique identification number. A total of 755 biogas and vermicomposting units have been constructed. The complete list of 755 beneficiaries has already been provided to the Gold Standard in the previous verification process of the project activity.

2. Monitoring:

- Monitoring survey methodology

The required samples for the monitoring survey were selected on a random basis. A total of 119 beneficiaries were selected for the monitoring sample (out of the 755 units). The survey was carried out by SKGS team along with the local supervisors in-charge of the monitoring of respective villages in the project. The SKGS survey team collected the data from each of the beneficiary through a series of questionnaires. A sample copy of the survey sheets has been provided to the Gold Standard for further verifications. These survey sheets were rechecked by the SKGS senior staff member before recording them into the excel sheets. The report includes both the sustainable development indicators and the parameters used to determine the total emission reductions for the year 2013. The report includes a detailed description and justification for each of the parameters included in the monitoring survey.

SKGS survey team members were trained by the senior staff before the surveys on the following aspects of the survey forms:

1. Weight of the basket to be used to collect the cow dung.

2. Weight of the wood used for cooking and / or water heating.

3. Hours of biogas stove operation,

4. Head counting the number and type of animals

5. Types of repairs carried out on biogas unit and vermicomposting unit,

6. What aspects to be covered in the comments box,

7. Random selection of the household to be surveyed,

8. How to pose questions related to sustainable development and other parameters of development

in the questionnaire and etc.

The monitoring surveys were held between the 20/01/2014 – 11/02/2014.

- Continuous monitoring of the project:

Apart from this annual monitoring survey to collect the required data, the SKGS field teams have also visited the biogas and vermicomposting units on a monthly basis. The field visits by the team were conducted as a part of the maintenance of the units. These field visits also gave the SKGS team an opportunity to provide on-site training to the beneficiaries on the use and maintenance of both the biogas/ vermicomposting units. These on-site training have helped the team to observe and understand the various field issues, which were further discussed during the team meeting. Such regular team meetings also helped other field supervisors to solve similar problems during their field visits. The present monitoring survey data also includes details of the on-site training given to the beneficiaries by the SKGS team.

The GoodPlanet Foundation team members also carried out a random field visit to the project units in the month of June 2013. The units visited were functioning and did not come across any plants that had faced any major technical problems. Each beneficiary was asked to demonstrate the working of the biogas units and/or to demonstrate the feeding procedure of animal dung into the biodigester. These few demonstration to the GoodPlanet team also assured that the beneficiaries were well trained by the SKGS field officers about the minimum quantity of animal dung and water that is needed for a regular supply of the biogas.

3. Sustainable development monitoring parameters

| Data / Parameter: | Soil condition (quality and quantity) |
| --- | --- |
| Description | The slurry from the biogas unit is pre-treated along with the animal dung (if any remaining) before sending it for the vermicompost process. The vermicompost is used as an organic fertiliser for the agricultural activities. |
| Source of data: | Monitoring survey data 2013 |
| Measurement procedures (if any): | The parameter has been measured by asking specific questions regarding the use of the application of either the biogas slurry and/or vermicompost for agricultural needs. The total quantity of bags produced by each beneficiary in the monitoring survey has been recorded. The use of the biogas slurry and/or vermicompost also justifies the reduction of the use of chemical fertilisers by the beneficiaries. |
| Monitoring frequency: | Once a year. |
| QA/QC procedures: | Each beneficiary was asked the total amount of vermicompost produced during the year by measuring it with the locally available bags (40kg per bag). The monitoring survey data gives the total quantity of vermicompost used for agricultural needs by each beneficiary during the year 2013. The additional vermicompost, which is not utilised by the beneficiaries during the year, are dried and stored for future needs. |
| Any comment: | The monitoring survey for the year 2013 shows that around 50% the beneficiaries have produced vermicompost and these beneficiaries have been able to reduce their annual fertiliser use for agriculture. Remaining of the beneficiaries had not produced vermicompost, and therefore there has been no change in their annual fertilisers consumption. From the previous monitoring period, it has been observed that the few beneficiaries had faced issues of the earthworms being eaten by the predators and/or lack of maintenance of the vermicomposting units. Similar problems are observed in this monitoring period. During the visits to the project units, GoodPlanet team also observed that beneficiaries, who could produce vermicompost, stored the compost in a dried and aerobic condition. On an average 9 bags (weighing about 40 Kgs) of vermicompost were produced in the year 2013. The additional available dung was pre-treated with the biogas slurry for vermicomposting process. The team has been regularly visiting the units and are trying to promote a proper management of these units to assure that the production of the compost increases in the coming years. |

| Data / Parameter: | Air Quality |
| --- | --- |
| Description | Total quantity of firewood used for daily cooking needs after the implementation of the project activity. |
| Source of data: | Monitoring survey data 2013 |
| Measurement procedures (if any): | The indicator has been analysed through a series of questions that were asked to each beneficiary in the monitoring survey to know if there has been any improvement of the air quality due to the project activity. This has been compared to the baseline situation where the beneficiaries carried out indoor cooking with firewood, releasing harmful pollutants affecting the health of the beneficiaries. |
| Monitoring frequency: | Once a year. |
| QA/QC procedures: | Appropriate questions were posed in order to ensure that the indicator has been assessed properly. The monitoring team have also visited the kitchen to ensure that the beneficiary did not continue using firewood for cooking needs. GoodPlanet team has also visited the beneficiaries and have interviewed the beneficiaries in regards to this particular indicator. The beneficiaries have been content with the use of the biogas, which has improved the overall air-quality of the kitchen. |
| Any comment: | Out of the total 119 households surveyed – - 99 % of the beneficiaries have agreed to reduction in respiratory & eyes irritation problems due to the availability of biogas for daily cooking needs. - One of the beneficiaries had faced a problem of dome leakage with the biodigester. The SKS team repaired it and the amount firewood used during the absence of biogas has been taken into account in the emission reduction calculations. Other minor issues like stove-pans/stove cock were immediately taken into account and replaced by the SKG technical team. - None of the beneficiaries have experienced any respiratory and/or irritation of eyes from the use of biogas for daily cooking needs. |

| Data / Parameter: | Livelihood of the poor |
| --- | --- |
| Description | Access to animal waste management system by providing a biodigester to each family and disposing the animal waste in a sanitary way assuring hygiene around the household. |
| Source of data: | Monitoring survey data 2013 |
| Measurement procedures (if any): | The indicator has been analysed through a series of questions that were asked to each beneficiary in the monitoring. This has been compared to the baseline situation where the beneficiaries dumped the animal dung along with other waste into traditional compost pits near the households leading to unhygienic conditions. The change in the annual income due to the use of biogas and vermicompost was reviewed during the monitoring survey. |
| Monitoring frequency: | Once a year. |
| QA/QC procedures: | This indicator was assessed on three different scenarios. First, the saving of time from collecting the firewood. Second, if any savings of income due to the project. And third, if the beneficiaries have a better waste-management system compared to earlier and lastly, if they have either pre-treated the additional animal dung before using it for the vermicompost process. |
| Any comment: | Out of the total 119 households surveyed – - 99% of the households had access to the waste management systems provided through the project activity and have been working without any problems. The beneficiaries have reported a hygienic environment around the households since they have been able to completely utilise the animal dung in the biodigesters. The beneficiaries who had additional animal-dung have pre-treated it with the biogas slurry for the vermicompost production. The beneficiaries, who had lost earthworms, were provided another batch of worms by the SKG team without any additional costs. - One of the beneficiaries had reported the non-function of the biogas unit, which was repaired by the SKG team. - Some of the beneficiaries have provided the actual data on their income saving while others have only confirmed about the savings but have not provided any data. This savings in the income has occurred due to reduction in the use of chemical fertilisers and the regular use of biogas for daily cooking needs. The monitoring surveys shows that more than 95% of the beneficiaries have been able to witness on an average of 2500 INR savings. |

| Data / Parameter: | Access to affordable and clean energy services |
| --- | --- |
| Description | The access to energy services of the beneficiaries in the project area has been monitored in terms of the biogas supply for daily cooking needs. |
| Source of data: | Monitoring survey data 2013 |
| Measurement procedures (if any): | The indicator has been analysed through a series of questions that were asked to each beneficiary in the monitoring. This has been compared to the baseline situation where the beneficiaries used firewood for daily cooking needs. |
| Monitoring frequency: | Once a year. |
| QA/QC procedures: | Appropriate questions were posed in order to ensure that the indicator has been assessed properly. GoodPlanet team has also visited the beneficiaries and have interviewed some of the beneficiaries on this indicator. |
| Any comment: | Out of the total 119 households surveyed – - 99% households surveyed had sufficient supply of biogas as per their daily cooking needs. Some minor problems related to the appliances like the stove knobs, stove stands have either been repaired or replaced by the SKGS team during the field visits. - Only one of the beneficiaries had faced any technical issue with the biodigester and was repaired by the SKG team. A regular follow-up is carried out with all the beneficiaries by the technical staff of SKG to assure the continuous working of the units. |

| Data / Parameter: | Quality of Employment |
| --- | --- |
| Description | Any employment opportunity due to the projects and/or if any additional income generated by selling the vermicomposting. |
| Source of data: | Monitoring survey data 2013 |
| Measurement procedures (if any): | The indicator has been analysed through a series of questions that were asked to each beneficiary in the monitoring. This has been compared to the baseline situation where the beneficiaries (women) did not have any source of income. |
| Monitoring frequency: | Once a year. |
| QA/QC procedures: | Appropriate questions were posed in order to ensure that the indicator has been assessed properly. GoodPlanet team has also visited the beneficiaries and have interviewed some of the beneficiaries on this indicator. |
| Any comment: | Out of the total 119 households surveyed – On an average the beneficiaries in the project activity have been able to benefit from an income saving of 2500 INR. SKGS team has been trying to continuously follow-up with the beneficiaries, especially on the composting aspects considering the various issues faced for a regular production. The project still aims that each beneficiary is trained continuously and also takes the initiative to maintain and produce the vermicompost in the coming years. |

| Data / Parameter: | Human and institutional capacity |
| --- | --- |
| Description | Human and institutional capacity (including empowerment, education, involvement, gender) of the beneficiaries in the project area has been monitored in terms of access of the biogas for cooking. |
| Source of data: | Monitoring survey data 2013 |
| Measurement procedures (if any): | The indicator has been analysed through a series of questions that were asked to each beneficiary in the monitoring. |
| Monitoring frequency: | Once a year. |
| QA/QC procedures: | Appropriate questions were posed in order to ensure that the indicator has been assessed properly. GoodPlanet team has also visited the beneficiaries and have interviewed some of the beneficiaries on this indicator. |
| Any comment: | Out of the total 119 households surveyed – - 99% of the beneficiaries in the project activity have witnessed saving of time from collecting firewood. - Each beneficiary surveyed has received on-site training from the SKG supervisor during his field visits. - The annual saving due to the project activity has been observed for each beneficiary in the project activity and the actual amount saved has been provided in the monitoring survey sheets. |

| Data / Parameter: | Technology transfer and technological self-reliance |
| --- | --- |
| Description | The technological self-reliance parameter in the project has been monitored in terms of training provided to the beneficiaries on maintenance of the biogas and vermicomposting units. |
| Source of data: | Monitoring survey data 2013 |
| Measurement procedures (if any): | SKGS carries out various training programs both for the technical staff and the beneficiaries. These training are carried out in a group and also on an individual basis during the field visits. Each beneficiary in the project activity was asked in the monitoring survey if they have received any training by the trained staff of SKGS. |
| Monitoring frequency: | Once a year. |
| QA/QC procedures: | Appropriate questions were posed in order to ensure that the indicator has been assessed properly. GoodPlanet team has also visited some of the beneficiaries and have interviewed the beneficiaries on this indicator. |
| Any comment: | The survey shows that 99% of the beneficiaries had regular supply of biogas and had received a training programme by the SKG staff. The training programmes are provided to beneficiaries who still had maintenance issues related to the biogas and vermicomposting units. The monitoring survey sheets indicate the type of the training received by the beneficiary and the name of the SKGS officers who have provided the training. SKGS has also carried regular team meetings during the year. The details of the training programmes are as follows – - 24th May 2013 - Training programmes on the maintenance of Vermicomposting units conducted at the SKGS office. - 27th June 2013 – During the site visits, GoodPlanet team had also participated in one of the SKGS team meeting at the head office. - 25th December 2013 - Training programme for supervisors and other supporting staff on ‘Conducting the monitoring survey’. |

| Data / Parameter: | Biodiversity |
| --- | --- |
| Description | The beneficiaries either collect the firewood from forest and/or buy from the local market to meet daily cooking and water heating needs. This firewood consumption in the longer years could result in decrease of the forest area. |
| Source of data: | Monitoring survey data 2013 |
| Measurement procedures (if any): | This indicator has been assessed by comparing the quantity of firewood used in the baseline scenario with the present project scenario. |
| Monitoring frequency: | After every 2 years. |
| QA/QC procedures: | - |
| Any comment: | All the beneficiaries have replaced the use of firewood by biogas for their daily cooking needs. |

4. Emission reduction monitoring parameters

| Data / Parameter: | D 5 / nhh.y |
| --- | --- |
| Data unit: | 755 |
| Description | Total number of households participating in the programme in year 2013. |
| Source of data: | SKGS Database with all the details of the beneficiaries. |
| Measurement procedures (if any): | The total number of the households in the project activity is derived from the detailed database in which each unit has been allocated a unique identification corresponding to each beneficiary. This database has been maintained by the SKGS team, and also helps the team to avoid any double counting of the units during the monitoring survey. |
| Monitoring frequency: | Annually |
| QA/QC procedures: | Each household of the project activity has been allocated a separate serial number to avoid any double counting. The complete list of the details of each HH in the monitoring survey has been provided for further verification. |
| Any comment: | The total biogas and vermicomposting units for the project activity are 755 units. The GoodPlanet team has also cross-checked this ‘detailed list’ during the field visits to the units. The allocated identification number to each household was also cross-checked and there have been no repetitions of any numbers allocated to the units. |

| Data / Parameter: | ID 8 / Fi,y, pj |
| --- | --- |
| Data unit: | 0.02 kg/day |
| Description | Amount of fuel wood consumption for cooking needs in the project in year 2013 |
| Source of data: | Monitoring survey data 2013 |
| Measurement procedures (if any): | During the survey, the monitoring team asked each beneficiary in the survey sample about the average firewood consumed per day after the implementation of the project activity. |
| Monitoring frequency: | Annually |
| QA/QC procedures: | To assure that the beneficiary gives a correct data, the monitoring team weighed the firewood using the weighing machine, to record the accurate data. |
| Any comment: | One of the households had no supply of biogas for about 10 days due to a leakage of the pipe carrying the gaz. The SKG team replaced the pipe immediately. Remaining beneficiaries had a continuous supply of biogas throughout the monitoring year. The emission reductions of the firewood use have been taken into account while calculating total VER’s. |

| Data / Parameter: | ID 11/ MS(T,biodigester,k) |
| --- | --- |
| Data unit: | 77 % |
| Description | Fraction of livestock category T's manure fed into the biodigester, S |
| Source of data: | Monitoring survey data 2013 |
| Measurement procedures (if any): | It’s calculated by the total amount of cow dung that is collected by the beneficiary and fed into the biodigester. |
| Monitoring frequency: | Annually |
| QA/QC procedures: | The GoodPlanet team rechecked all the monitoring data and the excel sheets to be reassured that all the values corresponded to the revised documents. |
| Any comment: | The fraction of manure for each category of the animal has been calculated depending on the time it spends in the sheds. |

| Data / Parameter: | ID 12 / PL |
| --- | --- |
| Data unit: | 10 % |
| Description | Physical Leakage of the biodigester |
| Source of data: | Default values of 10%. From the 2006 IPCC Guidelines for National Greenhouse Gas Inventories are taken into account. |
| Measurement procedures (if any): | - |
| Monitoring frequency: | Annually |
| QA/QC procedures: | - |
| Any comment: | If any changes in the IPCC guidelines are observed for this parameter, the necessary documents will be revised. |

| Data / Parameter: | ID 13 / LC |
| --- | --- |
| Data unit: | 1 numbers per Household. |
| Description | Number of life stock of category –Dairy cows. |
| Source of data: | Monitoring survey data 2013 |
| Measurement procedures (if any): | This is the average numbers of dairy cows present with each household. |
| Monitoring frequency: | Once a year |
| QA/QC procedures: | The GoodPlanet team rechecked all the monitoring data and the excel sheets to be reassured that all the values corresponded to the revised documents. |
| Any comment: |  |

| Data / Parameter: | ID 13 / LC |
| --- | --- |
| Data unit: | 1 numbers per Household. |
| Description | Number of life stock of category –Buffaloes. |
| Source of data: | Monitoring survey data 2013 |
| Measurement procedures (if any): | This is the average numbers of buffaloes present with each household. |
| Monitoring frequency: | Once a year |
| QA/QC procedures: | The GoodPlanet team rechecked all the monitoring data and the excel sheets to be reassured that all the values corresponded to the revised documents. |
| Any comment: |  |

| Data / Parameter: | ID 13 / LC |
| --- | --- |
| Data unit: | 2 numbers per Household. |
| Description | Number of life stock of category –Other Cattle. |
| Source of data: | Monitoring survey data 2013 |
| Measurement procedures (if any): | This is the average numbers of other cattle’s present with each household. |
| Monitoring frequency: | Once a year |
| QA/QC procedures: | The GoodPlanet team rechecked all the monitoring data and the excel sheets, to be reassured that all the values corresponded to the revised documents. |
| Any comment: |  |

| Data / Parameter: | ID 16 / GWPCH4 |
| --- | --- |
| Data unit: | 25 tCO2e / t CH4 |
| Description | Global Warming Potential (GWP) of methane |
| Source of data: | Most recent IPCC guidelines |
| Measurement procedures (if any): | - |
| Monitoring frequency: | Annually |
| QA/QC procedures: | - |
| Any comment: | - |

Data and parameters to be monitored, in order to take into account specificities of the project

| Data / Parameter: | ID 17 / MSS,T,h,p |
| --- | --- |
| Data unit: | 3 % |
| Description | Fraction of livestock category T's manure not fed into the biodigester and treated according to the animal waste management system S. |
| Source of data: | Monitoring survey data 2013 |
| Measurement procedures (if any): | This parameter is measured by asking each beneficiary in the monitoring survey to total amount of animal dung collected from the shed and fields. The amount of dung fed to the digester and the amount left in the open pits. |
| Monitoring frequency: | Annually |
| QA/QC procedures: | The GoodPlanet team rechecked all the monitoring data and the excel sheets to be reassured that all the values corresponded to the revised documents. |
| Any comment: | The remaining 3 % is pre-treated in an aerobic condition by mixing the cow-dung with agricultural residues at a regular interval. This mixture is further introduced in the vermicomposting units to produce an organic fertiliser. As a conservative approach, this 3 % has also been considered in the project emission calculations as per the registered PDD. |

5. Emission Reductions

# Monitoring results:

The following data gives total emission reductions for the year 2013 from the project activity: -

| 1 | Baseline Emissions | 6.80 tCO2/yr./household | Baseline Survey |
| --- | --- | --- | --- |
| 2 | Project Emissions | 0.63 tCO2/yr/household | Monitoring Survey |
| 3 | Emission Reductions | 6.17 tCO2/yr./household | Calculated |

# Summary of the Emission Reductions: -

| Year | Months | Total Number of Units functional | TOTAL VERs | UNIT |
| --- | --- | --- | --- | --- |
| 2013 | January –December | 755 | 4655 | tCO2 |
| TOTAL EMISSION REDUCTIONS |  |  | 4655 | tCO2 |

# Conclusion:-

# Total Emission reduction for the year 2013 is – 4655 tCO2e

The emission reductions are claimed from 01/01/2013 till 31/12/2013.

A set of all the copies of the monitoring survey sheets have also been sent to the Gold Standard Foundation local contact (Delhi, India), as a part of the verification requirement.

# Annexe I

Few samples of the monitoring sheets have been uploaded on the GS registry.