- MONITORING REPORT FORM (CDM-MR) *

- Version 01 - in effect as of: 28/09/2010

## CONTENTS

- General description of the project activity

  - Brief description of the project activity

  - Project participants

  - Location of the project activity

  - Technical description of the project

  - Title, reference and version of the baseline and monitoring methodology applied to the project activity

  - Registration date of the project activity

  - Crediting period of the project activity and related information

  - Name of responsible person(s)/entity(ies)

- Implementation of the project activity

  - Implementation status of the project activity

  - Revision of the monitoring plan

  - Request for deviation applied to this monitoring period

  - Notification or request of approval of changes

- Description of the monitoring system

- Data and parameters monitored

  - Data and parameters used to calculate baseline emissions

  - Data and parameters used to calculate project emissions

  - Data and parameters used to calculate leakage emissions

  - Other relevant data and parameters

- Emission reductions calculation

  - Baseline emissions calculation

  - Project emissions calculation

  - Leakage calculation

  - Emission reductions calculation

  - Comparison of actual emission reductions with estimates in the registered CDM-PDD

  - Remarks on difference from estimated value

- MONITORING REPORT

- Version 3.0 19/05/2017

- Energy Efficient Cook Stoves for Siaya Communities, Kenya

- GS 879

- Monitoring period 5 (01/01/2017 - 31/12/2017)

SECTION A. 	General description of the project activity

A.1.	Brief description of the project activity: >>

>>

1. The objective of this project is to construct energy efficient stoves for rural communities in the Siaya County in Nyanza province, Kenya, to replace inefficient 3-stone fires for cooking. Over 7 years the project plans to install approximately 48,900 stoves into households in Siaya County, Kenya.

An innovative village based community savings and loaning mechanism is integrated in the project to enhance affordability and access to efficient cook stoves through soft loans. This scheme involves local capital mobilization methodology that seeks to address the unmet needs of the poor brought about by the existing gap in the major financial services providers like the banks and insurance companies.

2. The employed technology is a fix installed biomass rocket stove designed for burning wood and consisting of two cooking units that can be separately fired. The efficient cook stoves are constructed using locally available materials, such as mud, bricks and sawdust.

3. Relevant dates for the project activity:

Start date of the project: 04 October 2010

Start date of crediting period: 01 January 2011

Date of first stove sale: 04 October 2010

First monitoring period: 01 January 2011 – 02 July 2012

Second monitoring period: 03 July 2012 to 31 Dec 2013

Third monitoring period: 01 Jan 2014 to 31 Dec 2014

Fourth monitoring period: 01 Jan 2015 to 31 Dec 2015

Fifty monitoring period: 01 Jan 2016 to 31 Dec 2016

Sixty monitoring period: 01 Jan 2017to 31 Dec 2017

Date of registration: 03 July 2012

Project is in continuous operation.

4. Total emission reductions achieved in this monitoring period are 110,179tCO2e

A.2.	Project Participants

>>

| - Name of Party involved (*) - ((host) indicates a host Party) | - Private and/or public entity(ies) project participants (*) - (as applicable) | - Kindly indicate if the Party involved wishes to be considered as project participant (Yes/No) |
| --- | --- | --- |
| ### Kenya (host) | Private entity: - Tembea Youth Centre for Sustainable Development | No |
| ### Switzerland (Annex 1) | Private entity - myclimate Foundation | No |

A.3.	Location of the project activity:

>>

Country: Kenya

Province: Nyanza

County: Siaya

Coordinates: The County is located between the following coordinates: 0°24'08.52''S, 34°17'24.05''E to the south, 0°01'57'59''S, 34°00'31.65''E to the west,  0°19'04.01''N, 34°16'52.80''E to the north and 0°06'38.41''N, 34°33'16.82''E to the far east.

The coordinates of the town Ugunja, where the office of the project owner Tembea Youth Centre for Sustainable Development is located, are 00° 10' 59.88" N and 34° 17' 59.99" E.

Map 1: Divisions in Siaya County

A.4.	Technical description of the project

>>

The project currently produces and installs one type of efficient biomass stoves.

The project disseminates a rocket-type improved cook stove to replace the use of open fires for cooking. The efficient cook stoves are constructed using locally available materials, such as mud, bricks and sawdust. Local artisans are identified in the villages and trained in stove construction and household mobilisation.

Installed project rocket stove with two cooking units.

A.5.	Title, reference and version of the baseline and monitoring methodology applied to the project activity:

>>

The approved monitoring methodology applied to the project activity is Gold Standard methodology “Technologies and Practices to Displace Decentralized Thermal Energy Consumption (11/04/2011).” The reference is http://www.cdmgoldstandard.org/project-certification/gs-methodologies

A.6.	Registration date of the project activity:

>> 03 July 2012

A.7.	Crediting period of the project activity and related information (start date and choice of crediting period):

>> The start date of the crediting period is 01 January 2011.

A crediting period of 7 years with the option of renewal is chosen for the project activity

A.8.	Name of responsible person(s)/entity(ies):

>>

Jared Buoga, Tembea Youth Center for Sustainable Development

buoga.jared@tembeayouth.org

Job Orina, Tembea Youth Center for Sustainable Development

job.orina@tembeayouth.org

Tobias Hoeck, myclimate

tobias.hoeck@myclimate.org

SECTION B.	Implementation of the project activity

B.1.	Implementation status of the project activity

>>

- Start date of operations: 04 October, 2010

- Actual Operations: The project continuously installed efficient cook stoves since the start of project implementation. Since then a total of 44,156 project stoves have been installed. In this way the project could provide clean and efficient cooking to 205,105 persons. The project also continuously trained community members in the Community Savings and Loaning Methodology (CSL) and established to date a total of 1503 groups with 44,315 participants: of it there are 1257 supervised groups with 39,771 participants. 100% of all cook stoves installed where purchased through the CSL mechanism. This clearly shows how important this saving and loaning mechanism is for the dissemination and affordability of the cook stove.

Table 1: Annual stove installations

| Year | number of stoves |
| --- | --- |
| 2010 | 324 |
| 2011 | 4,662 |
| 2012 | 5,139 |
| 2013 | 5,187 |
| 2014 | 6,840 |
| 2015 | 14,186 |
| 2016 | 7,818 |
| 2017 | 6,940 |
| TOTAL | 51,097 |

Furthermore, the project trained 168 persons in efficient stove construction and conducted awareness and education events on efficient cooking and climate change.

Tembea supports a climate change education program that targets primary and secondary schools. In the monitoring period Tembea was able to implement the program in Siaya County and the entire Nyanza region. The following activities were accomplished;

- Development of Information and education communication materials

- Running a workshop that brought together various actors in Kenya and in climate education

- Community based trainings on climate change

- Support for climate change/environment clubs in schools through provision of vegetable seeds

- Establishment of tree nurseries in schools

The project’s awareness creation activities reached a total number of 3094 people.

- Impact on applicability of methodology: No events occurred during this monitoring period, which impact the applicability of the monitoring methodology.

B.2.	Revision of the monitoring plan

>>

The validated monitoring plan has not been revised.

Forward Action Request from Gold Standard 4rd issuance review:

As part of the next monitoring the PP shall provide evidence of unique users of 1320 duplicate data stoves for instance it shall provide names of women in polygamous families, names or pictures of end users using mobile number and address of relatives or friends to ensure uniqueness and verifiability of data. In case PP is unable to provide user data as requested then equivalent VER shall be deducted from the next verification for both this and next monitoring period.

Action taken

- The PP approached GS to enable them address the FAR gradually, the request was approved allowing the PP to close the FAR by the 6th verification.

- By the date of writing this report the PP had traced 1320 stove owners and changed details as expected. The process sought to identify the location of the stoves, the stove owners and stove users. The data has been presented in excel format for consideration.

- The corrections undertaken have been presented for action (170218_FAR list_ver 1)

We have met the outlined tasks by this 6th verification.

B.3.	Request for deviation applied to this monitoring period

>>

NA

B.4.	Notification or request of approval of changes

>>

NA

SECTION C.	Description of the monitoring system

>>

A detailed description of the monitoring system can be found in the latest version of the Monitoring Manual provided as a separate document. This includes roles and responsibilities, organizational structure, etc.

Monitoring coordination

Specific Personnel and Qualifications

| Name | Designation | qualification |
| --- | --- | --- |
| Job Orina | Internal monitoring manager | Bsc In Disaster Mitigation and Sustainable development, certificate in Low Carbond development (WBI) and monitoring & evaluation (UNPAN), long exepirience in data collection, analysis and report preparation as well long experience in the climate change sector. |
| Victor John Mondi | Data Manager/deputy manager | Bsc In Disaster Mitigation and sustainable development, long experience in data managment |
| Nicholas Ngesa | Project officer in charge of construction | Bachelor of Commerce |
| Joshua Omondi | Project officer in charge of CSL | Certifcate in project design and development and Certificate in Community saving and loaning |
| Erick Otieno | Field officer csl/stove construction | Certificate in Community Saving and Loaning |
| Sarah Sophy | Finance officer | Dilploma in Community development and social work, certificate in Accounting |
| Vincent Odour | Lead artisan | Long experience in stove construction, kenya secondary school certificate |

General Summary of Monitoring System:

Data management and storage

Tembea has developed internal mechanisms to ensure availability of data within and beyond the project period. All data used for monitoring is stored in soft and hard copies. Tembea uses cloud storage, back up systems as well as file cabins in the office to ensure safe keeping of the data.

Monitoring data collection tools and methodologies

The following approaches are used in collecting data for monitoring;

a) Office based

- Sales record: this is an excel file that is used to enter details about the stoves. The file enable entry on the data of sale, name of stove owner, location, postal address, telephone number, GPS coordinates, mode of use, stove type, stove number and other monitoring details.

- CSL database: this is a customized excel file that is used to analyze and store data on the community savings and loaning approach that is used to facilitate local communities to acquire cook stoves. The file capture the names of the groups, names and sex of the members, dates of formation, asset based information, loan information amongst others.

- Excel sheet for monitoring data: this is a template that is used to enter and store all the data collected from the field for monitoring surveys. The file captures the questions in the questionnaires and their varying responses. This is used to capture the sustainable development indicators that the project is promoting.

b) Field based

- Artisan Data sheet: this is a tool used by the artisan involved in the construction of the stoves in the field. They capture the following details; date of construction, name of stove user, sub-location, village, address and phone number.

- Lead Artisan construction summary sheet: This is a tool that has been developed to help lead artisans collect information on the stoves constructed. The template collects the date of construction, the constructing artisan information, stove owner name, contacts, stove number, mode of purchase, initial amount, GPS coordinates and lead artisans remarks.

- Transaction books for CSL: these are books that are used by the CSL groups to record their transactions. The book collect the details of the groups including, date of formation, group name, names of members, transaction procedures, loans information and meetings dates.

- Questionnaires: there are many questionnaires that are administered to monitor project progress. The Questionnaires include the one for monitoring and usage survey. They are all attached in the monitoring manual.

C) Data flow consistency and intervals

- Sales Record: the sales records is updated once a month. Every other Monday of the week the data manager receives data from the field and throughout the month QA/QC procedures are administered on the data.

- CSL database: is updated once a month. Throughout the month field officer and the project officer are involved in collecting and verifying data from the groups.

- Excel sheet for monitoring data: this is done once a year as is agreed upon with the project partners.

D) QA/QC measures

Tembea is responsible for ensuring data quality, the following measures are undertaken for the information described above;

- Tracking of data

- Use of SP/SPA

- Counter checking with field officer documents

- Review of group transaction books

- Review of financial records

- Counter checking of data

SECTION D.	Data and parameters

D.1. Data and parameters determined at registration and not monitored during the monitoring period, including default values and factors

| Data / Parameter: | EFb,co2 |
| --- | --- |
| Data unit: | tCO2/t_fuel |
| Description: | CO2 emission factor arising from use of wood-fuel in baseline scenario |
| Source of data used: | 2006 IPCC Guidelines for National Greenhouse Gas Inventories, Tables 1.2/2.5 |
| Value(s) : | 1.7472 tCO2/t wood |
| Indicate what the data are used for (Baseline/ Project/ Leakage emission calculations) | Default IPCC values for wood / wood waste are applied |
| Additional comment: |  |

| Data / Parameter: | EFb,non-co2 |
| --- | --- |
| Data unit: | tCO2/t_fuel |
| Description: | Non-CO2 emission factor arising from use of wood-fuel in baseline scenario |
| Source of data used: | 2006 IPCC Guidelines for National Greenhouse Gas Inventories, Table 2.5 |
| Value applied: | 0.1356 tCO2eq/t wood (from 01.01.2013 on) |
| Justification of the choice of data or description of measurement methods and procedures actually applied : | Default IPCC values for CH4 and N20 emissions for wood / wood waste are applied and summed. From 01.01.2013 on the following GWP100 are applied: 25 for CH4, 298 for N20. |
| Any comment: |  |

| Data / Parameter: | EFp,co2 |
| --- | --- |
| Data unit: | tCO2/t_fuel |
| Description: | CO2 emission factor arising from use of wood-fuel in project scenario |
| Source of data used: | 2006 IPCC Guidelines for National Greenhouse Gas Inventories, Tables 1.2/2.5 |
| Value applied: | 1.7472 tCO2/t wood (=112.0 tCO2/TJ * 0.0156 TJ/ t ) |
| Justification of the choice of data or description of measurement methods and procedures actually applied : | Default IPCC values for wood / wood waste are applied |
| Any comment: |  |

| Data / Parameter: | EFp,non-co2 |
| --- | --- |
| Data unit: | tCO2/t_fuel |
| Description: | Non-CO2 emission factor arising from use of wood-fuel in project scenario |
| Source of data used: | 2006 IPCC Guidelines for National Greenhouse Gas Inventories, Table 2.5 |
| Value applied: | 0.1356 tCO2eq/t wood (from 01.01.2013 on) |
| Justification of the choice of data or description of measurement methods and procedures actually applied : | Default IPCC values for CH4 and N20 emissions for wood / wood waste are applied and summed. From 01.01.2013 on the following GWP100 are applied: 25 for CH4, 298 for N20. |
| Any comment: |  |

| Data / Parameter: | fNRB,i,y |
| --- | --- |
| Data unit: | Fractional non-renewability (%) |
| Description: | Non-renewability status of woody biomass fuel in scenario I during year y |
| Source of data used: | CDM default value: http://cdm.unfccc.int/DNA/fNRB/index.html |
| Value applied: | 92% |
| Justification of the choice of data or description of measurement methods and procedures actually applied : | The CDM default value for fNRB published on the CDM website for Kenya and approved by the Kenyan DNA is applied. |
| Any comment: | The applied methodology states on page 25: “"The non-renewable biomass fraction is fixed based on the results of the NRB assessment. Over the course of a project activity the project proponent may at any time choose to re-examine renewability by conducting a new NRB assessment. In case of a renewal of the crediting period and as per GS rules, the NRB fraction must be reassessed as any other baseline parameters and updated in line with most recent data available". |

Since a fixed baseline is applied, the following baseline parameters are also known. They will not be monitored.

| Data / Parameter: | Pb,y |
| --- | --- |
| Data unit: | t_biomass/unit-year and t_biomass/unit-day |
| Description: | Quantity of woody biomass consumed in the baseline scenario in year y and per day in year y. |
| Source of data used: | BFT 2011 |
| Value applied: | 2.6645 t wood/year and 0.0073 t wood/day |
| Justification of the choice of data or description of measurement methods and procedures actually applied : | Estimated mean (justified because statistical analysis fits within 90/30 rule). |
| Any comment: |  |

The following project parameter from the PFT was also known at validation, but it is monitored and updated if needed during the crediting period.

| Data / Parameter: | Pp,y |
| --- | --- |
| Data unit: | t_biomass/unit-year and t_biomass/unit-day |
| Description: | Quantity of woody biomass consumed in the project scenario in year y and per day in year y. |
| Source of data used: | PFT 2015 |
| Value applied: | 1.3505 t wood/year and 0.0036t wood/day |
| Justification of the choice of data or description of measurement methods and procedures actually applied : | Estimated mean (justified because statistical analysis fits within 90/30 rule). |
| Any comment: | Results of the PFT 2011 were confirmed by PFT Update 2017 |

D.2. Data and parameters monitored

>> Since a fixed baseline is applied only project parameters but no baseline parameters are monitored.

| Data / Parameter: | Project technologies credited (units) |
| --- | --- |
| Data unit: | Number of stoves installed |
| Description: | Technologies in the project database/Total Sales Record for project scenario for the year y. |
| Measured /Calculated /Default: | Measured |
| Source of data: | Tembea sales records |
| Value(s) of monitored parameter: | Year; number of stoves. 2010; 324. 2011; 4,662. 2012; 5,139. 2013; 5,187. 2014; 6,840. 2015; 14,186. 2016; 7,818. 2017; 6,940. TOTAL; 51,097. |
| Indicate what the data are used for (Baseline/ Project/ Leakage emission calculations) | Calculation of technology days |
| Monitoring equipment (type, accuracy class, serial number, calibration frequency, date of last calibration, validity) | n.a. |
| Measuring/ Reading/ Recording frequency: | Continuously |
| Calculation method (if applicable): | The Total Sales Record is continuously populated with all sales of stoves installed since the start date 04 October 2010. The Total Sales Record for this monitoring period contains sales from 04 October 2010 to 31 December 2017. |
| QA/QC procedures applied: | Third party financial audit of stove sales activities |

| Data / Parameter: | Pp,y |
| --- | --- |
| Data unit: | t_biomass/unit-year and t_biomass/unit-day |
| Description: | Quantity of woody biomass consumed in the project scenario during year y |
| Measured /Calculated /Default: | We measured quantity of woody biomass consumed per unit-day and calculated to biomass/unit-year |
| Source of data: | PFT Update 2017 |
| Value(s) of monitored parameter: | 1.2732 t wood/year and 0.0035t wood/day |
| Indicate what the data are used for (Baseline/ Project/ Leakage emission calculations) | Project emission reduction calculations |
| Monitoring equipment (type, accuracy class, serial number, calibration frequency, date of last calibration, validity) | Digital weight scales to measure wood weight |
| Measuring/ Reading/ Recording frequency: | Once prior to verification and then every other year |
| Calculation method (if applicable): | Mean of wood biomass use of all selected households was calculated |
| QA/QC procedures applied: | Transparent data analysis and reporting |

| Data / Parameter: | Usage (Up,2) |
| --- | --- |
| Data unit: | Percentage |
| Description: | Usage rate in project scenario during year y |
| Measured /Calculated /Default: | Calculated |
| Source of data: | Usage Survey 2017 (see Usage/Monitoring Survey Report) |
| Value(s) of monitored parameter: | 95.1% |
| Indicate what the data are used for (Baseline/ Project/ Leakage emission calculations) | Project emission reduction calculations |
| Monitoring equipment (type, accuracy class, serial number, calibration frequency, date of last calibration, validity) | N.A. |
| Measuring/ Reading/ Recording frequency: | Every year |
| Calculation method (if applicable): | A single usage parameter is weighted to be representative of the quantity of project technologies of each age being credited in a given project scenario. See Project Database for details. |
| QA/QC procedures applied: | Random sampling of population |

| Data / Parameter: | Project Technology Days (Np,1) |
| --- | --- |
| Data unit: | Number of days |
| Description: | Cumulative number of technology days in the project database for project scenario |
| Measured /Calculated /Default: | Calculated |
| Source of data: | Sales record/Project database |
| Value(s) of monitored parameter: | 17,484,804 |
| Indicate what the data are used for (Baseline/ Project/ Leakage emission calculations) | Project emission reduction calculations |
| Monitoring equipment (type, accuracy class, serial number, calibration frequency, date of last calibration, validity) | N.A. |
| Measuring/ Reading/ Recording frequency: | Every year |
| Calculation method (if applicable): | The number of days between the installation date of each stove and the day before registration (defining the first monitoring period) was calculated then adjusted for the 21 days time period between date of sale and start of stove usage for households. |
| QA/QC procedures applied: | N.A. |

| Data / Parameter: | Leakage (LEp,y) |
| --- | --- |
| Data unit: | t_CO2eq per year |
| Description: | Leakage in project scenario during year y |
| Measured /Calculated /Default: | Calculated |
| Source of data: | PDD and Monitoring/Usage Survey 2017 |
| Value(s) of monitored parameter: | 0 Potential leakage effects were assessed at the stage of validation in 2012 and were considered insignificant. Further, results from Monitoring/Usage Survey conducted in 2017 showed no leakage effects. |
| Indicate what the data are used for (Baseline/ Project/ Leakage emission calculations) | Project emission reduction calculations |
| Monitoring equipment (type, accuracy class, serial number, calibration frequency, date of last calibration, validity) | N.A. |
| Measuring/ Reading/ Recording frequency: | Every other year |
| Calculation method (if applicable): |  |
| QA/QC procedures applied: | Random selection of surveyed households. |

| Data / Parameter: | Similar cook stove project activities in the project area |
| --- | --- |
| Data unit: | Number of projects and/or extent of overlap |
| Description: | List of similar cook stove projects and an assessment of how (e.g. target population, cook stove type, etc.) and to what degree overlap occurs |
| Measured /Calculated /Default: | Reported |
| Source of data: | Gold Standard registry, UNEP Risoe CDM Pipeline and other local sources. |
| Value(s) of monitored parameter: | 0 (no similar project activity was identified) |
| Indicate what the data are used for (Baseline/ Project/ Leakage emission calculations) | Avoid double counting |
| Monitoring equipment (type, accuracy class, serial number, calibration frequency, date of last calibration, validity) | N.A. |
| Measuring/ Reading/ Recording frequency: | Annually |
| Calculation method (if applicable): | N.A. |
| QA/QC procedures applied: | N.A. |

Sustainable Development Indicators:

| Data / Parameter: | SD 1) Air Quality |
| --- | --- |
| Data unit: | Number of households |
| Description: | # of positive comments from stove users |
| Measured /Calculated /Default: | Measured |
| Source of data: | Monitoring/Usage Survey 2017 |
| Value(s) of monitored parameter: | 100 % of households state improved indoor air quality |
| Indicate what the data are used for (Baseline/ Project/ Leakage emission calculations) | N.A. |
| Monitoring equipment (type, accuracy class, serial number, calibration frequency, date of last calibration, validity) | N.A. |
| Measuring/ Reading/ Recording frequency: | Every year |
| Calculation method (if applicable): | N.A. |
| QA/QC procedures applied: | Random sampling of population |

Summary: The target for this indicator was that all new stove users give positive comments about indoor air quality. We found that all (100%) stove users agree that the project stove generates less smoke emissions than the baseline stove. As specific indicators for improvements of air quality in the kitchen households mention less eye irritation (98%), it is easier to breathe (95%), less coughing (90%) and less headache (78%). Thus, it can be concluded that the project stove considerably improved indoor air quality and this has an effect on stove users’ health.

| Data / Parameter: | SD 2) Quality of employment |
| --- | --- |
| Data unit: | Number of persons |
| Description: | Number of artisans trained in stove construction |
| Measured /Calculated /Default: | Calculated |
| Source of data: | Training records |
| Value(s) of monitored parameter: | Number of artisans trained: 205(52% women, 48% men) |
| Indicate what the data are used for (Baseline/ Project/ Leakage emission calculations) | N.A. |
| Monitoring equipment (type, accuracy class, serial number, calibration frequency, date of last calibration, validity) | N.A. |
| Measuring/ Reading/ Recording frequency: | Every year |
| Calculation method (if applicable): | N.A. |
| QA/QC procedures applied: | N.A. |

| Data / Parameter: | SD 3) Livelihood of the poor |
| --- | --- |
| Data unit: | Time (hours/year), money (KSH/year) and number of persons |
| Description: | - Time and money savings due to reduced fuel consumption: Time and money spent on fuel per household per year compared to the baseline scenario. - Number of people in savings and loaning groups: - to acquire efficient cook stoves - to access medical care, pay for school fees, and other social services. |
| Measured /Calculated /Default: | Calculated |
| Source of data: | Household interviews for Monitoring Survey 2017. Record keeping of savings and loaning groups. |
| Value(s) of monitored parameter: | - Time and money savings due to reduced fuel consumption: 8,616 KES saved per household per year 280 hours’ time saved per household per year - Number of people in savings and loaning groups: - Total: 51,097 - 51,097 acquired efficient cook stoves - Purposes loans are used for: 35% for trade activities, 21% to access medical care, 25% for food, and 19% for other purposes. |
| Indicate what the data are used for (Baseline/ Project/ Leakage emission calculations) | N.A. |
| Monitoring equipment (type, accuracy class, serial number, calibration frequency, date of last calibration, validity) | N.A. |
| Measuring/ Reading/ Recording frequency: | Every year |
| Calculation method (if applicable): | N.A. |
| QA/QC procedures applied: | N.A. |

Summary:

The BS estimated an expenditure of KES 10,972 on fuel per year and 431 hours used in fuel gathering per year for the baseline scenario. The monitoring survey 2017 showed average annual expenditures of KES 2,356 on fuel and 151 hours for fuel collection. This results in average annual savings of KES 8,616 and 280 hours per household.

There are a total of 51,097persons participating in 1,579 Saving and Loaning Groups established to date: of it there are 1333 supervised groups with 46,533participants. 100% of participants used the CSL mechanism to purchase an efficient cook stove. Other common purposes loans are used for trade activities (35%), to access medical care (21%), for food (25%) and for other social services (19%).

| Data / Parameter: | SD 4) Access to affordable and clean energy services |
| --- | --- |
| Data unit: | Number of households |
| Description: | Number of households using efficient cook stoves. |
| Measured /Calculated /Default: | Measured |
| Source of data: | Sales Record/Project Database |
| Value(s) of monitored parameter: | 48593 |
| Indicate what the data are used for (Baseline/ Project/ Leakage emission calculations) | N.A. |
| Monitoring equipment (type, accuracy class, serial number, calibration frequency, date of last calibration, validity) | N.A. |
| Measuring/ Reading/ Recording frequency: | Every year |
| Calculation method (if applicable): | Number of stoves installed multiplied with latest usage rate (= 51,097 x 95.1) |
| QA/QC procedures applied: | N.A. |

Summary:

The project installed stoves into 44,156 households. Applying the latest usage rate of 92.9% this results in 41021 stoves in use. From the latest monitoring and usage survey we know that households have on average 5.0 members. Thus, the project provided clean and efficient cooking stoves for 205,105 persons.

| Data / Parameter: | SD 5) Human/institutional capacity |
| --- | --- |
| Data unit: | Number of women, number of persons |
| Description: | - Number of women trained: - number of women trained for saving and loaning groups (CSL) - number of animators (women) trained for awareness creation and education - Number of people reached through awareness creation on efficient cook stoves and climate change. |
| Measured /Calculated /Default: | Calculated |
| Source of data: | Training records |
| Value(s) of monitored parameter: | - Number of women trained: - 45,688 women trained for saving and loaning groups (CSL) - 82animators (59 women and 23 men) trained for awareness creation and education - 2,033people reached through awareness creation on efficient cook stoves and climate change. |
| Indicate what the data are used for (Baseline/ Project/ Leakage emission calculations) | N.A. |
| Monitoring equipment (type, accuracy class, serial number, calibration frequency, date of last calibration, validity) | N.A. |
| Measuring/ Reading/ Recording frequency: | Every year |
| Calculation method (if applicable): | N.A. |
| QA/QC procedures applied: | N.A. |

Summary:

The project trained 51,097 persons (of which 45,688 are women) on CLS methodology and at the same time created awareness for clean cook stoves. In addition 2,033 persons were reached through awareness creation events in this monitoring period.

| Data / Parameter: | SD 6) Quantitative employment and income generation |
| --- | --- |
| Data unit: | Number of persons |
| Description: | Number of people receiving income from project activity |
| Measured /Calculated /Default: | Measured |
| Source of data: | Employment records and financial records |
| Value(s) of monitored parameter: | - 79 artisans installing cook stoves - 18 project staff (field officers, coordinator, administration, project officers…) - 60 community mobilizers Total: 157 persons receiving income from project activity 100% are local employees |
| Indicate what the data are used for (Baseline/ Project/ Leakage emission calculations) | N.A. |
| Monitoring equipment (type, accuracy class, serial number, calibration frequency, date of last calibration, validity) | N.A. |
| Measuring/ Reading/ Recording frequency: | Every year |
| Calculation method (if applicable): | N.A. |
| QA/QC procedures applied: | N.A. |

The project aims at maintaining a close and continued contact with the stove users to ensure stove usage. This is important to receive feedback from the stove users and to advise on appropriate project stove application. One main instrument for this is the Community Savings & Loaning groups (CSL) approach. In addition also community mobilizers and environmental clubs in schools are crucial to reach out to households:

- The CSL groups play a very important role for the successful adoption and use of the project stove and discontinuation of the baseline technology. CSL groups meet on a weekly basis and provide a perfect framework for peer-to-peer support and knowhow exchange amongst stove users thus increasing use and adoption of the Tembea stoves. Further, Tembea staff attends CSL meetings of each group on a monthly basis. This is a good opportunity to get regular feedback from households on their experience with the project stove, to advise on appropriate stove usage and to discourage the use of the three stone fire.

- A network of community mobilizers visits stove users on a random basis to provide accompaniment/solidarity in decommissioning the traditional stoves. Regular reporting/feedback from the community mobilizers to lead artisans/project staff helps in gauging the level of discontinuation by stove users.

- The environmental clubs run by Tembea in schools in the project catchment area play a crucial role in sensitizing pupils/students in efficient stove usage and to discourage parents from using traditional stoves.

In addition a new awards scheme was recently introduced on effective and continuous use of Tembea stove during public awareness campaigns. Best stove users are awarded (e.g. with cooking pans or official certificate of recognition) during regular public awareness and education days as well as during visits by mobilizers.

The project monitors the use of baseline technology through monitoring/usage surveys.

SECTION E.	Emission reductions calculation

E.1.	Baseline emissions calculation

>> According to the applied methodology, there is no need to calculate baseline emissions separately. When the baseline fuel and the project fuel are the same and the baseline emission factor and project emission factor are considered the same, overall GHG reductions achieved by the project activity are calculated as follows (see applied methodology, page 14):

ERy = Σb,y (Np,y* Up,y* Pp,b,y* NCVb,fuel* (fNRB,b,y* EFfuel,CO2+EFfuel, nonCO2)) – LEp,y

Where:

Σb,y  = sum over all relevant (baseline b/project p) couples

Np,y = cumulative number of project technology days included in the project database for project     scenario p against the baseline scenario b in year y.

Up,y = cumulative usage rate for technologies in project scenario p in year y, based on cumulative adoption rate and drop off rate revealed by usage surveys (fraction)

Pp,b,y = Specific fuel savings for an individual technology of project p against an individual technology of baseline b in year y, in tons/day, as derived from the statistical analysis of the data collected from field tests.

NCVb,fuel = Net calorific value of the fuel that is substituted or reduced ((IPCC default for wood fuel, 0.015 TJ/ton)

fNRB,b,y = fraction of biomass used in year y for baseline scenario b that can be established as non-renewable biomass

EFfuel,CO2 = CO2 emission factor of the fuel that is substituted or reduced. 112 tCO2/TJ for wood/wood waste.

EFfuel, nonCO2 = Non-CO2 emission factor of the fuel that is reduced

LEp,y = leakage for project scenario p in year y (tCO2eq/yr)

The parameters NCVb,fuel and NCVp,fuel are not applicable to this project since EF is in units of tCO2/t_fuel (see methodology page 21). Therefore the formula applied is:

ERy = Σb,y (Np,y* Up,y* Pp,b,y*(fNRB,b,y* EFfuel,CO2+EFfuel, nonCO2)) – LEp,y

E.2.	Project emissions calculation

>> According to the applied methodology, there is no need to calculate project emissions separately. When the baseline fuel and the project fuel are the same and the baseline emission factor and project emission factor are considered the same, overall GHG reductions achieved by the project activity are calculated as follows (see applied methodology, page 14):

ERy = Σb,y (Np,y* Up,y* Pp,b,y* NCVb,fuel* (fNRB,b,y* EFfuel,CO2+EFfuel, nonCO2)) – LEp,y

Where:

Σb,y  = sum over all relevant (baseline b/project p) couples

Np,y = cumulative number of project technology days included in the project database for project     scenario p against the baseline scenario b in year y.

Up,y = cumulative usage rate for technologies in project scenario p in year y, based on cumulative adoption rate and drop off rate revealed by usage surveys (fraction)

Pp,b,y = Specific fuel savings for an individual technology of project p against an individual technology of baseline b in year y, in tons/day, as derived from the statistical analysis of the data collected from field tests.

NCVb,fuel = Net calorific value of the fuel that is substituted or reduced ((IPCC default for wood fuel, 0.015 TJ/ton)

fNRB,b,y = fraction of biomass used in year y for baseline scenario b that can be established as non-renewable biomass

EFfuel,CO2 = CO2 emission factor of the fuel that is substituted or reduced. 112 tCO2/TJ for wood/wood waste.

EFfuel, nonCO2 = Non-CO2 emission factor of the fuel that is reduced

LEp,y = leakage for project scenario p in year y (tCO2eq/yr)

The parameters NCVb,fuel and NCVp,fuel are not applicable to this project since EF is in units of tCO2/t_fuel (see methodology page 21). Therefore the formula applied is:

ERy = Σb,y (Np,y* Up,y* Pp,b,y*(fNRB,b,y* EFfuel,CO2+EFfuel, nonCO2)) – LEp,y

E.3.	Leakage calculation

>>According to PDD, no significant leakages are currently included.

Based on the monitoring conducted no leakages were identified in the possible leakage effects identified in PDD.  Leakage therefore is:

∑ LE1  = 0

E.4.	Emission reductions calculation / table

>> According to the applied methodology, we applied the formulae:

ERy = Σb,y (Np,y* Up,y* Pp,b,y* NCVb,fuel* (fNRB,b,y* EFfuel,CO2+EFfuel, nonCO2)) – LEp,y

Where:

Σb,y  = sum over all relevant (baseline b/project p) couples

Np,y = cumulative number of project technology days included in the project database for project     scenario p against the baseline scenario b in year y.

Up,y = cumulative usage rate for technologies in project scenario p in year y, based on cumulative adoption rate and drop off rate revealed by usage surveys (fraction)

Pp,b,y = Specific fuel savings for an individual technology of project p against an individual technology of baseline b in year y, in tons/day, as derived from the statistical analysis of the data collected from field tests.

NCVb,fuel = Net calorific value of the fuel that is substituted or reduced ((IPCC default for wood fuel, 0.015 TJ/ton)

fNRB,b,y = fraction of biomass used in year y for baseline scenario b that can be established as non-renewable biomass

EFfuel,CO2 = CO2 emission factor of the fuel that is substituted or reduced. 112 tCO2/TJ for wood/wood waste.

EFfuel, nonCO2 = Non-CO2 emission factor of the fuel that is reduced

LEp,y = leakage for project scenario p in year y (tCO2eq/yr)

The parameters NCVb,fuel and NCVp,fuel are not applicable to this project since EF in units of tCO2/t_fuel (see methodology page 21). Therefore the formula applied is:

ERy = Σb,y (Np,y* Up,y* Pp,b,y*(fNRB,b,y* EFfuel,CO2+EFfuel, nonCO2)) – LEp,y

The table below summarizes the values used in 2017 for the parameters of the applied formula:

| Parameter | Project Scenario |
| --- | --- |
| Baseline wood use (tons/day) | 0.0073 |
| Project wood use (tons/day) | 0.0035 |
| Pp,b,1: Fuel savings (tons/day) | 0.0038 |
| Fraction NRB | 0.92 |
| Up | 95.1 |
| Np | 17,484,804 |
| EFfuel,CO2 | 1.7472 |
| EFfuel, nonCO2 | 0.1356 |
| LEp | 0 |

The formula for emission reduction calculations including the values used for the parameters is:

ER2016  = 17,484,804*0.951 * 0.0038 * (0.92 * 1.7472 + 0.1356) – 0

Total ERs = ER2016 = 110,179

Achieved emission reductions in the monitoring period per calendar year:

| Year | ER (tCO2e) |
| --- | --- |
| 2017 | 109,431 |
| Total | 109,431 |

E.5.	Comparison of actual emission reductions with estimates in the CDM-PDD

>>

This section shall include a comparison of actual values of the emission reductions achieved during the monitoring period with the estimations in the registered CDM-PDD.

| Item | Values applied in ex-ante calculation of the registered CDM-PDD | Actual values reached during the monitoring period |
| --- | --- | --- |
| Emission reductions (tCO2e) | 2017: 82,500 | 2017: 110,179 |

E.6.	Remarks on difference from estimated value in the PDD

> Differences between ex ante estimation of ER in PDD and actual monitored emission reductions for first monitoring period are due to the following reasons:

- Increased installation in the previous year due to increased community uptake

- Adjustment values for project technology days in use were not applied during writing the PDD.

Annex 1

References

| No. | Description | Available at | File name |
| --- | --- | --- | --- |
| 1 | Applied methodology: “Technologies and Practices to Displace Decentralized Thermal Energy Consumption (11/04/2011).” | GS website: http://www.cdmgoldstandard.org/project-certification/gs-methodologies | - |
| 2 | Monitoring and Usage Survey Report 2017 | GS registry | 171120_Monitoring_Usage_Survey_Report_Tembe_V01.pdf |
| 3 | Monitoring and Usage Survey Data 2017 | GS registry | 171122_Monitoring_Usage_Survey_analysis_V02.xlsx |
| 4 | Monitoring Manual | GS registry | 120829_monitoring_manual_V02.pdf |
| 5 | PDD | GS registry | 120710_PDD_Tembea_V3_2.pdf |
| 6 | GS Passport | GS registry | 120710_GS_Passport_Tembea_V3_2.pdf |
| 7 | Project Database V01 | GS registry | 171120_Tembea_project_database_V01.xlsx |
| 8 | Tembea Monitoring report | GS registry | 171120_Tembea_monitoring_report_V01.pdf |

This figure is lower than total number of CSL participants, since the training is conducted at the beginning of a loaning cycle and further participants join the group later on.