Monitoring Report

###### PUBLICATION DATE  14.10.2020
VERSION  v. 1.1 
RELATED SUPPORT - TEMPLATE GUIDE Monitoring Report v. 1.1

This document contains the following Sections

KEY PROJECT INFORMATION

SECTION A. DESCRIPTION OF PROJECT

SECTION B. IMPLEMENTATION OF PROJECT

SECTION C. DESCRIPTION OF MONITORING SYSTEM APPLIED BY THE PROJECT

SECTION D. DATA AND PARAMETERS

SECTION E. CALCULATION OF SDG IMPACTS

SECTION F. SAFEGUARDS REPORTING

SECTION G. STAKEHOLDER INPUTS AND LEGAL DISPUTES

### KEY PROJECT INFORMATION

##### Programme of Activity Information – (delete below table if N.A.)

| GS ID of Programme | GS1340 |
| --- | --- |
| Title of Programme | Efficient cookstoves in Burkina Faso (PoA) |
| Version of POA-DD applicable to this monitoring report | 4 |
| Name and GS ID of fully Validated CPA/VPAs (i.e. non compliance check) | - GS1340 Efficient cookstoves in Burkina Faso – VPA-01 - tiipaalga F3PA cookstoves in Bam and Loroum (GS2456) - GS1340 Efficient cookstoves in Burkina Faso – VPA-02 - tiipaalga F3PA cookstoves in Bam and Loroum (GS3516) - GS1340 Efficient cookstoves in Burkina Faso – VPA-03 - tiipaalga F3PA cookstoves in Bam and Loroum (GS3517) - GS1340 Efficient cookstoves in Burkina Faso – VPA-04 - tiipaalga F3PA cookstoves in Bam and Loroum (GS3518) - GS1340 Efficient cookstoves in Burkina Faso – VPA-05 - tiipaalga F3PA cookstoves in Bam and Loroum (GS3519) - GS1340 Efficient cookstoves in Burkina Faso – VPA-06 - tiipaalga F3PA cookstoves in Bam and Loroum (GS3520) - GS1340 Efficient cookstoves in Burkina Faso – VPA-07 - tiipaalga F3PA cookstoves in Bam and Loroum (GS3521) - GS1340 Efficient cookstoves in Burkina Faso – VPA-08 - tiipaalga F3PA cookstoves in Bam and Loroum (GS3522) - GS1340 Efficient cookstoves in Burkina Faso – VPA-09 - tiipaalga F3PA cookstoves in Bam and Loroum (GS3523) - GS1340 Efficient cookstoves in Burkina Faso – VPA-10 - tiipaalga F3PA cookstoves in Bam and Loroum (GS3524) - GS1340 Efficient cookstoves in Burkina Faso – VPA-11– Tiipaalga – F3PA cookstoves in Kourwéogo (GS6152) - GS1340 Efficient cookstoves in Burkina Faso – VPA-12– Tiipaalga – F3PA cookstoves in Kourwéogo (GS6419) - GS1340 Efficient cookstoves in Burkina Faso – VPA-13– Tiipaalga – F3PA cookstoves in Kourwéogo (GS6420) - GS1340 Efficient cookstoves in Burkina Faso - VPA-14 – Improved cookstove F3PA project in Nahouri (GS10778) - GS1340 Efficient cookstoves in Burkina Faso - VPA-15 – Improved cookstove F3PA project in Nahouri (GS10779) - GS1340 Efficient cookstoves in Burkina Faso - VPA-16 – Improved cookstove F3PA project in Nahouri (GS10780) - GS1340 Efficient cookstoves in Burkina Faso - VPA-17 – Improved cookstove F3PA project in Nahouri (GS10781) - GS1340 Efficient cookstoves in Burkina Faso - VPA-18 – tiipaalga F3PA cookstoves in Center-South Protected Areas (GS10922) - GS1340 Efficient cookstoves in Burkina Faso - VPA-19 – tiipaalga F3PA cookstoves in Center-South Protected Areas (GS10923) - GS1340 Efficient cookstoves in Burkina Faso - VPA-20 – tiipaalga F3PA cookstoves in Center-South Protected Areas (GS10924) - GS1340 Efficient cookstoves in Burkina Faso - VPA-21 – tiipaalga F3PA cookstoves in Center-South Protected Areas (GS10925) - GS1340 Efficient cookstoves in Burkina Faso - VPA-22 – tiipaalga F3PA cookstoves in Center-South Protected Areas (GS10926) - GS1340 Efficient cookstoves in Burkina Faso - VPA-23 – tiipaalga F3PA cookstoves in Center-South Protected Areas (GS10927) - GS1340 Efficient cookstoves in Burkina Faso - VPA-24 – tiipaalga F3PA cookstoves in Center-South Protected Areas (GS10928) - GS1340 Efficient cookstoves in Burkina Faso – VPA-25 – Solidagro F3PA cookstoves in Passoré (GS11070) - GS1340 Efficient cookstoves in Burkina Faso – VPA-26 – Solidagro F3PA cookstoves in Passoré (GS11071) - GS1340 Efficient cookstoves in Burkina Faso – VPA-27 – Solidagro F3PA cookstoves in Passoré (GS11072) - GS1340 Efficient cookstoves in Burkina Faso – VPA-28 – Solidagro F3PA cookstoves in Passoré (GS11073) - GS1340 Efficient cookstoves in Burkina Faso – VPA-29 – Improved cookstove F3PA project in Nahouri (GS11074) |

##### Key Project Information

| GS ID (s) of Project (s) | GS6152 (VPA-11) GS6419 (VPA-12) GS6420 (VPA-13) |
| --- | --- |
| Title of the project (s) covered by monitoring report | GS1340 Efficient cookstoves in Burkina Faso – VPA-11– Tiipaalga – F3PA cookstoves in Kourwéogo (GS6152) GS1340 Efficient cookstoves in Burkina Faso – VPA-12– Tiipaalga – F3PA cookstoves in Kourwéogo (GS6419) GS1340 Efficient cookstoves in Burkina Faso – VPA-13– Tiipaalga – F3PA cookstoves in Kourwéogo (GS6420) |
| Version number of the PDD/VPA-DD (s) applicable to this monitoring report | GS6152 (VPA-11) : v.4 GS6419 (VPA-12) : v.4 GS6420 (VPA-13) : v.5 |
| Version number of the monitoring report | 2.0 |
| Completion date of the monitoring report | 16/03/2023 |
| Date of project design certification | GS6152 (VPA-11): 27/09/2019 GS6419 (VPA-12): 27/09/2019 GS6420 (VPA-13): 27/09/2019 |
| Date of Last Annual Report | 02/12/2022 |
| Monitoring period number | GS6152 (VPA-11): Monitoring period #4 GS6419 (VPA-12): Monitoring period #3 GS6420 (VPA-13): Monitoring period #2 |
| Duration of this monitoring period | GS6152 (VPA-11): 01/01/2021 to 31/12/2021 (inclusive of both dates) GS6419 (VPA-12): 01/01/2021 to 31/12/2021 (inclusive of both dates) GS6420 (VPA-13): 01/01/2021 to 31/12/2021 (inclusive of both dates) |
| Project Representative | Association tiipaalga CO2logic |
| Host Country | Burkina Faso |
| Activity Requirements applied | Community Services Activities Renewable Energy Activities Land Use and Forestry Activities/Risks & Capacities N.A. |
| Methodology (ies) applied and version number | The Gold Standard Simplified Methodology for Efficient Cookstoves - Version 1 |
| Product Requirements applied | GHG Emissions Reduction & Sequestration Renewable Energy Label N.A. |

##### Table 1 - Sustainable Development Contributions Achieved

| Sustainable Development Goals Targeted | SDG Impact | Amount Achieved | Units/ Products |
| --- | --- | --- | --- |
| SDG 13 | Emission reductions | VPA 11: 10,000 VPA 12: 9,829 VPA 13: 8,497 Total : 28,326 | VERs |
| SDG 3 | Proportion of households perceiving: - less often smoke levels - incidence of coughing - incidence of respiratory illness incidence of itchy eyes | 100% 100% 100% 100% | Percentage |
| SDG 4 | Number of training initiatives for staff involved in the programme | 1 | Number |
| SDG 4 | Number of workshops carried out for women for the group of VPA’s | 85 | Number |
| SDG 5 | Proportion of stove users perceiving reduced amount of time spent on fuel collection Proportion of stove users perceiving reduced amount of money spent on wood fuel purchase | 100% 100% | Percentage |
| SDG 7 | Number of F3PA efficient cookstoves disseminated for the group of VPA’s | VPA-11: 10,387 VPA-12: 10,165 VPA-13: 8,629 Total: 29,181 | Number |

##### Table 2 – Product Vintages

|  |  |  | Amount Achieved |
| --- | --- | --- | --- |
| No. VPA | Start Dates | End Dates | VERs |
| VPA 11 | 01/01/2021 | 31/12/2021 | 10,000 |
| VPA 12 | 01/01/2021 | 31/12/2021 | 9,829 |
| VPA 13 | 01/01/2021 | 31/12/2021 | 8,497 |

#### SECTION A. DESCRIPTION OF PROJECT

##### A.1. General description of project

The group of micro-scale VPA 11, VPA 12 and VPA 13 projects promotes the distribution and utilization of the mud made 3 stones efficient woodstove “F3PA” in the province of Kourwéogo in the region Plateau Central in the center of Burkina Faso. Those three microscale VPA’s were implemented together in the province of Kourwéogo between 2018 and 2020. The efficient F3PA cookstoves replaces the traditional stove whilst respecting the local three stone cooking culture. This is possible as the efficient F3PA cookstove, seen in the figure below, will integrate the three stones from each household inside its design. These three stones represent the pillar of the household’s marital union.

The improved technology F3PA is significantly more efficient than the traditional open fire three stone cooking method. The project will thus help reduce wood consumption by more than half in each household and therefore preserve the local forests and their biodiversity. This will also help combat the ever-increasing threat of desertification in the area. The F3PA has further benefits like the reduction of harmful smoke in the local rural village households and the reduction of time spent in collecting wood. The project does not consist a fuel switch as locally available wood is still being used.

Figure 1 Locally produced F3PA cookstove

Association tiipaalga, a local association in Burkina Faso, has been working on reforestation and agriculture since 2003. On the demand of the women and the urgent need to better protect woody resources, tiipaalga introduced a project of efficient cookstoves in Burkina Faso. Association tiipaalga adapted and improved an already existing efficient mud made cookstove model and attached importance to the monitoring system. This innovative distribution system is based on a tight collaboration with the women to ensure the training and monitoring in the villages.

The project’s approach involves training of women in the rural zones to build, use and maintain these efficient cookstoves themselves using local material. The training includes as well as education on hygienic usage and on the threat of climate change and health hazards related to the old cooking system and inform on the health and environmental benefits of using such efficient cookstoves. The distribution mechanism of the F3PA cookstove is based on 	pyramidal knowledge sharing approach. First, a certain number of female animators are identified by Association tiipaalga. It is ensured that they have the required level of training and skills to pass down their F3PA construction knowhow to the next level of the pyramid. The animators have the ground knowledge and understanding of the context in the intervention zone. Each animator will manage and train a certain number of leader women (Monitrice Endogène) in the various villages every year. These leader women are selected by the other women in the village and represent the more influential and knowledgeable members of the community who have the capacity to pass on their acquired understanding of F3PA construction skills. These leader women will thus educate and inform a specific quantity of women in the villages to build, use and maintain their own efficient F3PA cookstoves.

Figure 2 Distribution pyramid

The monitoring report applies to the F3PA efficient cookstove which is the primary technology disseminated and installed for households in the province Kourwéogo in the Plateau central region of Burkina Faso within VPA-11, VPA-12 and VPA-13.

During this monitoring period from 01/01/2021 to 31/12/2021, it is calculated that the group of three VPAs have generated 28,326 tonnes of CO2eq emissions reductions.

##### A.2. Location of project

Burkina Faso, province Kourwéogo. The project boundary of the current mirco-scale VPA are 4 out of the 5 municipalities located in the province in Kourwéogo in the Plateau Central region, which are Boussé, Niou, Toéghin and Sourgoubila.

Province Kourwéogo in Burkina Faso

Municipalities included in project

Figure 3 Location of the province of Kourwéogo with its 5 municipalities

Table 3 Project intervention area

| GS/VPA number | Country | Province | Municipality | Latitude | Longitude |
| --- | --- | --- | --- | --- | --- |
| GS6152 (VPA-11) GS6419 (VPA-12) GS6420 (VPA-13) | Burkina Faso | Kourwéogo | Boussé | 12° 39’ 38” N | 1° 53’ 32” E |
|  | Burkina Faso | Kourwéogo | Niou | 12° 46’ 08” N | 1° 56’ 11” E |
|  | Burkina Faso | Kourwéogo | Toéghin | 12° 48’ 58” N | 1° 43’ 35” E |
|  | Burkina Faso | Kourwéogo | Sourgoubila | 12° 25’ 03” N | 1° 48’ 25” E |

##### A.3. Reference of applied methodology

“The Gold Standard Simplified Methodology for Efficient Cookstoves”, version 1

##### A.4. Crediting period of project

GS6152 – VPA 11: 13/01/2018 – 12/01/2025 (7 years)

GS6419 – VPA-12: 21/01/2019 – 20/01/2026 (7 years)

GS6420 – VPA-13: 12/01/2020 – 11/01/2027 (7 years)

#### SECTION B. IMPLEMENTATION OF PROJECT

##### B.1. Description of implemented project

The implemented project is a group of three VPA’s, ie VPA-11 (GS6152), VPA-12 (GS6419) and VPA-13 (GS6420), which were implemented within three years between 2018 and 2020 (as according the PDD). The project activities have served the following number of households with F3PA efficient cookstoves with a corresponding calculated GHG offsets generated during the third monitoring period for VPA-11, second monitoring period for VPA-12 and first monitoring period for VPA-13 :

| GS/VPA number | Number of households | Dissemination calendar | Generated VER’s |
| --- | --- | --- | --- |
| GS6152 (VPA-11) | 3,436 | 13/01/2018 – 23/07/2018 | 10,000 |
| GS6419 (VPA-12) | 3,330 | 21/01/2019 – 27/06/2019 | 9,829 |
| GS6420 (VPA-13) | 3,174 | 12/01/2020 – 08/11/2020 | 8,497 |

B.1.1 Forward Action Requests

No FAR were raise during previous verification. For more details please consult verification report: ‘GS1340_GS6152_GS6419_GS6420_Verification_Report_SC_Approved’

##### B.2. Post-Design Certification changes

Not applicable.

B.2.1. Temporary deviations from the approved Monitoring & Reporting Plan, methodology or standardized baseline

Not applicable.

B.2.2. Corrections

Not applicable.

B.2.3. Changes to start date of crediting period

Not applicable.

B.2.4. Permanent changes from the Design Certified monitoring plan, applied methodology or applied standardized baseline

No permanent changes have been made for this monitoring period.

B.2.5. Changes to project design of approved project

No changes to the project design have been made during this monitoring period.

#### SECTION C. DESCRIPTION OF MONITORING SYSTEM APPLIED BY THE PROJECT

Process of unique identification of stove users:

Significant part of the households in the project area are polygamous. Most of the wives within a household included in the carbon project have a cookstove set of at least two F3PA efficient cookstoves of different sizes. The project cookstoves are single pot stoves. As every cooking pot size has its specific size of cookstove, different sizes of project cookstoves have been implemented according to the cooking habits of the stove users. The sizes of the cooking pots and so the cookstoves used in the VPA’s are 2, 3, 4, 5, 6, 7, 8, 10, 12 and 15 due to its frequency of utilization.  The women using different cookstove sets in a polygamous household are credited as one single household.

The individual identification of the micro scale – VPA’s is ensured with the identification of each household and each wife within the household using the project cookstoves by a unique serial number referring to the micro scale – VPA 11, VPA 12 or VPA 13. The syntax of the unique serial number is defined as GS1340-VPA-xx-yyyy/z, where (i) GS1340 is the Gold Standard number of the PoA “Efficient cookstoves in Burkina Faso” to which the VPA belongs, (ii) VPA-xx is the number of the VPA of the PoA, (iii) yyyy is the number of the household from 1 to 9999 and (iv) z is the number of the wife in the household from 1 to 9.

The following information is documented for each household of which each wife of the household (when polygamous) has replaced all traditional three stones cookstoves for domestic use with project cookstoves:

- Unique VPA ID number of each household and each wife within the household;

- Type and size of appliance (ex. F3PA – size 2);

- GPS Coordinates of the household;

- Name/Address/national ID Number/Mobile Number/Picture of wife with her project cookstoves;

- Stove installation date;

All data are stored in an electronic database using AKVO Flow software (www.akvo.org). The following files are raw data files of data stored in the cloud:

- ‘DR_Tiipaalga_VPA-11_HH_20220404’ & ‘DR_Tiipaalga_VPA-12_HH_20220404 & ‘DR_Tiipaalga_VPA-13_HH_20220404’: distribution records (DR) of households with the following data:

  - Identifier (Unique internal ID number);

  - GS number: GS PoA-nr / VPA-nr / Household nr;

  - Location info;

  - Data on head of household.

- ‘DR_Tiipaalga_VPA-11_ICS_20220404’ & ‘DR_Tiipaalga_VPA-12_ICS_20220404’ & ‘DR_Tiipaalga_VPA-13_ICS_20220404’: data on wives and type of stoves used per wife within the household with the following data:

  - Identifier (Unique internal ID number) which is the unique key to household info (‘DR_Tiipaalga_VPA-11_HH_20220404’ & ‘DR_Tiipaalga_VPA-12_HH_20220404’ & ‘DR_Tiipaalga_VPA-13_HH_20220404)’;

  - Identification data per wife: name, picture of wife with its stoves;

  - Data on stoves used per wife: size of stoves, installation dates of each stove, location of stoves, …

The start of the crediting period of each household is considered as the latest installation date of all stoves within the cooking sets of the different wives within the household (see file ‘Tiipaalga_DR_VPA-11_ICS_MP4_20220404_Recent date per HH’ & ‘Tiipaalga_DR_VPA-12_ICS_MP3_20220404_Recent date per HH’ & ‘Tiipaalga_DR_VPA-13_ICS_MP2_20220404_Recent date per HH’).). For each household the number of days in age group 0-1, age-group 1-2, age-group 2-3 and age-group 3-4 are calculated.

Data concerning double counting:

The project developer tiipaalga monitors any risks of double counting in this project, specifically determining whether any of the efficient cookstoves part of this project are counted in any other emission reduction project. There are other registered GHG reduction projects in Burkina Faso promoting the F3PA efficient cookstoves. Among those, one project is implemented in the north of Burkina Faso, in the provinces of Bam and Loroum, ie VPA-01 to 10 GS2456 and GS3516 to GS3524 under the same PoA GS1340. A second project under this PoA is located in the province Nahouri in the Center South region (VPA-14 to 17 and 29, GS10778 to GS10781 and GS11074). A third project is located in the provinces of Nahouri and Zoundwéogo (VPA-18 to 24, GS10922 to GS10928).  Those projects are also monitored by tiipaalga, that makes sure there is no double counting. Lastly, there is also a project in Passoré (VPA 25-28, GS11070 to GS11073) under the same PoA lead by Solidagro, but this is in a different province than the current project and therefore there is no risk of double counting. Association tiipaalga is also aware of another cookstove project in Burkina Faso registered under the Gold Standard. However, this project promotes a different kind of stoves rather for non-household cooking purposes.

Association tiipaalga continues to monitor whether any other projects with same technology exist. In such cases, tiipaalga will make every effort to compare total distribution databases with the other project developer(s) to ensure that there is no overlap. In addition, the project continues to use all legal documentation outlined in the VPA-DD to ensure legal ownership over offsets, a step that further avoids double counting.

Data processing and archiving:

Distribution records are captured with Smartphones using the AKVO Flow software with necessary pictures and GPS coordinates. Monitoring data are extracted to Microsoft Excel for analyses. Records will be kept for two years after the project activity is completed.

Quality assurance and quality control measures

Quality control rules were developed for the F3PA efficient cookstoves and were explained during the stove construction trainings. Quality control rules included in the construction protocol of the F3PA efficient cookstove are among others:

- It should be possible to move a hand between the wall of the cookstove and the cookpot;

- The height of the wood entrance of the cookstove is at most half the total height of the cookstove;

- The distance between the cooking pot and floor of cookstove should either not be higher than a hand or the handles of the cooking pot should be higher than the wall of the cookstove.

During monitoring surveys, the F3PA efficient cookstoves are evaluated with the following statuses:

- Green: the construction norms have been respected and the F3PA efficient cookstove doesn’t need any maintenance action. It means that (i) the outer surface of the F3PA efficient cookstove are not washed by rain, (ii) there is no hole in the floor of the efficient stove;

- Orange: the construction norms have been respected, but the efficient cookstove has not well been maintained. It concerns F3PA efficient cookstoves (i) from which the outer surface has been washed by rain and that need re-polishing; (ii) that have been constructed more than two years ago and that need re-polishing of internal and outer surface; (iii) that have some cracks, but which are external and do not affect the quality of the combustion of the wood. For these cases the application of the reparation protocol will fix the cracks and repolish the surface, so that the status will turn again into green.

- Red: the construction norms are not respected, or the F3PA efficient cookstoves have not been well maintained or used in a proper way. If the F3PA efficient cookstove has not been well constructed, the cookstove will not be registered in the initial database. An example of poor usage is sitting before the entrance of the stove. The combustion will not happen in an appropriate way and the risk that the cookstove will crack at the level of the entrance is high. A red cookstove needs to be reconstructed.

Orange cookstoves will be monitored, so that the maintenance activities of these stoves bring them again in green status. If these maintenance activities do not take place, they probably will in the short term, get into the red status. Orange F3PA efficient cookstoves are considered to have the same efficiency as the green F3PA efficient cookstoves of the same age group. The red F3PA efficient cookstoves will be monitored, as long as the cookstove has not been reconstructed. After reconstruction, the status of the F3PA efficient cookstove will turn to green. Red F3PA efficient cookstoves do not have the targeted efficiency of the F3PA efficient cookstove anymore, and so are not considered in the emission reduction calculations as long as they are not reconstructed.

Diagram of Responsibilities

As there are several entities involved in initial data collection and project monitoring it is important to clearly designate the relationships between and responsibilities of entities. Association tiipaalga will act as the managing entity of the project and be responsible for communication with the Gold Standard Foundation and the Objective Observer. CO2logic provides technical support in the initial data collection, data quality assurance, monitoring, drafting of the verification report. A diagram of responsibilities is shown here below.

Figure 4 Diagram of responsibilities

Employees from Association tiipaalga train leader women, who are selected by the women in the villages, for the construction, the use and maintenance of mud made 3 stones efficient woodstoves. These leader women conduct the same training sessions with the women in their villages and help them to build the cookstoves. tiipaalga employees in collaboration with the leader women, will perform quality checks and collect the initial stove data.

End user information is collected by tiipaalga agents with mobile smartphone, and is consolidated into an electronic database in the cloud from which project monitoring can be conducted. The central electronic database is accessible by tiipaalga and CO2logic. Data can be made available through data extraction. CO2logic performs quality checks.

Monitoring tasks such as monitoring surveys are managed by tiipaalga and realized by the tiipaalga surveyors. They are the most capable of collecting these data because of extensive knowledge of the technology and end-users. The tiipaalga surveyors are trained and retrained prior conducting surveys during a 2-days training session conducted from 19/03/2022 till 20/03/2022. CO2logic assists tiipaalga in cross-checking the integrity of data with other variables to ensure consistency and accuracy, and to avoid mistakes.

#### SECTION D. DATA AND PARAMETERS

##### D.1. Data and parameters fixed ex ante or at renewal of crediting period

| Relevant SDG Indicator | SDG 13, Climate Action |
| --- | --- |
| Data/parameter: | EFb,fuel,CO2 |
| Unit | tCO2/ton of firewood |
| Description | CO2 emission factor arising from use of firewood in baseline scenario |
| Source of data | IPCC default value, table 1.4 of Chapter 1 of Vol.2, 2006 IPCC Guidelines for National Greenhouse Gas Inventories |
| Value(s) applied) | 1.747 tCO2/ton of firewood |
| Choice of data or measurement methods and procedures | As defined under the Gold Standard Simplified Methodology for Efficient Cookstoves v1.0 |
| Purpose of data | Calculation of emission reductions |
| Additional comments | N.A. |

| Relevant SDG Indicator | SDG 13, Climate Action |
| --- | --- |
| Data/parameter: | EFb,fuel,non_CO2 |
| Unit | tCO2/ton of firewood |
| Description | Non-CO2 emission factor arising from use of firewood in baseline scenario |
| Source of data | IPCC Fifth Assessment Report: Climate Change (IPCC AR5) |
| Value(s) applied) | 0.58 tCO2/ton of firewood |
| Choice of data or measurement methods and procedures | From rule update: Applicability of Global Warming Potential for Gold Standard For The Global Goals Projects (06/03/2021). |
| Purpose of data | Calculation of emission reductions |
| Additional comments | N.A. |

| Relevant SDG Indicator | SDG 13, Climate Action |
| --- | --- |
| Data/parameter: | Ƞb |
| Unit | Fraction |
| Description | Efficiency of the cookstove being used in the baseline scenario |
| Source of data | Gold Standard Simplified Methodology for Efficient Cookstoves v1.0 |
| Value(s) applied) | 0.10 |
| Choice of data or measurement methods and procedures | As defined under the Gold Standard Simplified Methodology for Efficient Cookstoves v1.0 |
| Purpose of data | Calculation of emission reductions |
| Additional comments | N.A. |

| Relevant SDG Indicator | SDG 13, Climate Action |
| --- | --- |
| Data/parameter: | Ƞp |
| Unit | Fraction |
| Description | Efficiency of the cookstove being used in the project scenario |
| Source of data | Determined following the Water Boiling Test Protocol |
| Value(s) applied) | 0.234 |
| Choice of data or measurement methods and procedures | As defined under the Gold Standard Simplified Methodology for Efficient Cookstoves v1.0 |
| Purpose of data | Calculation of emission reductions |
| Additional comments | For each wife of one household included in the VPA, at least two efficient cookstoves of the defined project sizes 2, 3, 4, 5, 6, 7, 8, 10, 12 and 15 will be installed according the local cooking habits. Each size of project cookstove is tested according to the WBT protocol. To determine the project cookstove efficiency of one particular size, three sample runs have been carried out on one randomly selected project cookstove. The average of the three results is taken as the efficiency for the project cookstove of this particular size. The lowest value of project cookstove efficiency of the various sizes is taken as reference value for the efficiency of the cookstoves being used in the project scenario to calculate the emission reductions. The project cookstove efficiency in the year y ƞp,y will be determined using the discount factor DFƞ to account for efficiency loss of project cookstove per year of operation (fraction). |

| Relevant SDG Indicator | SDG 13, Climate Action |
| --- | --- |
| Data/parameter: | fNRB,b,y |
| Unit | Fractional non-renewability |
| Description | Non-renewability status of wood fuel during year y |
| Source of data | Default NRB value provided by the CDM executive board and endorsed by the host country DNA (http://cdm.unfccc.int/DNA/fNRB/docs/burkina.pdf) |
| Value(s) applied) | 0.90 |
| Choice of data or measurement methods and procedures | As defined under the Gold Standard Simplified Methodology for Efficient Cookstoves v1.0 |
| Purpose of data | Calculation of emission reductions |
| Additional comments | The project activity may choose to update the fNRB,b,y during the crediting period |

| Relevant SDG Indicator | SDG 13, Climate Action |
| --- | --- |
| Data/parameter: | Bb,y |
| Unit | Tonnes firewood per household per year |
| Description | Firewood consumption for cooking in the baseline |
| Source of data | Average household size within the project boundary is determined using data from the latest population census in 2006 in the National institute for Statistics and Demography. The minimum service level or the default baseline biomass consumption according the Gold Standard Simplified Methodology for Efficient Cookstoves v1.0 is set at 0.5 tonnes per capita per year. |
| Value(s) applied) | Ex ante: - 3.32 for the whole project boundary Ex post: - 3.24 for the municipality of Boussé - 3.27 for the municipality of Niou - 3.45 for the municipality of Sourgoubila - 3.33 for the municipality of Toeghin |
| Choice of data or measurement methods and procedures | Option c of Minimum service level has been chosen to determine the firewood consumption for cooking in the baseline as detailed information per municipality on average household size is available in the “Recensement général de la population et l’habitation (RGPH) de 2006 du Burkina Faso” or the general census of the population and habitat of Burkina Faso, table 15. Other sources show that the population in Burkina Faso is growing each year . This means that the used value can be considered as conservative to calculate the CO2 reduction emissions. |
| Purpose of data | Calculation of emission reductions |
| Additional comments | The average household size across the four municipalities of the project boundary is 6.65, whereas for the municipalities Boussé 6.49, Niou 6.53, Sourgoubila 6.91 and Toeghin 6.67: Municipality; # HH; #persons; #pers/HH; Bb,y. Boussé; 6,682; 43,352; 6.49; 3.25. Niou; 4,133; 26,998; 6.53; 3.27. Sourgoubila; 5,654; 39,044; 6.91; 3.46. Toeghin; 2,475; 16,500; 6.67; 3.34. Total; 18,944; 125,894; 6.65; 3.32. Based on the minimum service level of 0.5 tonnes per capita per year the average annual consumption of firewood per household is estimated at 3.32 tonnes/year for the total project boundary and more specifically for the municipality of Boussé 3.25 tonnes/year, for Niou 3.27 tonnes/year, for Sourgoubila 3.46 tonnes/year and for Toeghin 3.34 tonnes/year. |

##### D.2 Data and parameters monitored

| Relevant SDG Indicator | SDG 3, Good health and well-being |
| --- | --- |
| Data/ Parameter | Smoke level reduction Incidence of coughing reduction Incidence of respiratory illness reduction Incidence of itchy eyes reduction |
| Unit | Fraction |
| Description | Proportion of households perceiving less often smoke levels, incidence of coughing, incidence of respiratory illness, incidence of itchy eyes since the implementation of F3PA efficient cookstoves |
| Source of data | Monitoring surveys. See document ‘GS1340_MS_VPA-11-12-13_Vintage 2021’ |
| Value(s) applied | Smoke level reduction: 100% Incidence of coughing reduction: 100% Incidence of respiratory illness reduction: 100% Incidence of itchy eyes reduction: 100% |
| Measurement methods and procedure | The measurement of the parameter is based on qualitative information collected during Monitoring surveys. The end users are asked whether, since they have the F3PA efficient cookstoves, smoke level occurs for each more often, less often among the family members or the situation has not changed. The same is asked for coughing, respiratory illnesses and itchy eyes. |
| Monitoring frequency | Annual |
| QA/QC procedures | The data is analyzed in the monitoring report and raw data of the Monitoring surveys is made available for review. |
| Purpose of data | Calculation of the parameter “Proportion of households perceiving less often smoke levels, incidence of coughing, incidence of respiratory illness, incidence of itchy eyes” |
| Additional comment | See Document ‘GS1340_MS_VPA-11-12-13_Vintage 2021’ |

| Relevant SDG Indicator | SDG 4, Quality Education |
| --- | --- |
| Data/ Parameter | Number of trainings initiatives for staff involved in the programme |
| Unit | Number |
| Description | Number of trainings initiatives for staff involved in the programme in order to increase their performance in the programme |
| Source of data | Reports regarding the training initiatives See original document: ‘Compte rendu de formation des enqueteurs verification An4_FR’ and its translation in English : ‘Compte rendu de formation des enqueteurs verification An4_EN translation’. |
| Value(s) applied | 1 |
| Measurement methods and procedure | The list of training initiatives during the corresponding monitoring period |
| Monitoring frequency | Annual |
| QA/QC procedures | The data is analyzed in the reports regarding the training initiatives, which is made available for review |
| Purpose of data | Calculation of the parameter “Number of trainings initiatives for staff involved in the programme” |
| Additional comment | Starting from the 19th of March 2022, three surveyors received a 2-days training under the supervision of three members of Association tiipaalga. The purpose of the training was to teach the fundamentals of the usage survey with a theoretical and practical phase and to familiarize with the used tools (Akvo software). The surveyors were ultimately able to collect quality data from the households on the field for the purpose of the monitoring survey. More details regarding the training and the participants list can be found in document: ‘Compte rendu de formation des enqueteurs verification An4_EN translation’. |

| Relevant SDG Indicator | SDG 4, Quality Education |
| --- | --- |
| Data/ Parameter | Number of workshops carried out for women |
| Unit | Number |
| Description | Number of workshops carried out for women in order to increase their empowerment |
| Source of data | Reports regarding the workshops carried out for women. See document ‘Bilan des activités - sensibilisation et formation - VPA 11-12-13_2021_with comments’. |
| Value(s) applied | 85 |
| Measurement methods and procedure | The list of workshops carried out for women during the corresponding monitoring period |
| Monitoring frequency | Annual |
| QA/QC procedures | The data is analyzed in the reports regarding the workshops carried out for women, which is made available for review |
| Purpose of data | Calculation of the parameter “Number of workshops carried out for women” |
| Additional comment | Two types of workshops were organized: i) sensitization workshops; and ii) (re-)training workshops of leader women for the construction of F3PA efficient cookstoves. During the sensibilization sessions stove users are informed about the advantages of the project cookstoves for the climate and desertification of the project area, tiipaalga’s activities, on how the banco or mud should be prepared for the construction of the cookstoves etc. During training or retraining sessions leader women are trained on how the F3PA efficient cookstoves should be constructed. In total, 3,506 participants were present during the workshops. A complete summary of the different sessions can be found in document : ‘Bilan des activités - sensibilisation et formation - VPA 11-12-13_2021_with comments’. The following table gives an overview of the number of sessions and number of participants: Municipality; Sensitization sessions; Training workshops of leader women; Total. # sessions; # participants; # sessions; # participants; # sessions; # Participants. Toèghin; 17; 691; 6; 307; 23; 998. Niou; 15; 576; 10; 380; 25; 956. Boussé; 11; 518; 2; 52; 13; 570. Sougoubila; 16; 706; 8; 276; 24; 982. Total; 59; 2,491; 26; 1,015; 85; 3,506. Evidences of the sensitisation and training sessions (participants lists) can be sent upon request. |

| Relevant SDG Indicator | SDG 5, Gender equality |
| --- | --- |
| Data/ Parameter | Proportion of stove users perceiving reduced amount of time spent on wood fuel collection and/or reduced amount of money spent on wood fuel purchase |
| Unit | Fraction |
| Description | Proportion of stove users perceiving reduced time spent on wood fuel collection and/or reduced money spent on wood fuel purchase since the implementation of the F3PA efficient cookstoves |
| Source of data | Monitoring surveys. See document: ‘GS1340_MS_VPA-11-12-13_Vintage 2021’ |
| Value(s) applied | Reduced amount of time spent on wood fuel collection: 100% - Domestic tasksp: 97% - Income generating activitiesp: 56% - Field labourp: 40% - Gardeningp: 2% - Participation to a literacy programp: <1% - Community workp: <1% - Doing nothingp: 12% - Religious activitiesp: <1% - Leisurep: 2% Reduced amount of money spent on wood fuel purchase: 100% - School feesp: 46% - Purchase of medical drugsp: 38% - Purchase of foodp: 62% - Income generating activitiesp: 15% - Savingsp : 38% |
| Measurement methods and procedure | The measurement of the parameter is based on qualitative information collected during Monitoring surveys. The end users are asked whether, since they have the F3PA efficient cookstoves, they spent more, less time to collect the wood or the situation has not changed. In case of purchase wood fuel, the end users are asked they spent more, less money on the purchase of wood fuel or the situation has not changed. |
| Monitoring frequency | Annual |
| QA/QC procedures | The data is analyzed in the monitoring report and raw data of the Monitoring surveys is made available for review. |
| Purpose of data | Calculation of the parameter “Proportion of stove users perceiving reduced amount of time spent on wood fuel collection and/or reduced amount of money spent on wood fuel purchase” |
| Additional comment | N.A. |

| Relevant SDG Indicator | SDG 7, Affordable and clean energy |
| --- | --- |
| Data/ Parameter | Number of F3PA efficient cookstoves disseminated |
| Unit | Number |
| Description | Number of F3PA efficient cookstoves included in the project database for project scenario p |
| Source of data | Project database. See documents ‘DR_Tiipaalga_VPA-11_ICS_20220404’ & ‘DR_Tiipaalga_VPA-12_ICS_20220404’ & ‘DR_Tiipaalga_VPA-13_ICS_20220404’ |
| Value(s) applied | VPA 11: 10,387 VPA 12: 10,165 VPA 13: 8,629 Total: 29,181 |
| Measurement methods and procedure | The project database provides a list of end-users with number of F3PA efficient cookstoves per end-user. |
| Monitoring frequency | Continuous |
| QA/QC procedures | The data is analyzed in the monitoring report and Project database is made available for review. |
| Purpose of data | Calculation of the parameter “Number of F3PA efficient cookstoves disseminated” |
| Additional comment | N.A. |

| Relevant SDG Indicator | SDG 13, Climate action |
| --- | --- |
| Data/ Parameter | Up,1 |
| Unit | Percentage |
| Description | Usage rate in project scenario p during year 1 |
| Source of data | Annual usage/monitoring survey. See document ‘GS1340_MS_VPA-11-12-13_Vintage 2021’/Tab ‘Analysis’. |
| Value(s) applied | 76.19% |
| Measurement methods and procedure | The measurement of the usage rate is based on qualitative information collected in the usage/monitoring survey. A question concerning the current use of the technology is asked to each end user of the sample and is validated by the observation of the surveyor in order to determine the usage rate of each technology age category. |
| Monitoring frequency | Annual |
| QA/QC procedures | Transparent data analysis and reporting |
| Purpose of data | Calculation of emission reductions |
| Additional comment | - A usage parameter is derived for each age group of project cookstove being credited. The usage survey will determine if the project cookstoves can be considered as ‘in use’ or ‘not in use’ and if the project cookstoves are in ‘good condition’ or ‘not in good condition’. The record keeping system of this VPA is at household level (with household number) for which all baseline cookstove set(s) (comprising of several traditional three stone cookstoves for domestic use) have been replaced by project cookstove set(s). Cookstove set(s) within a household can only be considered ‘in use’ if all the cookstoves in the set(s) (in polygamous households all cookstoves of all cookstove sets of all women in the household) are being used. Similarly, cookstove set(s) can only be considered in ‘good condition’ as long as all cookstoves within the cookstove set(s) (in polygamous households all cookstoves of all cookstove sets of all women in the household) are in a ‘good condition’. - At the sampling date (04/04/2022), no households recorded in the database belonged in AG 0-1. This is because the latest installed cookstove in the project was distributed on the 08/11/2020 (household: ‘VPA 13 - Zouda Antoinette - 4099 - ouedraogo moussa’), hence 1.4 years since the sampling date. To still account for a usage factor for the technology.days in AG0-1 during the monitoring period, PD decided to use the parameter Up,y of the next age-group, namely AG1-2. This approach is deemed conservative since according to project experience, older cookstoves tend to have lower usage rates. Hence, the associated issuances within AG0-1 are expected to be lower. |

| Relevant SDG Indicator | SDG 13, Climate action |
| --- | --- |
| Data/ Parameter | Up,2 |
| Unit | Percentage |
| Description | Usage rate in project scenario p during year 2 |
| Source of data | Annual usage/monitoring survey. See document ‘GS1340_MS_VPA-11-12-13_Vintage 2021’/Tab ‘Analysis’. |
| Value(s) applied | 76.19% |
| Measurement methods and procedure | The measurement of the usage rate is based on qualitative information collected in the usage/monitoring survey. A question concerning the current use of the technology is asked to each end user of the sample and is validated by the observation of the surveyor in order to determine the usage rate of each technology age category. |
| Monitoring frequency | Annual |
| QA/QC procedures | Transparent data analysis and reporting |
| Purpose of data | Calculation of emission reductions |
| Additional comment | - A usage parameter is derived for each age group of project cookstove being credited. The usage survey will determine if the project cookstoves can be considered as ‘in use’ or ‘not in use’ and if the project cookstoves are in ‘good condition’ or ‘not in good condition’. The record keeping system of this VPA is at household level (with household number) for which all baseline cookstove set(s) (comprising of several traditional three stone cookstoves for domestic use) have been replaced by project cookstove set(s). Cookstove set(s) within a household can only be considered ‘in use’ if all the cookstoves in the set(s) (in polygamous households all cookstoves of all cookstove sets of all women in the household) are being used. Similarly, cookstove set(s) can only be considered in ‘good condition’ as long as all cookstoves within the cookstove set(s) (in polygamous households all cookstoves of all cookstove sets of all women in the household) are in a ‘good condition’. - Compared to other age-group and previous project experience, the usage rate for AG1-2 is abnormally low. This low rate would be due to insufficient field monitoring of the use, maintenance and protection of F3PAs by the management team of the two municipalities concerned (Niou and Boussé). In 2020, the Animator (cf. Figure 2 Distribution pyramid) responsible for capacity building and monitoring of F3PAs in VPA-13 (most recently established) was redeployed to reinforce another tiipaalga team in the province of Zoundwéogo in the Centre-Sud region (GS1340/GS10922-10928), which affected field monitoring activities. This has also impacted on the functions of the leader women (“monitrices endogènes” or “ME”) and has been reflected in the state of the cookstoves of the municipalities concerned. The time taken by the new Animator to take charge of the project intervention area worked to the disadvantage of the main VPA-13 cookstoves encountered in the municipalities of Boussé and Niou. The intensification of sensitisation, support and monitoring activities is continuing with the aim of increasing the capacity of the MEs to provide better care for women beneficiaries in the households covered by the project. |

| Relevant SDG Indicator | SDG 13, Climate action |
| --- | --- |
| Data/ Parameter | Up,3 |
| Unit | Percentage |
| Description | Usage rate in project scenario p during year 3 |
| Source of data | Annual usage/monitoring survey. See document ‘GS1340_MS_VPA-11-12-13_Vintage 2021’/Tab ‘Analysis’. |
| Value(s) applied | 85.32% |
| Measurement methods and procedure | The measurement of the usage rate is based on qualitative information collected in the usage/monitoring survey. A question concerning the current use of the technology is asked to each end user of the sample and is validated by the observation of the surveyor in order to determine the usage rate of each technology age category. |
| Monitoring frequency | Annual |
| QA/QC procedures | Transparent data analysis and reporting |
| Purpose of data | Calculation of emission reductions |
| Additional comment | A usage parameter is derived for each age group of project cookstove being credited. The usage survey will determine if the project cookstoves can be considered as ‘in use’ or ‘not in use’ and if the project cookstoves are in ‘good condition’ or ‘not in good condition’. The record keeping system of this VPA is at household level (with household number) for which all baseline cookstove set(s) (comprising of several traditional three stone cookstoves for domestic use) have been replaced by project cookstove set(s). Cookstove set(s) within a household can only be considered ‘in use’ if all the cookstoves in the set(s) (in polygamous households all cookstoves of all cookstove sets of all women in the household) are being used. Similarly, cookstove set(s) can only be considered in ‘good condition’ as long as all cookstoves within the cookstove set(s) (in polygamous households all cookstoves of all cookstove sets of all women in the household) are in a ‘good condition’. |

| Relevant SDG Indicator | SDG 13, Climate action |
| --- | --- |
| Data/ Parameter | Up,4 |
| Unit | Percentage |
| Description | Usage rate in project scenario p during year 4 |
| Source of data | Annual usage/monitoring survey. See document ‘GS1340_MS_VPA-11-12-13_Vintage 2021’/Tab ‘Analysis’. |
| Value(s) applied | 90.99% |
| Measurement methods and procedure | The measurement of the usage rate is based on qualitative information collected in the usage/monitoring survey. A question concerning the current use of the technology is asked to each end user of the sample and is validated by the observation of the surveyor in order to determine the usage rate of each technology age category. |
| Monitoring frequency | Annual |
| QA/QC procedures | Transparent data analysis and reporting |
| Purpose of data | Calculation of emission reductions |
| Additional comment | A usage parameter is derived for each age group of project cookstove being credited. The usage survey will determine if the project cookstoves can be considered as ‘in use’ or ‘not in use’ and if the project cookstoves are in ‘good condition’ or ‘not in good condition’. The record keeping system of this VPA is at household level (with household number) for which all baseline cookstove set(s) (comprising of several traditional three stone cookstoves for domestic use) have been replaced by project cookstove set(s). Cookstove set(s) within a household can only be considered ‘in use’ if all the cookstoves in the set(s) (in polygamous households all cookstoves of all cookstove sets of all women in the household) are being used. Similarly, cookstove set(s) can only be considered in ‘good condition’ as long as all cookstoves within the cookstove set(s) (in polygamous households all cookstoves of all cookstove sets of all women in the household) are in a ‘good condition’. |

| Relevant SDG Indicator | SDG 13, Climate action |
| --- | --- |
| Data/ Parameter | Np,1 |
| Unit | Number of households included in the project (Units), based on days of usage of age group 0-1 during the monitoring period related to one year. |
| Description | Household in the project database for project scenario p through year i for which all baseline cookstove set(s) (comprising of several traditional three stone cookstoves for domestic use) have been replaced by project cookstove set(s). |
| Source of data | Project database. See documents: ‘Tiipaalga_DR_VPA-11_ICS_MP4_20220404_Recent date per HH’ ‘Tiipaalga_DR_VPA-12_ICS_MP3_20220404_Recent date per HH’ ‘Tiipaalga_DR_VPA-13_ICS_MP2_20220404_Recent date per HH’ . |
| Value(s) applied | VPA 11: 0 VPA 12: 0 VPA 13: 1,018 Total: 1,018 |
| Measurement methods and procedure | For the determination of the number of usage days at household level for age group 0-1 during the corresponding monitoring period, the latest start day of use of all constructed F3PA efficient cookstoves within the household will be taken in order to have conservative approach. Number of households included in the project (Units) are calculated based on days of usage of age group 0-1 during the corresponding monitoring period related to one year. |
| Monitoring frequency | Annual |
| QA/QC procedures | Transparent data analysis and reporting |
| Purpose of data | Calculation of emission reductions |
| Additional comment | A part of the households in the project area of the VPA are polygamous. Each wife of the household included in the carbon project must have at least two F3PA efficient cookstoves. This is a local cooking requirement as one is for the Mush “Tô”, the other for the sauce “Sauce”. Additional cookstoves could be used for boiling water or preparing the soup. All the traditional three stone cookstoves for domestic use will be replaced by the F3PA efficient cookstoves. This means that according to the needs of the household, an un-predetermined number of project cookstoves will be constructed and used at household level. As the quantity of firewood consumed in the baseline is determined at household level, the number of households will be monitored instead of project cookstoves to determine the emissions reductions. Women will be trained by the Tiipaalga instructors or leader women to build the project cookstoves themselves using local materials according to a strict construction protocol. In tight collaboration of the project coordinator, the instructor and the leader women the logistical management, quality assurance of the project cookstoves according to the construction protocol and the management of the project database recording all constructed project cookstoves will be ensured. |

| Relevant SDG Indicator | SDG 13, Climate action |
| --- | --- |
| Data/ Parameter | Np,2 |
| Unit | Number of households included in the project (Units), based on days of usage of age group 1-2 during the monitoring period related to one year. |
| Description | Household in the project database for project scenario p through year i for which all baseline cookstove set(s) (comprising of several traditional three stone cookstoves for domestic use) have been replaced by project cookstove set(s). |
| Source of data | Project database. See documents: ‘Tiipaalga_DR_VPA-11_ICS_MP4_20220404_Recent date per HH’ ‘Tiipaalga_DR_VPA-12_ICS_MP3_20220404_Recent date per HH’ ‘Tiipaalga_DR_VPA-13_ICS_MP2_20220404_Recent date per HH’ . |
| Value(s) applied | VPA 11: 0 VPA 12: 834 VPA 13: 2,156 Total: 2,991 |
| Measurement methods and procedure | For the determination of the number of usage days at household level for age group 1-2 during the corresponding monitoring period, the latest start day of use of all constructed F3PA efficient cookstoves within the household will be taken in order to have conservative approach. Number of households included in the project (Units) are calculated based on days of usage of age group 1-2 during the corresponding monitoring period related to one year. |
| Monitoring frequency | Annual |
| QA/QC procedures | Transparent data analysis and reporting |
| Purpose of data | Calculation of emission reductions |
| Additional comment | A part of the households in the project area of the VPA are polygamous. Each wife of the household included in the carbon project must have at least two F3PA efficient cookstoves. This is a local cooking requirement as one is for the Mush “Tô”, the other for the sauce “Sauce”. Additional cookstoves could be used for boiling water or preparing the soup. All the traditional three stone cookstoves for domestic use will be replaced by the F3PA efficient cookstoves. This means that according to the needs of the household, an un-predetermined number of project cookstoves will be constructed and used at household level. As the quantity of firewood consumed in the baseline is determined at household level, the number of households will be monitored instead of project cookstoves to determine the emissions reductions. Women will be trained by the Tiipaalga instructors or leader women to build the project cookstoves themselves using local materials according to a strict construction protocol. In tight collaboration of the project coordinator, the instructor and the leader women the logistical management, quality assurance of the project cookstoves according to the construction protocol and the management of the project database recording all constructed project cookstoves will be ensured. |

| Relevant SDG Indicator | SDG 13, Climate action |
| --- | --- |
| Data/ Parameter | Np,3 |
| Unit | Number of households included in the project (Units), based on days of usage of age group 2-3 during the monitoring period related to one year. |
| Description | Household in the project database for project scenario p through year i for which all baseline cookstove set(s) (comprising of several traditional three stone cookstoves for domestic use) have been replaced by project cookstove set(s). |
| Source of data | Project database. See documents: ‘Tiipaalga_DR_VPA-11_ICS_MP4_20220404_Recent date per HH’ ‘Tiipaalga_DR_VPA-12_ICS_MP3_20220404_Recent date per HH’ ‘Tiipaalga_DR_VPA-13_ICS_MP2_20220404_Recent date per HH’ . |
| Value(s) applied | VPA 11: 1,079 VPA 12: 2,496 VPA 13: 0 Total: 3,574 |
| Measurement methods and procedure | For the determination of the number of usage days at household level for age group 2-3 during the corresponding monitoring period, the latest start day of use of all constructed F3PA efficient cookstoves within the household will be taken in order to have conservative approach. Number of households included in the project (Units) are calculated based on days of usage of age group 2-3 during the corresponding monitoring period related to one year. |
| Monitoring frequency | Annual |
| QA/QC procedures | Transparent data analysis and reporting |
| Purpose of data | Calculation of emission reductions |
| Additional comment | A part of the households in the project area of the VPA are polygamous. Each wife of the household included in the carbon project must have at least two F3PA efficient cookstoves. This is a local cooking requirement as one is for the Mush “Tô”, the other for the sauce “Sauce”. Additional cookstoves could be used for boiling water or preparing the soup. All the traditional three stone cookstoves for domestic use will be replaced by the F3PA efficient cookstoves. This means that according to the needs of the household, an un-predetermined number of project cookstoves will be constructed and used at household level. As the quantity of firewood consumed in the baseline is determined at household level, the number of households will be monitored instead of project cookstoves to determine the emissions reductions. Women will be trained by the Tiipaalga instructors or leader women to build the project cookstoves themselves using local materials according to a strict construction protocol. In tight collaboration of the project coordinator, the instructor and the leader women the logistical management, quality assurance of the project cookstoves according to the construction protocol and the management of the project database recording all constructed project cookstoves will be ensured. |

| Relevant SDG Indicator | SDG 13, Climate action |
| --- | --- |
| Data/ Parameter | Np,4 |
| Unit | Number of households included in the project (Units), based on days of usage of age group 3-4 during the monitoring period related to one year. |
| Description | Household in the project database for project scenario p through year i for which all baseline cookstove set(s) (comprising of several traditional three stone cookstoves for domestic use) have been replaced by project cookstove set(s). |
| Source of data | Project database. See documents: ‘Tiipaalga_DR_VPA-11_ICS_MP4_20220404_Recent date per HH’ ‘Tiipaalga_DR_VPA-12_ICS_MP3_20220404_Recent date per HH’ ‘Tiipaalga_DR_VPA-13_ICS_MP2_20220404_Recent date per HH’ . |
| Value(s) applied | VPA 11: 2,357 VPA 12: 0 VPA 13: 0 Total: 2,357 |
| Measurement methods and procedure | For the determination of the number of usage days at household level for age group 3-4 during the corresponding monitoring period, the latest start day of use of all constructed F3PA efficient cookstoves within the household will be taken in order to have conservative approach. Number of households included in the project (Units) are calculated based on days of usage of age group 3-4 during the corresponding monitoring period related to one year. |
| Monitoring frequency | Annual |
| QA/QC procedures | Transparent data analysis and reporting |
| Purpose of data | Calculation of emission reductions |
| Additional comment | A part of the households in the project area of the VPA are polygamous. Each wife of the household included in the carbon project must have at least two F3PA efficient cookstoves. This is a local cooking requirement as one is for the Mush “Tô”, the other for the sauce “Sauce”. Additional cookstoves could be used for boiling water or preparing the soup. All the traditional three stone cookstoves for domestic use will be replaced by the F3PA efficient cookstoves. This means that according to the needs of the household, an un-predetermined number of project cookstoves will be constructed and used at household level. As the quantity of firewood consumed in the baseline is determined at household level, the number of households will be monitored instead of project cookstoves to determine the emissions reductions. Women will be trained by the Tiipaalga instructors or leader women to build the project cookstoves themselves using local materials according to a strict construction protocol. In tight collaboration of the project coordinator, the instructor and the leader women the logistical management, quality assurance of the project cookstoves according to the construction protocol and the management of the project database recording all constructed project cookstoves will be ensured. |

| Relevant SDG Indicator | SDG 13, Climate action |
| --- | --- |
| Data/ Parameter | DFƞ |
| Unit | Fraction |
| Description | Discount factor to account for efficiency loss of project stoves |
| Source of data | Gold Standard Simplified Methodology for Efficient Cookstoves v1.0 |
| Value(s) applied | Default value: 0.99 i.e., 1 % efficiency loss per year |
| Measurement methods and procedure | N.A. |
| Monitoring frequency | N.A. |
| QA/QC procedures | N.A. |
| Purpose of data | Calculation of emission reductions |
| Additional comment | N.A. |

| Relevant SDG Indicator | SDG 13, Climate action |
| --- | --- |
| Data/ Parameter | DFb,stove,1 |
| Unit | Percentage |
| Description | Discount factor to account for the baseline stove use in project scenario p during the year 1 |
| Source of data | Monitoring data. See document ‘GS1340_MS_VPA-11-12-13_Vintage 2021’. |
| Value(s) applied | 4.52% |
| Measurement methods and procedure | The measurement of the discount factor to account for the baseline stove use is based on qualitative information collected in the usage/monitoring survey. A question concerning the current use of the baseline technology is asked to each end user of the sample and is validated by the observation of the surveyor in order to determine the discount factor to account for the baseline stove use in project scenario p of each technology age category. |
| Monitoring frequency | Annual |
| QA/QC procedures | Transparent data analysis and reporting |
| Purpose of data | Calculation of emission reductions |
| Additional comment | - The discount factor for the baseline-stove shall be determined based on the number of meals cooked using the baseline stove. The required information shall be captured through sample surveys carried out following a random sampling approach for age-group 0-1 of the project stove. The impact of seasonal variation on use of baseline stove should be considered as part of the monitoring survey. The survey format for sample question to capture this information is described in the Monitoring Plan. In case of polygamous households the discount factor shall be determined for each cookstove set and the highest value of all cookstove sets within the household shall be used as representative discount factor for the household. - At the sampling date (04/04/2022), no households recorded in the database belonged in AG 0-1. This is because the latest installed cookstove in the project was distributed on the 08/11/2020 (household: ‘VPA 13 - Zouda Antoinette - 4099 - ouedraogo moussa’), hence 1.4 years since the sampling date. To still account for a discount factor DFb,stove,1 for the technology.days in AG0-1 during the monitoring period, PD decided to use the parameter of the next age-group, namely AG1-2. This approach is deemed conservative since according to project experience, older cookstoves tend to have higher discount factor DFb,stove. Hence, the associated issuances within AG0-1 are expected to be lower. |

| Relevant SDG Indicator | SDG 13, Climate action |
| --- | --- |
| Data/ Parameter | DFb,stove,2 |
| Unit | Percentage |
| Description | Discount factor to account for the baseline stove use in project scenario p during the year 2 |
| Source of data | Monitoring data. See document ‘GS1340_MS_VPA-11-12-13_Vintage 2021’. |
| Value(s) applied | 4.52% |
| Measurement methods and procedure | The measurement of the discount factor to account for the baseline stove use is based on qualitative information collected in the usage/monitoring survey. A question concerning the current use of the baseline technology is asked to each end user of the sample and is validated by the observation of the surveyor in order to determine the discount factor to account for the baseline stove use in project scenario p of each technology age category. |
| Monitoring frequency | Annual |
| QA/QC procedures | Transparent data analysis and reporting |
| Purpose of data | Calculation of emission reductions |
| Additional comment | - The discount factor for the baseline-stove shall be determined based on the number of meals cooked using the baseline stove. The required information shall be captured through sample surveys carried out following a random sampling approach for age-group 1-2 of the project stove. The impact of seasonal variation on use of baseline stove should be considered as part of the monitoring survey. The survey format for sample question to capture this information is described in the Monitoring Plan. In case of polygamous households the discount factor shall be determined for each cookstove set and the highest value of all cookstove sets within the household shall be used as representative discount factor for the household. - Compared to other age-group and previous project experience, the discount factor DFb,stove for AG1-2 is abnormally high. This low rate would be due to insufficient field monitoring of the use, maintenance and protection of F3PAs by the management team of the two municipalities concerned (Niou and Boussé). In 2020, the Animator (cf. Figure 2 Distribution pyramid) responsible for capacity building and monitoring of F3PAs in VPA-13 (most recently established) was redeployed to reinforce another tiipaalga team in the province of Zoundwéogo in the Centre-Sud region (GS1340/GS10922-10928), which affected field monitoring activities. This has also impacted on the functions of the leader women (“monitrices endogènes” or “ME”) and has been reflected in the state of the cookstoves of the municipalities concerned. The time taken by the new Animator to take charge of the project intervention area worked to the disadvantage of the main VPA-13 cookstoves encountered in the municipalities of Boussé and Niou. The intensification of sensitisation, support and monitoring activities is continuing with the aim of increasing the capacity of the MEs to provide better care for women beneficiaries in the households covered by the project. |

| Relevant SDG Indicator | SDG 13, Climate action |
| --- | --- |
| Data/ Parameter | DFb,stove,3 |
| Unit | Percentage |
| Description | Discount factor to account for the baseline stove use in project scenario p during the year 3 |
| Source of data | Monitoring data. See document ‘GS1340_MS_VPA-11-12-13_Vintage 2021’. |
| Value(s) applied | 2.0% |
| Measurement methods and procedure | The measurement of the discount factor to account for the baseline stove use is based on qualitative information collected in the usage/monitoring survey. A question concerning the current use of the baseline technology is asked to each end user of the sample and is validated by the observation of the surveyor in order to determine the discount factor to account for the baseline stove use in project scenario p of each technology age category. |
| Monitoring frequency | Annual |
| QA/QC procedures | Transparent data analysis and reporting |
| Purpose of data | Calculation of emission reductions |
| Additional comment | The discount factor for the baseline-stove shall be determined based on the number of meals cooked using the baseline stove. The required information shall be captured through sample surveys carried out following a random sampling approach for age-group 2-3 of the project stove. The impact of seasonal variation on use of baseline stove should be considered as part of the monitoring survey. The survey format for sample question to capture this information is described in the Monitoring Plan. In case of polygamous households the discount factor shall be determined for each cookstove set and the highest value of all cookstove sets within the household shall be used as representative discount factor for the household. |

| Relevant SDG Indicator | SDG 13, Climate action |
| --- | --- |
| Data/ Parameter | DFb,stove,4 |
| Unit | Percentage |
| Description | Discount factor to account for the baseline stove use in project scenario p during the year 4 |
| Source of data | Monitoring data. See document ‘GS1340_MS_VPA-11-12-13_Vintage 2021’. |
| Value(s) applied | 1.23% |
| Measurement methods and procedure | The measurement of the discount factor to account for the baseline stove use is based on qualitative information collected in the usage/monitoring survey. A question concerning the current use of the baseline technology is asked to each end user of the sample and is validated by the observation of the surveyor in order to determine the discount factor to account for the baseline stove use in project scenario p of each technology age category. |
| Monitoring frequency | Annual |
| QA/QC procedures | Transparent data analysis and reporting |
| Purpose of data | Calculation of emission reductions |
| Additional comment | The discount factor for the baseline-stove shall be determined based on the number of meals cooked using the baseline stove. The required information shall be captured through sample surveys carried out following a random sampling approach for age-group 3-4 of the project stove. The impact of seasonal variation on use of baseline stove should be considered as part of the monitoring survey. The survey format for sample question to capture this information is described in the Monitoring Plan. In case of polygamous households the discount factor shall be determined for each cookstove set and the highest value of all cookstove sets within the household shall be used as representative discount factor for the household. |

| Relevant SDG Indicator | SDG 13, Climate Action |
| --- | --- |
| Data/ Parameter | Number of tCO2e reduced by the project |
| Unit | Ton of CO2e |
| Description | Number of tCO2e reduced thanks to the implementation of the project during the corresponding monitoring period. |
| Measured/calculated/default | Measured |
| Source of data | ER calculations: see documents : ‘GS 1340 - VPA 11 - ER_MP4’ ‘GS 1340 - VPA 12 - ER_MP3’ ‘GS 1340 - VPA 13 - ER_MP2’ |
| Value(s) of monitored parameter | VPA 11: 10,000 (11,068) VPA 12: 9,829 VPA 13: 8,497 Total: 28,326 |
| Monitoring equipment | N.A. |
| Measuring/reading/recording frequency | Annual |
| Calculation method (if applicable) | See section E.4 |
| QA/QC procedures | Transparent data analysis and reporting |
| Purpose of data | Calculation of emission reductions |
| Additional comments |  |

##### D.3. Comparison of monitored parameters with last monitoring period

| Data/Parameter | Value obtained in this monitoring period | Value obtained last monitoring period |
| --- | --- | --- |
| SDG 13: Number of tCO2e reduced by the project | VPA 11: 10,000 VPA 12: 9,829 VPA 13: 8,497 Total : 28,326 | VPA 11: 9,486 VPA 12: 9,752 VPA 13: 6,946 Total : 26,184 |
| SDG 13: Up,1 Up,2 Up,3 Up,4 DFb,stove,1 DFb,stove,2 DFb,stove,3 DFb,stove,4 | 76.19% 76.19% 85.32% 90.99% 4.52% 4.52% 2.00% 1.23% | 90% 79% 77% N.A. 1.08% 0.88% 1.89% N.A. |
| SDG 3: Proportion of households perceiving: - less often smoke levels - incidence of coughing - incidence of respiratory illness - incidence of itchy eyes | 100% 100% 100% 100% | 100% 100% 100% 100% |
| SDG 4: Number of training initiatives for staff involved in the programme | 1 | 1 |
| SDG 4: Number of workshops carried out for women for the group of VPA’s | 85 | 75 |
| SDG 5: Proportion of stove users perceiving reduced amount of time spent on fuel collection Proportion of stove users perceiving reduced amount of money spent on wood fuel purchase | 100% 100% | 100% 100% |
| SDG 7: Number of F3PA efficient cookstoves disseminated for the group of VPA’s | VPA-11: 10,387 VPA-12: 10,165 VPA-13: 8,629 Total: 29,181 | VPA-11: 10,387 VPA-12: 10,165 VPA-13: 8,629 Total: 29,181 |

##### D.4. Implementation of sampling plan

In parallel with the distribution of the F3PA efficient cookstoves, and as per monitoring plan in the respective registered VPA-DD’s (VPA-11, VPA-12 & VPA-13), tiipaalga conducted the following monitoring activities:

| Date | Activity | Purpose |
| --- | --- | --- |
| Ongoing | Project database | Establish total distribution record to track number of households for which all baseline cookstove set(s) (comprising of several traditional three stone cookstoves for domestic use) have been replaced by project cookstove set(s) |
| From 17/04/2022 to 09/05/2022 | Monitoring survey | (i) To establish single usage rate factor of age group 0-1, age group 1-2, age group 2-3 and age-group 3-4 based on if the project cookstoves can be considered as ‘in use’ or ‘not in use’ and if the project cookstoves are in ‘good condition’ or ‘not in good condition’; (ii) To establish single discount factor age group 0-1, age group 1-2, age group 2-3 and age group 3-4 to account for the baseline stove use; (iii) To measure the parameters regarding SDG 3 and SDG 5. |

The parameters which need to be monitored through surveys for the VPA are (i) Up,y Usage rate in project scenario p during year y; and (ii) DFb,stove,y Discount factor to account for the baseline stove use in project scenario p during the year y. A single survey with cross sampling of households has been undertaken using a single random sampling plan. The sample size is calculated for the population of VPA-11, VPA-12 and VPA-13, using the sampling guidelines described below.

The number of households of which each wife of the household (when polygamous) has replaced all traditional three stones cookstoves for domestic use with project cookstoves, is recorded in the project database (see data base records file). Only the households recorded in the database are part of the project activity.

Since the project activities started in January 2018, there are four age groups, i.e. 0-1 age group, 1-2 age group, 2-3 age group and 3-4 age group. The start of the crediting period of each household is considered as the latest installation date of all stoves within the cooking sets of the different wives within the household (see files ‘DR_Tiipaalga_VPA-11_ICS_20220404’ & ‘DR_Tiipaalga_VPA-12_ICS_20220404’ & ‘DR_Tiipaalga_VPA-13_ICS_20220404’). For each household the number of technology-days during MP are calculated per age group: (i) age group 0-1 (i.e. installation date + 365days), (ii) age group 1-2 (i.e. installation date + 2*365), (iii) age group 2-3 (i.e. installation date + 3*365), (iv) age group 3-4 (i.e. installation date + 4*365). The number of households per age-group are determined after cumulation of the technology-days per age group of the households in the project database divided by the number of days in a year, i.e. 365 days. At the sampling date (04/04/2022), no households recorded in the database belonged in AG 0-1. This is because the latest installed cookstove in the project was distributed on the 08/11/2020 (household: ‘VPA 13 - Zouda Antoinette - 4099 - ouedraogo moussa’), hence 1.4 years since the sampling date. To still account for parameter Up,y and DFb,y for the technology.days in AG0-1 during the monitoring period, PD decided to use the parameters of the next age-group, namely AG1-2. This approach is deemed conservative since according to project experience, older cookstoves tend to have lower usage rates and higher discount factor DFb,y. Hence, the associated issuances within AG0-1 are expected to be lower.

The minimum household sample size of each age group is determined according to the following guidelines (according the Gold Standard Simplified Methodology for Efficient Cookstoves v1.0):

•	Project target population < 300: Minimum sample size 30;

•	Project target population 300 to 1,000: Minimum sample size 10 % of group size;

•	Project target population > 1,000: Minimum sample size 100.

As the number of recorded households for VPA-11, VPA-12 and VPA-13 per age-group is more than 1,000, the minimum sample size per age-group is 100. For this monitoring survey the household size was set at 110 households for AG 2-3 and AG 3-4 and 210 for AG 0-1-2 (see file ‘Tiipaalga_MS_Sampling_VPA-11-12-13_Vintage 2021_20220404’). The method of selecting households for the sample list for the monitoring survey is random sampling using the online random sequence generator randomdraws (see file ‘Tiipaalga_MS_Sampling_VPA-11-12-13_Vintage 2021_20220404’). For all parameters that are monitored via sampling it is understood that only the age of the project cookstove has an influence. Therefore, no geographic representativeness is deemed necessary for the selection of users participating in the sample groups. The monitoring surveys are performed by user interviews. Only people older than 18 years are interviewed.

The questions used during the survey are presented in the file ‘GS1340_Monitoring Survey form_VPA-11-12-13 Vintage 2021’. Apart from information for the sustainable development indicators, the survey has been built up in order to collect reliable data to calculate the usage rate Up,y per age group and the discount factor to account for the baseline stove use DFb,stove,y per age group.

The file ‘Tiipaalga_MS_Sampling_VPA-11-12-13_Vintage 2021_20220404’ contains the 430 at random selected households across VPA-11, VPA-12 and VPA-13.

The file ‘GS1340_MS_VPA-11-12-13_Vintage 2021’ of the monitoring survey contains the following data in worksheet “Group 2”:

- Identifier (Unique internal ID number) which is the unique key of household info;

- Identification data per wife: name, picture of wife with it stoves;

- Data on stoves used per wife: size of stoves, installation dates of each stove, location of stoves, frequency of usage, condition of stove …;

- Data on cooking habits during dry and wet season;

- Data related to sustainable indicators.

Based on this information the usage rate Up,y is calculated per household in column V and the discount factor to account for the baseline stove use DFb,stove,y per households in column AW. The worksheet “Analysis” contains the evaluated parameters usage rate Up,y and discount factor to account for the baseline stove use DFb,stove,y per age group.

Out of the 430 at random selected households for the different age-groups, thirty-seven (37) households have not been surveyed for the following reasons:

| Display Name | Reason |
| --- | --- |
| VPA 12 -3017- TAPSOBA ISZAK | Household moved outside project intervention area |
| VPA 11 -3608- SEBOGO ANBROISE | Divorced woman and household members have broken up |
| VPA 11 -3581- SEBOGO EMIL | Household moved outside project intervention area |
| VPA 13 -204- OUEDRAOGO PIGA MARIE | Woman very old and can no longer repair cookstoves are also broken and not rebuilt |
| VPA 12 -2007- OUEDRAOGO ARZOUMA FREDERIC | Household moved outside project intervention area |
| VPA 13 -1648- SAWADOGO ALBERT | F3PA broken and not rebuilt |
| VPA 13 -1639- GUELBEOGO NORAOGO PROSPER | F3PA broken and not rebuilt |
| VPA 12 -122- OUEDRAOGO ABDOU | F3PA broken and not rebuilt |
| VPA 13 -2313- OUEDRAOGO IDRISSA | Household moved outside project intervention area |
| VPA 12 -23- OUEDRAOGO SAiDOU | F3PA broken and not rebuilt |
| VPA 12 -25- OUEDRAOGO PIERRE | F3PA broken and not rebuilt |
| VPA 12 -136- OUEDRAOGO ARSEL | F3PA broken and not rebuilt |
| VPA 13 -2890- SAWADOGO KRISTO | F3PA broken and not rebuilt |
| VPA 13 -793- OUEDRAOGO ISAAC | F3PA broken and not rebuilt |
| VPA 13 -750- OUEDRAOGO SIBIRI | F3PA broken and not rebuilt |
| VPA 13 -892- OUEDRAOGO HONORE | F3PA broken and not rebuilt |
| VPA 13 -634- ZEMBA FRANCOIS | Household moved outside project intervention area |
| VPA 13 -709- OUEDRAOGO LASSANE | F3PA broken and not rebuilt |
| VPA 13 -839- OUEDRAOGO MADI | F3PA broken and not rebuilt |
| VPA 13 -846- KABORE TALATO | F3PA broken and not rebuilt |
| VPA 13 -861- OUEDRAOGO BOUKARE | Household moved outside project intervention area |
| VPA 13 -792- OUEDRAOGO ABDOULAYE | Household moved outside project intervention area |
| VPA 13 -870- OUEDRAOGO JEAN | F3PA broken and not rebuilt |
| VPA 13 -1058- BAGRE NIOUGA ROSALIE | Household moved outside project intervention area |
| VPA 13 -2810- BAGRE W AUGUSTIN | F3PA broken and not rebuilt |
| VPA 13 -2808- OUEDRAOGO ISSOUF | F3PA broken and not rebuilt |
| VPA 13 -2540- KABORE SALFO | Household moved outside project intervention area |
| VPA 12 -356- ZEMBA SYLVIN | F3PA not used |
| VPA 13 -3055- TARAGDO BINJAMIN | F3PA broken and not rebuilt |
| VPA 13 -3047- TARBAGDO ANDRE | F3PA broken and not rebuilt |
| VPA 13 -2537- TARBAGDO HAROUNA | F3PA broken and not rebuilt |
| VPA 13 -2898- SAWADOGO PASCAL | F3PA broken and not rebuilt |
| VPA 12 -208- OUEDRAOGO GILBERT | F3PA broken and not rebuilt |
| VPA 12 -232- OUEDRAOGO AMANDO | Household moved outside project intervention area |
| VPA 12 -281- OUEDRAOGO LEON | F3PA broken and not rebuilt |
| VPA 12 -432- TAPSOBA ALI | Household moved outside project intervention area |
| VPA 12 -2862- OUEDRAOGO SOULEY | Divorced woman and household members have broken up |

For these 37 households a usage rate Up,y has been accounted of 0%.

The surveyed households per age group are presented with pictures of stove users and stoves in the following file: ‘GS1340 VPA11-12-13 list of surveyed HH Vintage 2021’.

The following points were considered when evaluating the usage rate Up,y:

- All project cookstoves within the sample are assessed if they are still operational. If one stove user doesn’t use any of its project cookstoves, the corresponding household is considered as drop-off;

- The working conditions of project cookstoves are evaluated on the status (i) Green: the stove is in good working conditions, (ii) Orange: the stove is in acceptable working conditions, but needs some maintenance activities; and (iii) Red: the stove is not working well, and needs to be reconstructed (see section C for more details). A household with at least one red project cookstove is considered as a drop-off;

- If a stove-user migrated even for a temporary period, the corresponding household is considered as a drop-off;

Based on the collected data during the survey for this monitoring period the usage rate Up,1 of age group 0-1  and Up,2 of age group 1-2 is evaluated at 76.19%. The usage rate  Up,3  of age group 2-3 resulted in 85.32%. The usage rate  Up,4  of age group 3-4 resulted in 90.99%.

The discount factor to account for the baseline stove use is calculated based on the number of meals that have been cooked with the baseline stove during the monitoring period. The impact of dry and wet season on the baseline stove use has been evaluated. The baseline stove usage has been questioned in the survey in two ways (see ‘GS1340_MS_VPA-11-12-13_Vintage 2021’) (i) relative based on a week usage during dry and wet season (column AM till column AV); (ii) absolute based on total number of usages during dry and wet season (column BB and BQ).The following points were considered when evaluating the discount factor to account for the baseline stove use DFb,stove,y:

- The wet season starts on the 1st of June and ends the 31nd of October, which is 152 days;

- Usage of baseline stove during wet and dry season has been surveyed, as well as the number of meals cooked during dry and wet season;

- Based on the number of meals cooked with the baseline cookstove compared to the number of cooked meals, the baseline usage fraction is calculated per stove user. In the case of more than one stove user per household, the highest value will be taken in order to identify the baseline cookstove usage at household level;

- In case the two ways of baseline usage reporting (relative on weekly basis and absolute) didn’t match, the highest baseline usage has been calculated for the corresponding household;

- The discount factor for the baseline stove use is based on the average baseline stove use fraction of all the households within the sample;

- If a household has dropped off when evaluating the usage rate, it is not considered when calculating the average baseline stove use fraction;

- A conservative approach has been considered when evaluating the number of meals cooked with the baseline stove.

Based on the collected data during the survey, the baseline stove usage fractions have been evaluated at 4.52% for age group 0-1-2. For age group 2-3, the baseline stove usage fraction was 2.00% and for age group 3-4, the baseline stove usage fraction was 1.23%. This means that, on average, approximately 1 to 5 meal out of 100 meals are cooked with the baseline stove.

#### SECTION E. CALCULATION OF SDG IMPACTS

##### E.1. Calculation of baseline value or estimation of baseline situation of each SDG Impact

- SDG 3, Good health and well-being

Not applicable, the direct outcome is calculated, see section E.4.

- SDG 4, Quality Education

Not applicable, the direct outcome is calculated, see section E.4.

- SDG 5, Gender equality

Not applicable, the direct outcome is calculated, see section E.4.

- SDG 7, Affordable and clean energy

Not applicable, the direct outcome is calculated, see section E.4.

- SDG 13, Climate Action

The methodology directly provides equation for emission reductions (without separate baseline, projector leakage emission reduction equations). See section E.4. for the calculation of the emission reductions.

##### E.2. Calculation of project value or estimation of project situation of each SDG Impact

- SDG 3, Good health and well-being

Not applicable, the direct outcome is calculated, see section E.4.

- SDG 4, Quality Education

Not applicable, the direct outcome is calculated, see section E.4.

- SDG 5, Gender equality

Not applicable, the direct outcome is calculated, see section E.4.

- SDG 7, Affordable and clean energy

Not applicable, the direct outcome is calculated, see section E.4.

- SDG 13, Climate Action

The methodology directly provides equation for emission reductions (without separate baseline, projector leakage emission reduction equations). See section E.4. for the calculation of the emission reductions.

##### E.3. Calculation of leakage

- SDG 13, Climate Action

As defined under The Gold Standard Simplified Methodology for Efficient Cookstoves v1.0, the net emission reductions (ERy) for a micro-scale programme of activities (mPOA) need to be discounted by a factor of 0.95 to account for leakages related to non-renewable biomass saved by the project activity.

##### E.4. Calculation of net benefits or direct calculation for each SDG Impact

- SDG 3, Good health and well-being

Smoke level reduction = (Number of stove users perceiving less smoke since the implementation of F3PA efficient cookstoves) / (Number of respondents)

Incidence of coughing reduction = (Number of stove users perceiving less incidence of coughing since the implementation of F3PA efficient cookstoves) / (Number of respondents)

Incidence of respiratory illness reduction = (Number of stove users perceiving less incidence of respiratory illnesses since the implementation of F3PA efficient cookstoves) / (Number of respondents)

Incidence of itchy eyes reduction = (Number of stove users perceiving less incidence of itchy eyes since the implementation of F3PA efficient cookstoves) / (Number of respondents)

See document: ‘GS1340_MS_VPA-11-12-13_Vintage 2021’

- SDG 4, Quality education

Number of trainings initiatives for staff involved in the programme = Number of trainings initiatives for staff involved in the programme during the monitoring period

See document : ‘Compte rendu de formation des enqueteurs verification An4_EN translation’.

Number of workshops carried out for women for the group of VPA’s = Number of workshops carried out for women during the monitoring period

See documents:  ‘Bilan des activités - sensibilisation et formation - VPA 11-12-13_2021_with comments’.

- SDG 5, Gender equality

Proportion of stove users perceiving reduced amount of time spent on fuel collection = (Number of stove users perceiving reduced amount of time spent on fuel collection) / (Number of respondents collecting wood fuel)

Activities carried out by women during saved time:

- Domestic tasksp = (Number of women using their saved time to do domestic tasks) / (Number of women considering they save time thanks to the F3PA efficient cookstoves)

- Income generating activitiesp = (Number of women using their saved time to do income generating activities) / (Number of women considering they save time thanks to the F3PA efficient cookstoves)

- Field labourp = (Number of women using their saved time to do field labour) / (Number of women considering they save time thanks to the F3PA efficient cookstoves)

- Gardeningp = (Number of women using their saved time to do gardening) / (Number of women considering they save time thanks to the F3PA efficient cookstoves)

- Participation to a literacy programp = (Number of women using their saved time to participate to a literacy program) / (Number of women considering they save time thanks to the F3PA efficient cookstoves)

- Community workp = (Number of women using their saved time to do community work) / (Number of women considering they save time thanks to the F3PA efficient cookstoves)

- Doning nothingp = (Number of women using their saved time to participate to do nothing) / (Number of women considering they save time thanks to the F3PA efficient cookstoves)

- Religious activitiesp = (Number of women using their saved time to participate to religious activities) / (Number of women considering they save time thanks to the F3PA efficient cookstoves)

- Leisurep = (Number of women using their saved time to participate to do leisure) / (Number of women considering they save time thanks to the F3PA efficient cookstoves)

See document: ‘GS1340_MS_VPA-11-12-13_Vintage 2021’

Proportion of stove users perceiving reduced amount of money spent on wood fuel purchase = (Number of stove users perceiving reduced amount of money spent on wood fuel purchase) / (Number of respondents purchasing fuel)

Usage of saved money by women:

- School feesp = (Number of women using their saved money for the payment of school fees) / (Number of women considering they save money thanks to the F3PA efficient cookstoves)

- Purchase of medical drugsp = (Number of women using their saved money for the purchase of medical drugs) / (Number of women considering they save money thanks to the F3PA efficient cookstoves)

- Purchase of foodp = (Number of women using their saved money for the purchase of food) / (Number of women considering they save money thanks to the F3PA efficient cookstoves)

- Investment for field cropsp = (Number of women using their saved money to invest in field crops) / (Number of women considering they save money thanks to the F3PA efficient cookstoves)

- Purchase of equipmentsp = (Number of women using their saved money to purchase equipments like mobile, bicycle, …) / (Number of women considering they save money thanks to the F3PA efficient cookstoves)

- Income generating activitiesp = (Number of women using their saved money for income generating activities) / (Number of women considering they save money thanks to the F3PA efficient cookstoves)

- Savingsp = (Number of women using their saved money for their savings) / (Number of women considering they save money thanks to the F3PA efficient cookstoves)

See document: ‘GS1340_MS_VPA-11-12-13_Vintage 2021’

- SDG 7, Affordable and clean energy

Number of F3PA efficient cookstoves disseminated for the group of VPA’s = Number of F3PA efficient cookstoves included in the project database for project scenario p

See documents: ‘DR_Tiipaalga_VPA-11_ICS_20220404’ & ‘DR_Tiipaalga_VPA-12_ICS_20220404’ & ‘DR_Tiipaalga_VPA-13_ICS_20220404’.

- SDG 13, Climate Action

The methodology directly provides equation for emission reductions (without separate baseline, projector leakage emission reduction equations). The emission reduction for the VPA are calculated using the following equation.

ERy=0to1xtoyNP,y *Py*UP,y*(fNRB,y*EFb,fuel,CO2+EFb,fuel,nonCO2)*(1-DFb,Stove,y)

Where

| Np,y | Number of households with project cookstoves of each age group operational in the year y |
| --- | --- |
| Py | Quantity of firewood that is saved in the year y (tones per household in year y) |
| Up,y | Usage rate for project cookstoves in year y, based on adoption rate and drop off rate revealed by usage surveys (fraction) |
| fNRB,y | Factional non-renewability status of wood fuel during year y |
| EFb,fuel,CO2 | CO2 emission factor of firewood that is substituted or reduced |
| EFb,fuel,nonCO2 | Non CO2 emission factor of firewood that is substituted or reduced |
| DFb,stove,y | Usage of baseline cookstove during the year y (fraction) in project scenario |
| X | y-1 |
| Y | Year of the crediting period |

Determination of quantity of biomass saved (Py):

Quantity of firewood that is saved (Py) is estimated using the following equation:

Py=Bb,y*(1-ƞbƞp,y)

Where:

| Py | Quantity of firewood that is saved in the year y (tones per household in year y) |
| --- | --- |
| Bb,y | Quantity of firewood consumed in baseline scenario during year y (tones per household per year) |
| p,y | Efficiency of project cookstove in year y (fraction) |
| b | Efficiency of the baseline cookstove being replaced (fraction). A default value of 10% shall be used if the replaced cookstove is a three stone fire, or a conventional device without a grate or a chimney i.e. with no improved combustion air supply or flue gas ventilation |
| y | Year of the crediting period |

Determination of quantity of fire wood consumed in the baseline (Bb,y):

The firewood consumed is the estimated average annual consumption of firewood per household (tones/year), which may be derived using option (c) of the methodology: minimum service level i.e. energy derived from the combustion of 0.5 tonnes per capita per year as the default baseline biomass consumption. The average household size per municipality is available in the “Recensement général de la population et de l'habitation (RGPH) de 2006 du Burkina Faso” or the general census of the population and habitat of Burkina Faso, table 15.

Determination of project cookstove efficiency (p,y and p):

Efficiency of project cookstove in year y (ηp,y) is estimated as follows:

ƞp,y=ƞp*DFƞy-1*0.94

Where

| ηp,y | Efficiency of project cookstove in year y (fraction) |
| --- | --- |
| ηp | Efficiency of project cookstove (fraction) determined at the start of the project activity |
| DFη | Discount factor to account for efficiency loss of project cookstove per year of operation (fraction) |
| 0.94 | Adjustment factor to account for uncertainty related to project cookstove efficiency test |

See documents: ‘GS 1340 - VPA 11 - ER_MP4’ & ‘GS 1340 - VPA 12 - ER_MP3’ & ‘GS 1340 - VPA 13 - ER_MP2’. The consolidated results are presented in document : ‘GS1340 - VPA-11-12-13-Vintage 2021 - Consolidated ER calculation’.

| SDG | SDG Impact | Baseline estimate | Project estimate | Net benefit |
| --- | --- | --- | --- | --- |
| 13 | Number of tCO2e reduced by the project |  |  | Year 2021: VPA 11: 10,000 tCO2e VPA 12: 9,829 tCO2e VPA13 : 8,497 tCO2e Total : 28,326 tCO2e |
| 3 | Smoke level reduction Incidence of coughing reduction Incidence of respiratory illness reduction Incidence of itchy eyes reduction |  |  | 100% 100% 100% 100% |
| 4 | Number of trainings initiatives for staff involved in the programme |  |  | 1 |
| 4 | Number of workshops carried out for women for the group of VPA’s |  |  | 85 |
| 5 | Proportion of stove users perceiving reduced amount of time spent on fuel collection Proportion of stove users perceiving reduced amount of money spent on wood fuel purchase |  |  | 100% 100% |
| 7 | Number of F3PA efficient cookstoves disseminated for the group of VPA’s |  |  | 29,181 |

##### E.5. Comparison of actual SDG Impacts with estimates in approved PDD

| SDG | Values estimated in ex ante calculation of approved PDD for this monitoring period | Actual values achieved during this monitoring period |
| --- | --- | --- |
| 13 | Year 2021: VPA 11: 9,615 tCO2e VPA 12: 9,702 tCO2e VPA 13: 9,702 tCO2e Total : 29,019 tCO2e | Year 2021: VPA 11: 10,000 tCO2e VPA 12: 9,829 tCO2e VPA 13: 8,497 tCO2e Total : 28,326 tCO2e |
| 3 | Smoke level reduction: >90% Incidence of coughing reduction: >90% Incidence of respiratory illness reduction: >90% Incidence of itchy eyes reduction: >90% | Smoke level reduction: 100% Incidence of coughing reduction: 100% Incidence of respiratory illness reduction: 100% Incidence of itchy eyes reduction: 100% |
| 4 | Number of trainings initiatives for staff involved in the programme: 1 | Number of trainings initiatives for staff involved in the programme: 1 |
| 4 | Number of workshops carried out for women for the group of VPA’s: 60 (VPA-11: 20, VPA-12: 20 and VPA-13: 20) | Number of workshops carried out for women for the group of VPA’s: 85 |
| 5 | Proportion of stove users perceiving reduced amount of time spent on fuel collection: >90% Proportion of stove users perceiving reduced amount of money spent on wood fuel purchase: >90% | Proportion of stove users perceiving reduced amount of time spent on fuel collection: 100% Proportion of stove users perceiving reduced amount of money spent on wood fuel purchase: 100% |
| 7 | Number of F3PA efficient cookstoves disseminated for the group of VPA’s: VPA-11: 6,200 VPA-12: 6,200 VPA-13: 6,200 Total: 18,600 | Number of F3PA efficient cookstoves disseminated for the group of VPA’s: VPA-11: 10,387 VPA-12: 10,165 VPA-13: 8,629 Total: 29,181 |

E.5.1. Explanation of calculation of value estimated ex ante calculation of approved PDD for this monitoring period

Remark regarding SDGs indicator calculation:

- SDG 13 - Emission reductions: the ER for this monitoring period for the VPA-13 are less than the ex-ante estimates presented in the PDD (9,702 vs. 8,497 VERs). The reason is the usage parameters (Up,y and DFb,stove). Compared to other age-group and previous project experience, the parameters  for AG1-2, which mostly correspond to VPA-13) are abnormally low for Up and for high DFb,stove. This difference would be due to insufficient field monitoring of the use, maintenance and protection of F3PAs by the management team of the two municipalities concerned (Niou and Boussé). In 2020, the Animator (cf. Figure 2 Distribution pyramid) responsible for capacity building and monitoring of F3PAs in VPA-13 (most recently established) was redeployed to reinforce another tiipaalga team in the province of Zoundwéogo in the Centre-Sud region (GS1340/GS10922-10928), which affected field monitoring activities. This has also impacted on the functions of the leader women (“monitrices endogènes” or “ME”) and has been reflected in the state of the cookstoves of the municipalities concerned. The time taken by the new Animator to take charge of the project intervention area worked to the disadvantage of the main VPA-13 cookstoves encountered in the municipalities of Boussé and Niou. The intensification of sensitisation, support and monitoring activities is continuing with the aim of increasing the capacity of the MEs to provide better care for women beneficiaries in the households covered by the project.

- SDG 7 – Number of F3PA efficient cookstoves disseminated for the group of VPA’s: the ex-ante estimates presented in the VPA-DDs were evaluated considering that each household will have a set of two cookstoves. In reality, more F3PA cookstoves are installed per households leading to higher results. More details are found in project distribution records databases: ‘DR_Tiipaalga_VPA-11_ICS_20220404’, ‘DR_Tiipaalga_VPA-12_ICS_20220404’, ‘DR_Tiipaalga_VPA-13_ICS_20220404’.

##### E.6. Remarks on increase in achieved SDG Impacts from estimated value in approved PDD

- SDG4: More workshops have been carried out as there has been a higher adoption  rate and higher number of disseminated cookstoves. Therefore, more leading women needed to be trained.

- SDG 7 Number of efficient F3PA cookstoves: Due to the higher adoption rate of the project technology, the total number of disseminated F3PA cookstoves is higher than the previsions presented in the PDD.

- SDG 13 Emission reductions: For the VPA-11 and VPA-12 the ER estimates are slightly higher than the expected issuances in the associated VPA-DDs.This is explained by the increased number of households compared to ex-ante estimates (i.e. 3,437 (VPA-11) and 3,330 (VPA-12) vs. 3,100 in ex-ante estimates).

#### SECTION F. SAFEGUARDS REPORTING

Not applicable.

No safeguarding principles were added to the monitoring plan.

#### SECTION G. STAKEHOLDER INPUTS AND LEGAL DISPUTES

##### G.1. List all Inputs and Grievances which have been received via the Continuous Input and Grievance Mechanism together with their respective responses/mitigations.

No inputs/grievances have been received for the project during the monitoring period.

Pictures of the grievance book can be found in document: ’ 20220715-Grievance book F3PA Kourweogo_with comments”.

##### G.2. Report on any stakeholder mitigations that were agreed to be monitored.

Not applicable. No stakeholder mitigations were agreed to be monitored.

##### G.3. Provide details of any legal contest that has arisen with the project during the monitoring period

No legal contest or dispute has arisen.

Revision History

| Version | Date | Remarks |
| --- | --- | --- |
| 1.1 | 14 October 2020 | Hyperlinked section summary to enable quick access to key sections Improved clarity on Key Project Information Section for POA monitoring Forward action request section Improved Clarity on SDG contribution/SDG Impact term used throughout Clarity on safeguard reporting Clarity on design changes Leakage section added for VER/CER projects Addition of Comparison of monitored parameters with last monitoring period Provision of an accompanying Guide to help the user understand detailed rules and requirements |
| 1.0 | 10 July 2017 | Initial adoption |

The project (https://registry.goldstandard.org/projects/details/665) is an initiative of SNV, the Netherland Development Organization, to promote improved “dolo” stoves in the Boucle du Mouhoun Region of Burkina Faso. These stoves are used for brewing of “Dolo”, a traditional local drink made from sorghum which is is consumed during any ceremony, rituals, festivities and non-special occasions.

Report of the training session, see original document: ‘Compte rendu de formation des enqueteurs verification An4_FR’ and its translation in English : ‘Compte rendu de formation des enqueteurs verification An4_EN translation’.

- Rapport sur les tests de performances énergétiques des Foyers trois pierres améliorés (F3PA) de l’association Tiipaalga, Laboratoire Biomasse Energie et Biocarburant de 2IE, Ouagadougou, July 2015 (see document « tiipaalga_Rapport de tests de performance énergétiques_F3PA_24_07_2015_VF.pdf » or in English : « tiipaalga_Report WBT thermal efficiency_F3PA_24_07_2015_VF_EN »)

- INSD, recensement général de la population  et de l’habitation de 2006, juillet 2008, Ministère de l'Economie et des Finances, p49 (tableau 15),  52 pages : (Document « Resultats_definitifs_RGPH_2006_with EN translation »)

https://www.randomdraws.com/random-sequence-generator/

The document is in French, an English translation of the questions of the survey is available in headers of document : ‘GS1340_MS_VPA-11-12-13_Vintage 2021’.

- INSD, recensement général de la population  et de l’habitation de 2006, juillet 2008, Ministère de l'Economie et des Finances, p43 (tableau 15),  52 pages