Monitoring Report

###### PUBLICATION DATE  14.10.2020
VERSION  v. 1.1 
RELATED SUPPORT - TEMPLATE GUIDE Monitoring Report v. 1.1

This document contains the following Sections

Key Project Information

SECTION A - Description of project

SECTION B - Implementation of project

SECTION C - Description of monitoring system applied by the project

SECTION D - Data and parameters

SECTION E - Calculation of SDG Impacts

SECTION F - Safeguards Reporting

SECTION G - Stakeholder inputs and legal disputes

### KEY PROJECT INFORMATION

##### Programme of Activity Information – (delete below table if N/A)

| GS ID of Programme | GS 1729 |
| --- | --- |
| Title of Programme | GS 1729 Myanmar Stoves Campaign - Soneva in Myanmar – VPA No. 007 |
| Version of POA-DD applicable to this monitoring report | 4.0 |
| Name and GS ID of fully Validated CPA/VPAs (i.e. non compliance check) | GS1729 Myanmar Stoves Campaign - Soneva in Myanmar – VPA No. 007. GS ID – GS 6129 |

##### Key Project Information

| GS ID (s) of Project (s) | GS 6129 |
| --- | --- |
| Title of the project (s) covered by monitoring report | GS1729 Myanmar Stoves Campaign - Soneva in Myanmar – VPA No. 007 |
| Version number of the PDD/VPA-DD (s) applicable to this monitoring report | 4.0 |
| Version number of the monitoring report | 5.0 |
| Completion date of the monitoring report | 24/02/2024 |
| Date of project design certification | 14/06/2018 |
| Date of Last Annual Report | 05/12/2022 |
| Monitoring period number | 4 |
| Duration of this monitoring period | 01/07/2020 - 30/06/2021 |
| Project Representative | Arnfinn Oines |
| Host Country | Republic of the Union of Myanmar |
| Activity Requirements applied | Community Services Activities Renewable Energy Activities Land Use and Forestry Activities/Risks & Capacities N/A |
| Methodology (ies) applied and version number | The Gold Standard Simplified Methodology for Efficient Cookstoves, Version 01, February 2013, and Version 1.1 April 2020. |
| Product Requirements applied | GHG Emissions Reduction & Sequestration Renewable Energy Label N/A |

##### Table 1 - Sustainable Development Contributions Achieved

| Sustainable Development Goals Targeted | SDG Impact | Amount Achieved | Units/ Products |
| --- | --- | --- | --- |
| SDG 13: Take urgent action to combat climate change and its impacts | Emissions Reductions | 3352 | VERs |
| SDG 3: Ensure healthy lives and promote well-being for all ages | Improvement of health and safety by reducing the number of mortality rate attributed to household and ambient air pollution. | 4431 | People |
| SDG 7: Ensure access to affordable, reliable, sustainable and modern energy for all | Improvement in energy efficiency in cooking practices. | 1163 | Households |
| SDG 8: Promote sustained, inclusive and sustainable economic growth, full and productive employment and decent work for all | Informal job creation in non-agricultural sector | 46 | Informal jobs created |

##### Table 2 – Product Vintages

| Start Dates | End Dates | Amount Achieved |
| --- | --- | --- |
| 01/07/2020 | 31/12/2020 | 1682 |
| 01/01/2021 | 30/06/2021 | 1670 |
| Total |  | 3352 |

#### SECTION A. DESCRIPTION OF PROJECT

##### A.1. General description of project

>> Myanmar Stoves Campaign aims to ensure the use of carbon finance to support the distribution and maintenance of domestic and non-domestic Fuel-Efficient Stoves (FES) through local implementation partner(s) (IP) in the Republic of the Union of Myanmar.

The Myanmar Stoves Campaign is a programme of the Soneva Foundation and the first Gold Standard certified carbon project in Myanmar. This project activity is implemented by three actors, which are the Soneva Foundation, Mercy Corps and Local Vendors (Sales Agents) in each of the targeted project villages under this VPA.

Myanmar Stoves Campaign was started in September 2013 and currently, and since then, as of May 2018, the project has covered more than 1000 villages in central part of Myanmar. The co-ordinated action by the three actors in this project has been successful in distributing over 25,000 fuel efficient stoves which have improved the lives of more than 125,000 people.

The stoves distributed are the Envirofit SuperSaver GL (Earlier known as M-5000). Each household received at least one stove. There are two methods of payments which are lump sum (15000 MMK for lump sum payment) and instalment (17000 MMK for five (5) months instalment) payments. Instalment is an excellent method for some families who have financial hardship and couldn’t afford lump sum payment.

Selected FES model for this VPA:

•	Envirofit SuperSaver GL (Earlier known as M-5000), launched in 2011, is the successor model of the G-3300 and is produced in China, India and Kenya

•	Product weight 4.2kg

•	Size (in cm): 28x26.5x26.5

•	CO2 emission reduction compared to three stone fires of 66%

•	Wood use reduction compared to three stone fires of 66%

•	Thermal efficiency of 29.7%

•	Manufacturer guarantee of 2 years on outside and 5 years on the inside parts

•	Estimated product life of 5 years

Source: M5000 (SuperSaver GL) manufacturer website (Link)

Envirofit SuperSaver GL had been selected as suitable product for local users based on the inputs from local communities and various stakeholders after they were consulted through demonstration and filed tests. This followed with the stoves being distributed to the households in targeted villages.

This intervention has helped the local households to smoothly transition to a new FES stove from being dependent on the old three stone fires. The user experience and benefits has been highly positive and encouraging towards this modern technology. In addition to this, this project has successfully demonstrated the contribution in catalyzing the socio-economic development of these communities by having a positive impact on a range of indicators. There is an increasing awareness among the users in targeted villages and the nearby ones on the immediate and long term environmental and economic benefits coming from this project, which is helping in higher rates of adoption, all of which is helping the Myanmar Stoves Campaign to positively impact the lives of the rural under-served in a sustainable and environmentally friendly way.

This VPA consist of 1743 stoves for eligible crediting (1953 originally during validation in total)

Out of 1953, the following stoves were taken out from applying for verification:

i) End User Data Missing = 9

ii) Repeated Stove Serial Numbers = 28

iii) Electric Stoves as Baseline Stoves = 81

iv) Charcoal as Baseline Fuel = 48

v) Other discrepancies = 31

vi) Households having more than one project stoves = 13

After deducting i) to vi), 1743 stoves were selected for crediting period out of 1953 stoves considered originally.

Date of first stove sale & start date of the project activity = 01/03/2017 (to 30/06/2017)

Start date of crediting period = 01/07/2017

Fourth project monitoring resulta has been taken from the VPA009.

##### A.2. Location of project

>> Republic of the Union of Myanmar,Mandalay Division, Pyabwe Region.

The geographic location of the project activity is 20°33’07.28N and 95°47’51.08E. Stoves distributed under VPA – 007 are majorly in the villages of, which are clearly identifiable and can be distinguished from the other VPAs.

| List of Villages in VPA 007 |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Myin Twin | Shwe Pauk Pin | Lashio Gyi Ward | Than Bo | Pae Khine Gyi | Hpa Yar Hla | Nyaung Wu |
| Naw Khme | Sauk Taw Wa(N) | Yae Myet | Aung Thar | Kan Swei | Phar Yar Lay Kone | Shwe Bon Thar |
| Thin Ga Tone | War Yone Pin (Man Gyi Chan) | Ah Lel Kan | Yae Lel Thaung (East) | Hnan Khin | Thint Dauntk (N) | Myin Thar |
| Kin Bag | Hpyauk Seik Kone | No (1) Ward | Lin Kar Di Pa | Zee Phyu Kone | Lat Pan Chay Paw | Pyawt (Chin Myint Kyin) |
| Aung Thar | Myit Nge Ward | Ywar Thit Hpya | Yae Lel Thaung (West) | Kywe Swea | A Htet Nyan | Gwayt Gyi |
| Nwar Tat | Mi Chaung Tet | No (2) Ward | Hta Naung Kone | Kan Pauk Gyi | Khat Lan Kan | Htein Pan |
| Mae Khin Gyi | Shan Ywar Gyi | Pyaw | Ma Yoe Kone | Ohn Chaw | Mya Ga Gi Ri Ward | Out Yoe |
| Htan Lone Tat | Mon Taw | Let Khoke Kone | Sin Hpyu Kone | No (2) Ward | Chaung U (South) Ward | Gaung Kwe |
| Gway Saung | Hman Tan Ward | Nwar Shar Yoe | Nat_Gyi | Myo Thar (East) | Bo Tae Kone | Kun Thee Pain (Lay Ein Tan) |
| Kyauk Sa Ka Lay | Kan Gyi (East) | Pauk Myaing | Kone Lel | Moe Taung | Ywar Thit | Ya Thit |
| Taung Ta Lone | Nyaung Pin Thar | Inn Yin | Sat Pyar Kyin | Naung Hlaing | Oke Kyut Tann (West) Ward | Taung Khaung Pwar |
| Kya Swar | Thet Kei Kyin | Sin Chan | Kan Thar | Pay Taw | Kywe Tat | Kyauk Myaung |
| Ta Lin Gyi | Myin Thei | Bu Tar Ward | (Ga Nge) Ward | Nyaung Wun | Myin Ywar Ka Lay | Let Pan |
| Sapar Twin | Ta Pei | Shwe Thu Htay Ward | (Nga) Ward | Kan U | Kan Swei (East) | Nyaung Pin Wun |
| Zay Ywar | Pan Ya (South) | Shan Pwe Ward | (Ka Gyi) Ward | Pay Taw (Kan Pauk) | Sa Myaung | Chaung U |
| Mying Thar | Thit Taw Hpyar (North) | Nwar Ku Gyi | Si Thar | Myauk Kyun | Nyaung Wun (South) | Sue Lay Gone Ward |
| Tha Pyay Kan | Kyauk Ta Lone | Pon Nar | Pyin Si | Ah Neint | Ma Gyi Kan |  |
| Koke Ko Kan | Ywar Bo (South) | Ywar Thar Aye | Tha Pay Thar (Middle) | Te Kone | Kyauk Kone |  |
| Taung Kine | No (1) Ward | Kyauk Sauk | Tha Pay Thar (East) | Kyaung Phu | Myaung Char |  |
| Souk Taw Wa | No (4) Ward | Tha Pay Thar (East) | Lay Tan | Ya Thar | Min Win |  |
| Sauk Inn | Sin Tat | Tha_Pay_Thar_West | Ywar Thar Aye | Ma Yoe Kone | Ah Lel Kyun |  |
| Ta Ohm | Si Kan | Kan Kwayt | Pin_Lel | Thein | Thone Ein |  |
| Ae Bya | Kan Ma | Kone Thar | Te Gyi | Hpet Ping Aing | Kyan Tan Ward |  |
| Ma Gyi Kine | Hpyu Twin Kone | Aye | Kyar Kan | Son | Buu Tar Ward |  |
| Inn Kuu | Tha Yet Kan | Myin Chan Kone | Hnat Cho Taw | Ywar Thar Yar | Min Nay Kone |  |
| Sa Kar Tae | Htan Ta Pin | Kyar Myee Swea | Kan Chaw (Ga Lant) | Koke Ke | Tha Kyin |  |
| Moe Nan Chone | Pyin Hla Taw | Maing Maw | Thein Kone | Kyauk Tan | Let Pan Thar |  |
| Suu Kar King | Ma Gyi Kone | Kin Sein Zay (East) | Myay Sa Kaung | Lay Ywar Son | Thin Pan Kone Ward |  |
| Kan Gyi | Than Kone | Ta Ko Tee (North) | No (12) Ward | Hpon |  |  |
| Myo Ma Ward | Tha Nat Sit | Pay Kone | Shwe Chaung | Ku |  |  |
| Chan Aye Thar San Township | Na Be Pin | Wet Htein | Ma Har Myaing (1) Ward | Zee Pin Kan | No(7) Ward |  |
| Hta Naung Pin Hla | Chin Thayt Let | Tha Ma Tan | Min Yin | Zee Taw | No(18) Ward |  |
| Kyauk Chaw | Nga Lunt | Ta Mar Pin | Sat Pyar Kyin | Ywar Si (North) | Taung Kyun |  |
| Aung Chan Thar | (Ga Gyi) Ward | Nat Yae Kan | Pa Da Myar Ward | Sar Khar | Kyar Taing |  |
| Nauk Taw Par | (Kha Gway) Ward | Yae Poke | Nat Sin | Sin Gut | Hta Naung Pin Su (South) |  |
| Nyaung Pin Thar | Chan Mya Thar Zi (South) Ward | Kyaung Kone Gyi | Mone Za Le | Kaing Taung | Kywe Chan |  |
| Daunt Gyi Kwayt | Min Kun | Tha Pyay Thar | Pyin Pauk | Nyaung Pin | Sar Kyu |  |
| Kyun U | Pe Chet (East) | Hpaung Ka Taw | Aye Seint | Hta Naung Taing | Ku Lar |  |
| Kan Swei | Thar Si Lay | Nyaung Lay Pin | Ku Me | Kun Saik | Kyee Pin |  |
| Pei Lay Se | Myet Shu | Ma_Gyi_Kyat | Si Pin | Chay Say | Thea Hphy Wa Pyi Taw Thar |  |
| Pay Taw Gyi | Wet Lu (East) | Let Pa Kyin (South) | Tharsi lay | Myo Ma Ward | Tha Pyay Thar |  |
| Ba Lont | Pa Kin (Nar Lin) | Let Pa Kyin (North) | Ywar Thit | Nyaung Kan | Ma Yoe Kone |  |
| Mya Inn | Ah Lel Paing Ward | Se Yoe | Tha Phan Pin | Hpet Taw | Taw Pu |  |

##### A.3. Reference of applied methodology

>> The Gold Standard Simplified Methodology for Efficient Cookstoves, Version 01, February 2013.

##### A.4. Crediting period of project

>> Start Date of the Crediting Period as in approved PDD: 01/07/2017

Length of the crediting period is five years, renewable twice, hence 15 years in total.

#### SECTION B. IMPLEMENTATION OF PROJECT

##### B.1. Description of implemented project

>> In VPA 007, the total number of stoves distributed eligible for crediting are 1743.  This VPA particularly focused on expanding the project and distributing the fuel-efficient cookstoves mostly in the regions which come under the central dry zone of Myanmar. The project employs a model where local women and men are selected and trained for the role of local sale agents/local vendors for the marketing, distribution, sales and after-sales of the stoves. These local sale agents earn a commission on the sales they make. In addition to the financial incentive, the local sale agents significantly benefit from learning new skills and knowledge and building confidence via the training and capacity building programs. The sale agents also act as the first point of contact for the stove users in the event of any grievances and after-sale service requirements. This is then escalated to the project implementation partner of this VPA,  Mercy Corps (Myanmar) team who looks into stove repairs/replacements. In an event where the user needs after-sale service, he/she reaches out to the local sale agent, who then raises the matter with the local project team. Records of stoves services/replaced are maintained at the Mercy Corps local office. For this particular monitoring period, no such stove complains or requests for service/replacements were received from the stove users.

The project is implemented and is currently under annual monitoring. For the reported monitoring period, 52.63% of the users have been reported to use the improved cookstoves. There have been no major deviations in this VPA as per the approved project design. The VPA still maintains adherence to the approved project design, and this VPA has been implemented as per the original plan as per the VPA-DD

B.1.1 Forward Action Requests

>> Not applicable

Forward Action Request # 1: For monitoring sampling survey, PP shall select only stoves which are the part of end user database. PD and VVB are asked to clarify how this was addressed and validated.

Response: PD has maintained a user database for the VPAs and villages are selected randomly from this user database for the survey. The users which were surveyed are part of the end user database which was prepared during VPA implementation.

##### B.2. Post-Design Certification changes

B.2.1. Temporary deviations from the approved Monitoring & Reporting Plan, methodology or standardized baseline

The project developer applied with a request for temporary deviation with respect to the original monitoring plan in the light of COVID19 events, which was later approved by the GS team.

Instead of the earlier method, where the PD employed independent enumerators to go door-to-door and randomly select households for annual monitoring surveys, it planned to conduct this process with a change, by including the elements of ‘remote monitoring’ as mentioned under para 3.1.1 of the ‘COVID 19: INTERIM MEASURES’ published on 06/04/2020.

In the new proposed system, the local stove sale agents / Mercy Corp’s staff, who are already residing in the target villages, conducted the household interviews by visiting the end users from their villages. They asked all relevant questions as required by the methodology to the end-users and pass the answers to the implementation partner team via mobile phone call in real time. In this way, the team at the (home) office, is able to get all relevant data, and engage further with end users for additional information, via the already stationed local sale agents /Mercy Corp’s staff in target villages.

The data collected by the IP team in (home) office, was then fed in a spreadsheet, and handed over to the CME, which used it for preparing the annual monitoring reports.

PP has also taken the deviation from the mandatory site visit by the objective observer with the option of remote audit due to the ongoing violent protests in Myanmar during the current monitoring period. In the current situation of restricted travel, the remote audit is the best possible option to get credible data from end-users. This will not have any impact on the quality of data received.

Moreover, CME has taken a deviation from the monitoring survey which was unable to conduct due to the military coup. CME has used the most conservative usage rate reported in the fourth year of the verification from the other VPA.

B.2.2. Corrections

>>

Not Applicable

B.2.3. Changes to start date of crediting period

Not Applicable

B.2.4. Permanent changes from the Design Certified monitoring plan, applied methodology or applied standardized baseline

>> Not Applicable

B.2.5. Changes to project design of approved project

>> Not Applicable

#### SECTION C. DESCRIPTION OF MONITORING SYSTEM APPLIED BY THE PROJECT

>> The start of the stove distribution under this VPA was on 01st March 2017 and the distribution ended on 30th June 2017.

The monitoring plan is in accordance with " The Gold Standard Simplified Methodology for Efficient Cookstoves, Version 01, February 2013.”

The monitoring methodology is supported by:

•	Sales receipts

•	Total Sales Record (Project Tracking File)

•	Customer Database

Maintenance of a Total Sales Record

The Project Proponent collates and maintains the total sales data in electronic and paper format. The Total Sales Record comprises the following data:

•	Date of Sale

•	Model/type of project technology sold: Model/type of project technology sold:

•	Serial/ID number of the device

•	Name and telephone number (if available) of end-users

•	Application of device (type of end use: Commercial/Domestic)

•	Address/ Location of end-users2

The Sales Record information is collected using the following methods:

For the portable fuel-efficient stoves, the local vendors (sales agents) sell stoves directly to end-users and record sales and user training continuously. This data is then collated into a detailed Total Sales Record that tracks the chain of transactions between the user and the distributors.

The data received by the project implementation partners in paper format is converted and saved electronically for monitoring and analysis purposes. A mechanism, designed jointly between the CME and the implementing partner, has been agreed and put in place to accurately track sales, inventories, supply and purchases for every stove distributed. For assuring accuracy and consistency, the Total Sales Record is cross checked with import data, usage and other relevant data.

The names and addresses (village name) collected are commensurate with representative sampling, i.e. the names and addresses (where possible) within sales record are large enough so that surveys can be based on representative, randomly selected samples.

Project Database

The project database is derived from the Total Sales Record with project cookstoves differentiated by different project scenarios or VPAs.

Other periodic monitoring tasks

Monitoring consists of checking of a representative sample, once every year (annually) to ensure that project cookstoves are still operating by carrying out the usage survey as per the guidelines set out in the methodology.

Annual surveys for monitoring:

•	Usage Survey to establish the drop-off rates in technology usage from year-1 sales and other vintages. For example, if only cookstoves in the first year of use (age0-1) are being credited, a usage parameter is established for age-group 0-1, through a usage survey for cookstove age0-1. If cookstoves of age 0-1 and age 1-2 are being credited (as part of first request for issuance), usage parameters are established for age-group 0-1 and 1-2, respectively through a usage survey. If cookstoves of age-group 0-1 and 1-2 are being credited (as part of second request for issuance), usage parameters are established for age-group 1-2 only through a usage survey as the usage rate for cookstoves of age group 0-1 can be applied from the previous issuance.

•	Monitoring Survey to reassess household kitchen regimes. CME and/or Implementation Partner randomly samples households from the sales agreements received. Sampling is representative of geographic regions and technology used. Where replacements are made, monitoring shall also ensure that the efficiency of the new cookstove is similar to the appliances being replaced. Finally, the project also monitors the physical conditions of the cookstoves.

For this monitoring period in this VPA, there have been no cases of replacements or repairs reported.

CME has used the monitoring survey results from the VPA 009 survey results obtained.

The team involved in the project monitoring exercise is as follows:

| Name | Designation & Role | Qualification |
| --- | --- | --- |
| Shailendra Kewat | Consultant to the Soneva Foundation on Myanmar Stoves Campaign. Shailendra led the designing of the project monitoring survey exercise + QA/QC of data. | Shailendra Kewat is a consultant in the field of social development and Climate Change. He has an extensive experience of working in the development sector in India and Myanmar, specifically on energy access initiatives and clean energy sources. Shailendra has earned his Master’s degree in Applied Chemistry from RGPV, India. A Masters in Energy & Environment from DAVV, Indore, India. |
| Yin Yin Aung | Team Leader- Myanmar Cookstoves Campaign in Mercy Corps Myanmar She has planned the data collection, training of office staff and sale agents, supervision and QA/QC of data | Graduated with Master of Business Administration (MBA) from Asian Institute of Technology in Bangkok, Thailand, and Master of Commerce (M.Com) and Bachelor of Commerce (B.Com) from Yangon Institute of Economics in Yangon, Myanmar. She has lots of experiences not only in private sector business development but also in development sector such as rural development, livelihood and energy sectors. To highlight her many years experiences in energy sector before joining to Mercy Corps Organization, she worked as Marketing, Promotion and Business Manager in SCALE project (which is the locally produced cookstoves project funded by EU) under GERES Organization. In addition, she also worked as Marketing Specialist in Myanmar Cookstoves Pilot Project (funded by AusAID) under World Vision Organization. She has excellent knowledge about many types of cookstoves (locally made or exported) and nature of the market and well understanding the cookstoves local producers, distributors, sale agents and customers. She has good motivation and is independent but she would also abide by rules of the organization she work for. She can manage well her team members and crews to achieve the objective of the project. Moreover, she would turn the crisis into opportunities. She has variety of alternative approaches to the destination. She joined Mercy Corps Myanmar in March 2022 as Team Leader in Myanmar Cookstoves Campaign project. |

#### SECTION D. DATA AND PARAMETERS

##### D.1. Data and parameters fixed ex ante or at renewal of crediting period

>>

| Relevant SDG Indicator | SDG 13: Take urgent action to combat climate change and its impacts |
| --- | --- |
| Data/parameter | EFb, fuel, CO2 |
| Unit | tCO2/t firewood |
| Description | CO2 emission factor arising from the use of firewood in baseline scenario |
| Source of data | IPCC default values, table 1.4 of chapter 1 of Vol. 2, 2006 IPCC Guidelines for National Greenhouse Gas Inventories |
| Value(s) applied | 1.747 |
| Choice of data or Measurement methods and procedures | Deemed valid by GS VER Methodology |
| Purpose of data | To calculate VERs |
| Additional comment | Measuring emission factors from stove technologies is costly and difficult to do accurately. The CME applies default IPCC emission values. |

| - Relevant SDG Indicator | - SDG 13: Take urgent action to combat climate change and its impacts |
| --- | --- |
| - Data/parameter | EFb, fuel, non_CO2 |
| - Unit | tCO2/t firewood |
| - Description | Non-CO2 emission factor for use of firewood in baseline scenario |
| - Source of data | IPCC default value, table 2.9 of chapter 2 of Vol. 2, 2006 IPCC Guidelines for National Greenhouse Gas Inventories |
| - Value(s) applied | 0.58 |
| - Choice of data or Measurement methods and procedures | Deemed valid by GS VER Methodology |
| Purpose of data | - To calculate VERs |
| - Additional comment | Measuring emission factors from stove technologies is costly and difficult to do accurately. The CME applies default IPCC emission values. |

| - Relevant SDG Indicator | - SDG 13: Take urgent action to combat climate change and its impacts |
| --- | --- |
| - Data/parameter | ηb |
| - Unit | Fraction |
| - Description | Efficiency of the baseline system being replaced |
| - Source of data | Methodology |
| - Value(s) applied | 10% |
| - Choice of data or Measurement methods and procedures | Default value as per the GS methodology. |
| Purpose of data | - To calculate VERs |
| - Additional comment | - Measuring emission factors from stove technologies is costly and difficult to do accurately. The CME applies default IPCC emission values. |

| - Relevant SDG Indicator | - SDG 13: Take urgent action to combat climate change and its impacts |
| --- | --- |
| - Data/parameter | ηp |
| - Unit | Percent |
| - Description | Efficiency of the cookstove i being used in the project scenario |
| - Source of data | Manufacturer’s website> section on the specifications project stove Envirofit M5000 (SuperSaver GL) (Reference: Weblink) |
| - Value(s) applied | 29.7% |
| - Choice of data or Measurement methods and procedures | The value is derived from Envirofit, the manufacturers of these stoves who issue these results after complying with all relevant test standards and procedures for the certification of their products. |
| Purpose of data | To calculate VERs |
| - Additional comment | - The project stove has been independently tested and is widely used in different countries. |

| - Relevant SDG Indicator | - SDG 13: Take urgent action to combat climate change and its impacts |
| --- | --- |
| - Data/parameter | ƒNRB, y |
| - Unit | Fraction |
| - Description | Default values of fraction of non-renewable biomass for least developed countries and small island developing states |
| - Source of data | CDM EB67 Report Annex 22 (Weblink) http://www.fao.org/docrep/004/Y1997E/y1997e21.htm |
| - Value(s) applied | 0.95 |
| - Choice of data or Measurement methods and procedures | The default fNRB approved by CDM EB will be applied to all VPAs. If this value is updated by the EB or rejected by the Myanmar DNA, then each VPA using this value will be updated either at VPA inclusion or verification. |
| Purpose of data | - To calculate VERs |
| - Additional comment | - The PP has this value endorsed by the local implementation partner, Mercy Corps |

| - Relevant SDG Indicator | - SDG 13: Take urgent action to combat climate change and its impacts |
| --- | --- |
| - Data/parameter | Bb,y |
| - Unit | t/hh/a (tons firewood per household per annum) |
| - Description | Quantity of firewood consumed for cooking in baseline scenario during year y |
| - Source of data | Baseline survey |
| - Value(s) applied | 4.219 |
| - Choice of data or Measurement methods and procedures | The value derived from ex-ante baseline surveys. For more details, please refer the supporting document titled, ‘VPA 007 (GS 6129) – (Fourth Term) - Myanmar Stoves Campaign - Baseline Survey Report-March 2018’ Three main reasons for higher than usual fuelwood consumption: Most families own livestock, mainly pigs, chicken, and cows. A common feedstock is broken rice which is cooked together with other cereals in order to make it easier to digest for the animals. This habit adds another cooking session per day. Farmers are regularly visited by traders to negotiate purchases of harvested goods. During these visits families prepare food for guests, requiring additional cooking. During fieldwork, additional food is prepared for farmworkers. |
| Purpose of data | - To calculate VERs |
| - Additional comment | - All data sources are transparent and verifiable. Refer to baseline survey report for details. |

| - Relevant SDG Indicator | - SDG 13: Take urgent action to combat climate change and its impacts |
| --- | --- |
| - Data/parameter | LEp,i,y |
| - Unit | fraction |
| - Description | Leakage in project scenario p, for technology i, during year y |
| - Source of data | Default value |
| - Value(s) applied | 0.95 |
| - Choice of data or Measurement methods and procedures | Deemed valid per the GS methodology. |
| Purpose of data | - To calculate VERs |
| - Additional comment | - Not Applicable |

##### D.2 Data and parameters monitored

>>

| Relevant SDG Indicator | SDG 13: Take urgent action to combat climate change and its impacts |
| --- | --- |
| Data/parameter: | Up,y |
| Unit | Percentage |
| Description | Usage rate for project cookstove in year y, based on adoption rate and drop off rate as per usage surveys |
| Measured/calculated/default | Measured |
| Source of data | Annual Monitoring |
| Value(s) of monitored parameter | 52.63% |
| Monitoring equipment | Household Surveys |
| Measuring/reading/recording frequency: | Measuring and Recording Annually |
| Calculation method (if applicable): | Not Applicable |
| QA/QC procedures: | A representative sample of project cookstove end-users was selected for follow-up by the monitoring and evaluation team. A visit to conduct surveys with households verified information in the distribution database and determine usage drop-off rates. |
| Purpose of data: | To calculate VERs |
| Additional comments: |  |

| Relevant SDG Indicator | SDG 13: Take urgent action to combat climate change and its impacts |
| --- | --- |
| Data/parameter: | Np,y |
| Unit | Number of project cookstoves credited (units) |
| Description | Cookstove in the project database for project scenario p through year y |
| Measured/calculated/default | Measured |
| Source of data | VPA 007 (GS 6129) - End User Database |
| Value(s) of monitored parameter | 1743 |
| Monitoring equipment | Sale Record Entries |
| Measuring/reading/recording frequency: | Annual |
| Calculation method (if applicable): | Not Applicable |
| QA/QC procedures: | Transparent data analysis and reporting |
| Purpose of data: | To calculate VERs |
| Additional comments: | The total sales record is divided based on project scenario to create the project database. |

| Relevant SDG Indicator | SDG 13: Take urgent action to combat climate change and its impacts |
| --- | --- |
| Data/parameter: | DFn |
| Unit | Fraction |
| Description | Discount factor to account for efficiency loss n of project cookstoves |
| Measured/calculated/default | Default |
| Source of data | Fixed default value from the methodology. |
| Value(s) of monitored parameter | 0.92 & 0.91 i.e., 1% efficiency loss per year. |
| Monitoring equipment | NA |
| Measuring/reading/recording frequency: | Annual |
| Calculation method (if applicable): | Not Applicable |
| QA/QC procedures: | Transparent data analysis and reporting |
| Purpose of data: | To calculate VERs |
| Additional comments: | Not Applicable |

| Relevant SDG Indicator | SDG 13: Take urgent action to combat climate change and its impacts |
| --- | --- |
| Data/parameter: | DFb, Stove, y |
| Unit | Fraction |
| Description | Discount factor to account for usage of baseline cookstove during the year y in project scenario p |
| Measured/calculated/default | Measured |
| Source of data | Annual Monitoring |
| Value(s) of monitored parameter | 33.08 % |
| Monitoring equipment | Household Surveys |
| Measuring/reading/recording frequency: | Annual |
| Calculation method (if applicable): | Not Applicable |
| QA/QC procedures: | Transparent data analysis and reporting |
| Purpose of data: | To calculate VERs |
| Additional comments: | The discount factor for baseline-stove is determined based on a number of meals cooked using the baseline stove. The required information shall be captured through sample surveys carried out following a random sampling approach for each age-group of the project stove. The minimum number of sample sizes shall be selected following the guidelines provided in section 4.2, option (b) of the POA-DD. |

SDG Monitoring Indicators and Status:

| Relevant SDG Indicator | SDG 3: Ensure healthy lives and promote well-being for all at all ages. Target 3.9: By 2030, substantially reduce the number of deaths and illnesses from hazardous chemicals and air, water and soil pollution and contamination |
| --- | --- |
| Data/parameter: | Improvement in the indoor air quality, and health and safety of the stove users. |
| Unit | % |
| Description | Qualitative feedback from the stove users |
| Source of data | Project Survey |
| Value(s) of monitored parameter | 100% |
| Measuring/reading/recording frequency: | Household Surveys |
| Calculation method (if applicable): | Annual |
| QA/QC procedures: | Transparent data collection, analysis and reporting. |
| Purpose of data: | Aimed at gathering and analysing user feedback on improvement in Indoor Air Quality and sub-sequent health benefits (eg: improvements in irritation to eyes, breathing problems, other health and safety benefits). The FES has reported reductions in CO and PM emissions as compared to three stone fires by 82% and 70% respectively (Link), which contributes to the health and well-being by reduction of Indoor Air Pollution. |
| Additional comments: | Not Applicable |

| Relevant SDG Indicator | SDG 7: Ensure access to affordable, reliable, sustainable and modern energy for all. Target 7.3: By 2030, double the global rate of improvement in energy efficiency. |
| --- | --- |
| Data/parameter: | Number of households served. |
| Unit | Number |
| Description | Total households and lives impacted |
| Source of data | Ongoing data collection and storage. |
| Value(s) of monitored parameter | 1743 eligible households in this VPA 1163 in use, and 4431 lives impacted. |
| Measuring/reading/recording frequency: | Ongoing, Project User Database. The Total Sales Record collects and maintains the total number of FES distributed in this VPA, from its start date to end date, which helps to estimate the number of lives this VPA has impacted. |
| Calculation method (if applicable): | Annual |
| QA/QC procedures: | Transparent data collection, analysis and reporting. |
| Purpose of data: | To measure the number of households (and lives) impacted by access of a fuel-efficient cookstove. |
| Additional comments: | Not Applicable. The average HH size of 4.83 people/HH was derived at the time of VPA registration based on baseline survey, and not monitored during the project survey during this monitoring period. |

| Relevant SDG Indicator | SDG 8: Promote sustained, inclusive and sustainable economic growth, full and productive employment and decent work for all. Target 8.3: Promote development-oriented policies that support productive activities, decent job creation, entrepreneurship, creativity and innovation, and encourage the formalization and growth of micro-, small- and medium-sized enterprises, including through access to financial services. |
| --- | --- |
| Data/parameter: | Number of Sale Agents (Men and Women) created for the sales/distribution of stoves. |
| Unit | Number |
| Description | Employment and local capacity built up |
| Source of data | Ongoing data collection and storage. The Project Tracking File records the number of sale agents created during each VPA. |
| Value(s) of monitored parameter | 46 sale agent jobs created during this VPA period. |
| Measuring/reading/recording frequency: | Ongoing, Project Tracking File |
| Calculation method (if applicable): | Annual |
| QA/QC procedures: | Transparent data collection, analysis and reporting. |
| Purpose of data: | To measure the number of jobs created local men and women in the target region. |
| Additional comments: | Not Applicable |

##### D.3. Comparison of monitored parameters with last monitoring period

| Data/Parameter | Value obtained in this monitoring period | Value obtained last monitoring period |
| --- | --- | --- |
| Up,y | 52.63% | 99.1% |
| Np,y | 1743 | 1743 |
| DFn | 0.91 | 0.92 |
| DFb, Stove, y | 33.08% | 11.8% |

##### D.4. Implementation of sampling plan

>> In the light of the COVID19 events, these surveys were conducted remotely, via the sale agents stationed already in the respective villages. These sale agents went door-to-door, following all safety guidelines, and interviewed randomly selected households. The agents then passed on the information to the IP team working from (home) office via a mobile phone call, and the IP team entered the information in a spreadsheet in real time. In this way, all user data could be measured and recorded.

The PP chose a list of villages where the project made medium to high volume of sales. Following this, a simple random sampling approach was employed to choose between around 10 villages from this list. Lastly, the households in these chosen village were selected randomly for usage surveys.

Sampling, and Selection of Villages and Households for Survey

A simple random sample firstly of the villages was chosen from the population, which was all the villages included in this particular VPA where stoves were distributed in medium or high volumes (range from 10 stoves up to 50+). These were random choices by the PP with the care that each village had the same probability of being chosen as sample. This list of villages was then handed over to the Implementation Partner (IP) by the PP and the IP led the data collection part in these villages with experienced enumerators. During this exercise, the enumerators could choose random households and not any specific ones to ensure each of the households in these villages has an equal chance of being interviewed.

The selection of households for monitoring essentially can be described to be occurring in two phases: a) At the village selection level and, b) At the household selection level.

At the household selection, as described above, the enumerators are given a list of villages by the PP and the Implementation Partners. All the households in these villages have an equal chance of being interviewed for the survey, and the selection is purely done randomly.

Prior to this, at the village selection for conducting the surveys, the PP had manually selected these villages for the surveys from the total population (N) of villages under this VPA meeting the sales threshold as described above via the (Manual) Lottery Method, as the N was not large. No software support was used here. The PP planned to select around 10 villages spread across the start and end dates of the stove distribution date under this VPA, and have around 9-11 surveys done in each of the villages, in order to get results from as many different villages we can.

#### SECTION E. CALCULATION OF SDG IMPACTS

##### E.1. Calculation of baseline value or estimation of baseline situation of each SDG Impact

>> The following reporting is based on conditions of the households in this project prior to the project implementation and in the scenario when they were primarily dependent on three stone fires. These are logical estimates of the values in the absence of this project and when households were using old three stone fires, with no aspects of the project design being implemented such as local capacity building and job creation and environmental awareness campaigns.

SDG 3: Ensure healthy lives and promote well-being for all of all ages

= The households in this VPA were exposed to negative impacts from using three stone fire and constraint on productivity due to more time (and money) was spent on collecting firewood.

= 0 households having access to fuel efficient cookstoves.

SDG 7: Ensure access to affordable, reliable, sustainable and modern energy for all

= The households in this VPA did not have access to an improved cookstove prior to this project.

= 0 households having access to fuel efficient cookstoves.

SDG 8: Promote sustained, inclusive and sustainable economic growth, full and productive employment and decent work for all

= 0 local jobs created of the nature included in this project design.

SDG 13: Take urgent action to combat climate change and its impacts

= 4.2 T/household/annum of wood was consumed, and 5239 tonnes of CO2 was emitted due to use of three stone fires.

= 0 environmental awareness sessions were organized.

##### E.2. Calculation of project value or estimation of project situation of each SDG Impact

>> SDG 3: Ensure healthy lives and promote well-being for all of all ages

This VPA alone serves 1743 eligible households and with the latest usage rate from monitoring tests being 52.63%, 917 stoves are still in use, which have improved the health and safety of around 4431 people (Average household size = 4.83 people/HH) due to the fuel-efficient cookstove. This is in line with the Target 3.9.1, which states to reduce the number of mortality rate attributed to household and ambient air pollution. The latest monitoring results show that all 100% of the stove users agree with the improvement in air quality, reduction in smoke and visible health impacts (less burning of eyes, cough, etc).

SDG 7: Ensure access to affordable, reliable, sustainable and modern energy for all

This VPA has brought fuel-efficient cookstove, thus improving the energy efficiency for their cooking practices as compared to the old, three-stone fires, in line with the Target 7.3, which states, by 2030, double the global rate of improvement in energy efficiency. It also covers the Target 7.b, which focuses on bringing technology to LDCs. This VPA alone serves 1743 eligible households and with the latest usage rate from monitoring tests being 52.63%, 917 stoves are still in use, which has improved the health and safety of around 4431 people (Average household size = 4.83 people/HH) due to the fuel-efficient cookstove.

SDG 8: Promote sustained, inclusive and sustainable economic growth, full and productive employment and decent work for all

Myanmar Stoves Campaign’s project design includes selecting, training and developing the local men and women for the role of sale agents, for distribution and selling of stoves to the households. This provides these local entrepreneurs with transferable skills and income source. This is in line with the Target 8.3.1, which states, to increase the Proportion of informal employment in non-agriculture employment, by sex. Since the start of the program and until the end of this VPA period, 46 such sale agents were trained and developed, which includes 42 women.

SDG 13: Take urgent action to combat climate change and its impacts

The VERs claimed by this VPA, are 3352 VERs during the issuance from the fourth monitoring period.

The detailed calculations are shown as below:

##### E.3. Calculation of leakage

>> The leakage calculations have been factored in via the Leakage Discount Factor of 0.95, as described in the Row 23 of the spreadsheet titled, ‘VPA 007 (GS 6129) - (Third Term) Ex-Post Emission Reduction Calculation’.

##### E.4. Calculation of net benefits or direct calculation for each SDG Impact

| SDG | SDG Impact | Baseline estimate | Project estimate | Net benefit |
| --- | --- | --- | --- | --- |
| 13 | VERs | 5239 | 1887 | 3352 |
| 3 | People Served | 0 | 4431 | 4431 |
| 7 | Households Served | 0 | 917 | 917 |
| 8 | Informal Jobs Created | 0 | 46 | 46 |

##### E.5. Comparison of actual SDG Impacts with estimates in approved PDD

| SDG | Values estimated in ex ante calculation of approved PDD for this monitoring period | Actual values achieved during this monitoring period |
| --- | --- | --- |
| 13 | 10266 | 3352 |
| 3 | 10,000 | 4431 |
| 7 | 1953 | 917 |
| 8 | 410 | 46 |

E.5.1. Explanation of calculation of value estimated ex ante calculation of approved PDD for this monitoring period

>> SDG 3: Ensure healthy lives and promote well-being for all of all ages

a) Baseline Scenario = None of the households applied for crediting had any form of improved cookstove. They were exposed to the detrimental health impacts due to three stone fires and more time being spent on collecting firewood.

Baseline Calculations: 0 household/people.

b) Project Scenario (& the net benefit) = This VPA alone serves 1743 stove eligible for ER claim and with 52.63% usage rate, 917 stoves are still in use, which has positively impacted the health and safety of around 4431 people. The latest monitoring results show that all 100% of the stove users agree with the improvement in air quality, reduction in smoke and visible health impacts (less burning of eyes, cough, etc).

SDG 7: Ensure access to affordable, reliable, sustainable and modern energy for all

a) Baseline Scenario = The households in this VPA applied for crediting did not have access to any form of improved cookstove.

Baseline Calculations: 0 household/people.

b) Project Scenario (& the net benefit) = This VPA alone serves 1743 households that are applied for crediting and with the latest usage rate from monitoring tests being 52.63%, around 917 stoves are still in use, which has ensured access to affordable, reliable, sustainable and modern energy for around 4431 people.

For time savings and health impact results, please refer to ‘VPA 007 (GS 6129) – (Fourth Term) - Project Monitoring Survey Results’.

SDG 8: Promote sustained, inclusive and sustainable economic growth, full and productive employment and decent work for all

a) Baseline Scenario = None of the local jobs which are involved in this project design were created during the baseline scenario.

Baseline Calculations: 0 jobs created.

b) Project Scenario (& the net benefit) = Since the start and until the end of this VPA period, 46 sale agents were trained and developed, which includes 42 women.

Project Calculations: Values derived from the ‘VPA 007 (GS 6129) Fourth Term - Project Tracking File’.

SDG 13: Take urgent action to combat climate change and its impacts

a) Baseline Scenario = Around 4.2 Tonnes of Wood was consumed per household per year and about 5239 Tonnes of CO2 was emitted per household by burning firewood per year in this VPA. In addition, there were no awareness raising campaigns around the climate change/global warming issues.

Baseline Calculations: Baseline fuel consumption derived from ‘VPA 007 (GS 6129) – (fourth Term) - Myanmar Stoves Campaign - Baseline Survey Report’.

b) Project Scenario (& the net benefit) = Around 2.69 Tonnes of firewood is saved per year per household and the VERs claimed by this VPA, are 3352 VERs during the third issuance. In addition to this, in line with Target 13.3, states, to improve education, awareness-raising and human and institutional capacity on climate change mitigation, adaptation, impact reduction and early warning. The Myanmar Stoves Campaign has conducted more than 60 such village level awareness raising events which were attended by more than 1560 participants, of which 1049 were females.

Project Calculations: Please refer to ‘VPA 007 (GS 6129) Third Term - Ex Post Emission Reductions Sheet’ for ER calculations. The values of awareness raising events are derived from the ‘VPA 007 (GS 6129) Fourth Term - Project Tracking File’.

##### E.6. Remarks on increase in achieved SDG Impacts from estimated value in approved PDD

>> For SDG 3, the number of people impacted is less in monitoring period due to less number of stoves being applied for crediting and drop in usage rate. The same applies for SDG 7 & SDG 13 for the ER calculations. For SDG 8, durin the time of validation the PP had reported all the sale agents right from the project start, which was a mistake. Hence the actual number of sale agents trained during the period are rightfully reported as 46.

#### SECTION F. SAFEGUARDS REPORTING

>>

| Relevant SPA | Safeguarding Principle 1 – Human Rights |
| --- | --- |
| Data / Parameter | Non violation of Human rights and abuses of any kind |
| Unit | Incidents |
| Description | Qualitative feedback from the stove users/sale agents, and other local stakeholders |
| Source of data | Ongoing Observations |
| Value(s) applied | 0% |
| Measurement methods and procedures | Discussions with users and sale agents during households surveys conducted by the PD, and during the objective observer/external assessor visit. |
| Monitoring frequency | Annual |
| QA/QC procedures | Transparent data collection, analysis and reporting. |
| Purpose of data | To ensure internationally proclaimed human rights for everyone associated with this project. |
| Additional comment | Our ongoing discussions with relevant stakeholders reveals that no such incidents have been reported. |

| Relevant SPA | Safeguarding Principle 4 - Cultural heritage, Indigenous Peoples, Displacement and Resettlement |
| --- | --- |
| Data / Parameter | Project in sites, structures, or objects with historical, cultural, artistic, traditional or religious values or intangible forms of culture |
| Unit | Number |
| Description | Project being implemented in the above-mentioned site(s) |
| Source of data | Local input/records of such sites of importance |
| Value(s) applied | 0 |
| Measurement methods and procedures | On-going evaluation of such sites |
| Monitoring frequency | On-going |
| QA/QC procedures | Transparent data collection, analysis and reporting. |
| Purpose of data | To ensure the project does not negatively impact these kinds of special sites/structures. |
| Additional comment | None of our installations or other aspects of the project are around sites, structures, or objects with historical, cultural, artistic, traditional or religious values or intangible forms of culture |

| Relevant SPA | Safeguarding Principle 6 - Economic Impacts |
| --- | --- |
| Data / Parameter | No forced labour |
| Unit | % |
| Description | Any sale agents/other labour being forcefully employed by the project |
| Source of data | Ongoing observations |
| Value(s) applied | 0 |
| Measurement methods and procedures | Discussions with sale agents during households’ surveys conducted by the PD, and during the objective observer/external assessor visit. |
| Monitoring frequency | Annual |
| QA/QC procedures | Transparent data collection, analysis and reporting. |
| Purpose of data | To ensure there is no forced labour of any kind with the project. |
| Additional comment | No forced labour employed |

#### SECTION G. STAKEHOLDER INPUTS AND LEGAL DISPUTES

##### G.1. List all Inputs and Grievances which have been received via the Continuous Input and Grievance Mechanism together with their respective responses/mitigations.

>> The PP engaged with the stove users, sale agents and the local administration but did not receive any inputs/grievances during the monitoring period.

| Method | Include all details of Chosen Method (s) so that they may be understood and, where relevant, used by readers. |
| --- | --- |
| Continuous Input / Grievance Expression Process Book (mandatory) | In line with section 2.1 of the Annex W Phone numbers has been provided to the end users. PP has a continuous grievance input mechanism, which is through the phone. Since end users are based at remote villages it is practically not possible for them to reach out in person, hence they address their issues over phone. Stakeholders are free to voice their concerns via phone. Additionally, the end users always have an option to revert to the salesperson (representative of distribution/retail partners etc.) in case of any feedback / complaints with the product post distribution. |
| GS Contact (mandatory) | help@goldstandard.org |
| Other | Email: mail@soneva.com |

##### G.2. Report on any stakeholder mitigations that were agreed to be monitored.

>> Not Applicable. This is the third monitoring period.

##### G.3. Provide details of any legal contest that has arisen with the project during the monitoring period

>> The PP confirms there are no legal contest or disputes as it received no such notices during this monitoring period from any of the stakeholders directly or indirectly associated with this project.

Revision History

| Version | Date | Remarks |
| --- | --- | --- |
| 1.1 | 14 October 2020 | Hyperlinked section summary to enable quick access to key sections Improved clarity on Key Project Information Section for POA monitoring Forward action request section Improved Clarity on SDG contribution/SDG Impact term used throughout Clarity on safeguard reporting Clarity on design changes Leakage section added for VER/CER projects Addition of Comparison of monitored parameters with last monitoring period Provision of an accompanying Guide to help the user understand detailed rules and requirements |
| 1.0 | 10 July 2017 | Initial adoption |

- Whenever emission reductions are capped, both the original and capped values used for calculations must be transparently reported.  Use brackets to denote original values.