## Summary Sheet
Project Name : Renewable Power Project by Emami Power Ltd
Project Capacity : 20 MW
Monitoring Period : 01/04/2021 to 02/08/2022
Date of compilation: 30/11/2023
SDG 13 |  |  | SDG 7
Start Date of Monitoring Period | 2021-04-01 |  | Start Date of Monitoring Period | 2021-04-01
End Date of Monitoring Period | 2022-08-02 |  | End Date of Monitoring Period | 2022-08-02
Number of opertaional Days for Current Monitoring Period | 489 |  | Number of opertaional Days for Current Monitoring Period | 489
Annual (365 Days) estimated Emission Reduction | 31689 |  | Annual Net Electricity MWh estimation as per Registered PDD | 32412
ER Estimation for Current Monitoirng Period | 42454.5781 |  | Net Estimated Generation MWh Estimation for Current Monitoirng Period | 43423.2
Actual ER for Current Monitoring Period | 37901 |  | Actual Net Generation for Current Monitoring Period | 38766.3569
% Variation in Actual Vs Estimated ER | -10.73% |  | % Variation in Actual Vs Estimated Net Generation | -10.72%
Vintage Wise Distribution | SDG 13 | SDG 7 | SDG 8
2021 | 21273 | 21758.4994 | 4 training and 40 people employed
2022 | 16628 | 17007.8575 | 1 training and 40 people employed
Total | 37901 | 38766.3569 | 5 Training and 40 People employeed

## Generation Details
[5 empty] | SDG 7 |  | SDG13
Month | Export (KWh) | Import (KWh) | Net electricity generated (KWh) as per JMR | Net electricity generated (KWh) as per Invoice | Net electricity generated (MWh) | Baseline Emission Factor (tCO2e/MWh) | Emission reductions (tCO2e)
2021-04-01 | 2914800.13 | 14400 | 2900400.13 | 2900400.13 | 2900.4001 | 0.9777 | 2835.7212
2021-05-01 | 2648699 | 13300 | 2635399 | 2635399 | 2635.399 | 0.9777 | 2576.6296
2021-06-01 | 2789599.75 | 14500 | 2775099.75 | 2775099.75 | 2775.0997 | 0.9777 | 2713.215
2021-07-01 | 2172800 | 14200 | 2158600 | 2158600 | 2158.6 | 0.9777 | 2110.4632
2021-08-01 | 2328299.52 | 14200 | 2314099.52 | 2314099.52 | 2314.0995 | 0.9777 | 2262.4951
2021-09-01 | 2190499.84 | 14000 | 2176499.84 | 2176499.84 | 2176.4998 | 0.9777 | 2127.9639
2021-10-01 | 2596700.16 | 17000 | 2579700.16 | 2579700.16 | 2579.7002 | 0.9777 | 2522.1728
2021-11-01 | 2344300.54 | 17700 | 2326600.54 | 2326600.54 | 2326.6005 | 0.9777 | 2274.7173
2021-12-01 | 1911400.45 | 19300 | 1892100.45 | 1892100.45 | 1892.1004 | 0.9777 | 1849.9066
2022-01-01 | 1164099.58 | 19400 | 1144699.58 | 1144699.58 | 1144.6996 | 0.9777 | 1119.1728
2022-02-01 | 2182598.66 | 17500 | 2165098.66 | 2165098.66 | 2165.0987 | 0.9777 | 2116.817
2022-03-01 | 2977701.89 | 17900 | 2959801.89 | 2959801.89 | 2959.8019 | 0.9777 | 2893.7983
2022-04-01 | 2893099.01 | 15800 | 2877299.01 | 2877299.01 | 2877.299 | 0.9777 | 2813.1352
2022-05-01 | 2814199.55 | 15100 | 2799099.55 | 2799099.55 | 2799.0995 | 0.9777 | 2736.6796
2022-06-01 | 2550300.06 | 14800 | 2535500.06 | 2535500.06 | 2535.5001 | 0.9777 | 2478.9584
2022-07-01 | 2350000.13 | 14500 | 2335500.13 | 2335500.13 | 2335.5001 | 0.9777 | 2283.4185
2022-08-01 | 191884.4324 | 1025.8065 | 190858.626 | 2622500 | 190.8586 | 0.9777 | 186.6025
Total |  |  |  |  | 38766 |  | 37901
Vintage Wise Generation |  | 2021 | 2022
Net Power Generated (MWh) |  | 21758.4994 | 17007.8575
Emission Reductions (tCO2e) |  | 21273 | 16628
Note on D21: Abhishek Anjan: The Import Value has been bifurcated as per the unitary method in accordance with the number of days.

## DGR_Aug 2022
Generation date | Actual Production (MWh)
2022-08-01 | 89100 | For Export
2022-08-02 | 103200 | Export from 01/08/2022 to 31/08/2022 | 2644100
2022-08-03 | 75600 | Export from 01/08/2022 to 02/08/2022 | 192300
2022-08-04 | 63000 | Generation Ratio | 0.072728
2022-08-05 | 57100 | Export as per Billing Statement from 01/08/2022 to 31/08/2022 | 2638386
2022-08-06 | 93900 | Apportioned value of Export from 01/08/2022 to 02/08/2022 | 191884.4324
2022-08-07 | 63200
2022-08-08 | 106900
2022-08-09 | 99200
2022-08-10 | 96800
2022-08-11 | 52300
2022-08-12 | 109700
2022-08-13 | 107900
2022-08-14 | 88900
2022-08-15 | 63200
2022-08-16 | 80300
2022-08-17 | 101600
2022-08-18 | 104000
2022-08-19 | 80900
2022-08-20 | 32600
2022-08-21 | 98600
2022-08-22 | 95600
2022-08-23 | 102800
2022-08-24 | 73400
2022-08-25 | 93400
2022-08-26 | 80200
2022-08-27 | 81500
2022-08-28 | 88700
2022-08-29 | 76000
2022-08-30 | 92900
2022-08-31 | 91600
Total | 2644100