## Title
VCS ID |  | 2093
Title |  | Waste to Energy Projects by Mahindra Waste to Energy Solutions Limited
ER Sheet Version |  | 12
ER Sheet Dated |  | 2025-08-18
Monitoring Period | Start | 2022-01-01
| End | 2023-11-30
Actual ERs |  | 13624 | tCO2e

## Actual ER
ER Comparision Estimated Vs Actual
Monitoring Period |  |  | Unit |  |  |  | Verification Period |  | Actual Ers
Start date |  | 2022-01-01 |  |  |  |  | From | To | (tCO2e)
End date |  | 2023-11-30 |  |  |  | 1st Verification | 2019-05-01 | 2020-12-31 | 12833
Total No. of Days |  | 699 | Days |  |  | 2nd Verification | 2021-01-01 | 2021-12-31 | 15900
Annual ERs as per PD |  | 25440 | tCO2e |  |  | 3rd Verification | 2022-01-01 | 2023-11-30 | 13624 | Current Verification
Estimate ERs as per PD |  | 48719 | tCO2e | [5 empty] | 42357 | tCO2e
Actual ERs in this MP |  | 23089 | tCO2e
% difference |  | -52.61% | %
Computation of Emission Reductions (Project Level)
Vintage |  | Baseline Emissions (BEy) | Project Emissions (PEy) | Leakage Emissions (LEy) | Emission Reductions (ERy) | Estimate ERs as per PD | % difference | Total Error part | Total VCUs Claimed (tCO2e))
From | To | (tCO2e) | (tCO2e) | (tCO2e) | (tCO2e) | (tCO2e) | % | (tCO2e) | (tCO2e)
2022-01-01 | 2022-12-31 | 15545 | 2971 | 1582 | 10992 | 25440 | 56.79% | 9465 | 1527
2023-01-01 | 2023-11-30 | 17103 | 3105 | 1901 | 12097 | 23279 | 48.03% | 0 | 12097
Total |  | 32648 | 6076 | 3483 | 23089 | 48719 | 52.61% | 9465 | 13624
Bio Methanation (Aurangabad): | [6 empty] | Bio Methanation (Tirupati):
Vintage |  | Baseline Emissions (BEy) | Project Emissions (PEy) | Leakage Emissions (LEy) | Emission Reductions (ERy) |  | Vintage |  | Baseline Emissions (BEy) | Project Emissions (PEy) | Leakage Emissions (LEy) | Emission Reductions (ERy)
From | To | (tCO2e) | (tCO2e) | (tCO2e) | (tCO2e) |  | From | To | (tCO2e) | (tCO2e) | (tCO2e) | (tCO2e)
2022-01-01 | 2022-12-31 | 4185 | 975 | 647 | 2563 |  | 2022-01-01 | 2022-12-31 | 4728 | 697 | 748 | 3283
2023-01-01 | 2023-11-30 | 4559 | 1099 | 1001 | 2459 |  | 2023-01-01 | 2023-11-30 | 4764 | 693 | 743 | 3328
Total |  | 8744 | 2074 | 1648 | 5022 |  | Total |  | 9492 | 1390 | 1491 | 6611
Bio Methanation (Pidugaralla): | [6 empty] | Bio Methanation (Adoni):
Vintage |  | Baseline Emissions (BEy) | Project Emissions (PEy) | Leakage Emissions (LEy) | Emission Reductions (ERy) |  | Vintage |  | Baseline Emissions (BEy) | Project Emissions (PEy) | Leakage Emissions (LEy) | Emission Reductions (ERy)
From | To | (tCO2e) | (tCO2e) | (tCO2e) | (tCO2e) |  | From | To | (tCO2e) | (tCO2e) | (tCO2e) | (tCO2e)
2022-01-01 | 2022-12-31 | 3534 | 686 | 158 | 2690 |  | 2022-01-01 | 2022-12-31 | 3098 | 613 | 29 | 2456
2023-01-01 | 2023-11-30 | 4117 | 693 | 157 | 3267 |  | 2023-01-01 | 2023-11-30 | 3663 | 620 | 0 | 3043
Total |  | 7651 | 1379 | 315 | 5957 |  | Total |  | 6761 | 1233 | 29 | 5499

## Baseline Emissions
Bio Methanation (Aurngabad):
Computation of Baseline Emissions - Bio-Methanation of Municipal Solid Waste
Monitoring Period | x | y | φy | (1-fy) | GWPCH4 | (1 - OX) | F | DOCf,y | MCFy | Wj,i | DOCj | e(-kj X (y-x)) | (1 - e-kj) | DFRATE,t,y | BECH4,SWDS,y
01/05/2019 - 30/04/2020 | 1 | 1 | 0.85 | 1 | 28 | 0.9 | 0.5 | 0.5 | 1 | 4517 | 0.15 | 1 | 0.32968 | 0.4996 | 1586.9269
[14 empty] | BEy=1 | 1586.9269
01/05/2020 - 30/04/2021 | 1 | 2 | 0.85 | 1 | 28 | 0.9 | 0.5 | 0.5 | 1 | 4517 | 0.15 | 0.67032 | 0.32968 | 0.4996 | 1063.7489
| 2 | 2 | 0.85 | 1 | 28 | 0.9 | 0.5 | 0.5 | 1 | 1661 | 0.15 | 1 | 0.32968 | 0.4996 | 583.5478
[14 empty] | BEy=2 | 1647.2968
01/05/2021 - 31/12/2021 | 1 | 3 | 0.85 | 1 | 28 | 0.9 | 0.5 | 0.5 | 1 | 4517 | 0.15 | 0.44933 | 0.32968 | 0.4996 | 713.0522
| 2 | 3 | 0.85 | 1 | 28 | 0.9 | 0.5 | 0.5 | 1 | 1661 | 0.15 | 0.67032 | 0.32968 | 0.4996 | 391.1638
| 3 | 3 | 0.85 | 1 | 28 | 0.9 | 0.5 | 0.5 | 1 | 3067 | 0.15 | 1 | 0.32968 | 0.4996 | 1077.5083
01/01/2022 - 30/04/2022 | 3 | 3 | 0.85 | 1 | 28 | 0.9 | 0.5 | 0.5 | 1 | 1868.269 | 0.15 | 1 | 0.32968 | 0.4996 | 656.3663
[14 empty] | BEy=3 | 2838.0906
01/05/2022 - 31/12/2022 | 1 | 4 | 0.85 | 1 | 28 | 0.9 | 0.5 | 0.5 | 1 | 4517 | 0.15 | 0.30119 | 0.32968 | 0.4996 | 477.9732
| 2 | 4 | 0.85 | 1 | 28 | 0.9 | 0.5 | 0.5 | 1 | 1661 | 0.15 | 0.44933 | 0.32968 | 0.4996 | 262.2049
| 3 | 4 | 0.85 | 1 | 28 | 0.9 | 0.5 | 0.5 | 1 | 4935.269 | 0.15 | 0.67032 | 0.32968 | 0.4996 | 1162.2509
| 4 | 4 | 0.85 | 1 | 28 | 0.9 | 0.5 | 0.5 | 1 | 4631.2 | 0.15 | 1 | 0.32968 | 0.4996 | 1627.048
01/01/2023 - 30/04/2023 | 4 | 4 | 0.85 | 1 | 28 | 0.9 | 0.5 | 0.5 | 1 | 2240.97 | 0.15 | 1 | 0.32968 | 0.4996 | 787.3048
[14 empty] | BEy=4 | 4316.7818
01/05/2023 - 30/11/2023 | 1 | 5 | 0.85 | 1 | 28 | 0.9 | 0.5 | 0.5 | 1 | 4517 | 0.15 | 0.2019 | 0.32968 | 0.4996 | 320.395
| 2 | 5 | 0.85 | 1 | 28 | 0.9 | 0.5 | 0.5 | 1 | 1661 | 0.15 | 0.30119 | 0.32968 | 0.4996 | 175.7612
| 3 | 5 | 0.85 | 1 | 28 | 0.9 | 0.5 | 0.5 | 1 | 4935.269 | 0.15 | 0.44933 | 0.32968 | 0.4996 | 779.08
| 4 | 5 | 0.85 | 1 | 28 | 0.9 | 0.5 | 0.5 | 1 | 6872.17 | 0.15 | 0.67032 | 0.32968 | 0.4996 | 1618.3891
| 5 | 5 | 0.85 | 1 | 28 | 0.9 | 0.5 | 0.5 | 1 | 2500.95 | 0.15 | 1 | 0.32968 | 0.4996 | 878.6418
[14 empty] | BEy=5 | 3772.2672
Bio Methanation (Tirupati):
Computation of Baseline Emissions - Bio-Methanation of Municipal Solid Waste
Monitoring Period | x | y | φy | (1-fy) | GWPCH4 | (1 - OX) | F | DOCf,y | MCFy | Wj,i | DOCj | e(-kj X (y-x)) | (1 - e-kj) | DFRATE,t,y | BECH4,SWDS,y
01/05/2019 - 30/04/2020 | 1 | 1 | 0.85 | 1 | 28 | 0.9 | 0.5 | 0.5 | 1 | 4426 | 0.15 | 1 | 0.32968 | 0.4996 | 1554.9565
[14 empty] | BEy=1 | 1554.9565
01/05/2020 - 30/04/2021 | 1 | 2 | 0.85 | 1 | 28 | 0.9 | 0.5 | 0.5 | 1 | 4426 | 0.15 | 0.67032 | 0.32968 | 0.4996 | 1042.3185
| 2 | 2 | 0.85 | 1 | 28 | 0.9 | 0.5 | 0.5 | 1 | 2927 | 0.15 | 1 | 0.32968 | 0.4996 | 1028.323
[14 empty] | BEy=2 | 2070.6415
01/05/2021 - 31/12/2021 | 1 | 3 | 0.85 | 1 | 28 | 0.9 | 0.5 | 0.5 | 1 | 4426 | 0.15 | 0.44933 | 0.32968 | 0.4996 | 698.687
| 2 | 3 | 0.85 | 1 | 28 | 0.9 | 0.5 | 0.5 | 1 | 2927 | 0.15 | 0.67032 | 0.32968 | 0.4996 | 689.3055
| 3 | 3 | 0.85 | 1 | 28 | 0.9 | 0.5 | 0.5 | 1 | 4369 | 0.15 | 1 | 0.32968 | 0.4996 | 1534.9311
01/01/2022 - 30/04/2022 | 3 | 3 | 0.85 | 1 | 28 | 0.9 | 0.5 | 0.5 | 1 | 1557.603 | 0.15 | 1 | 0.32968 | 0.4996 | 547.2221
[14 empty] | BEy=3 | 3470.1457
01/05/2022 - 31/12/2022 | 1 | 4 | 0.85 | 1 | 28 | 0.9 | 0.5 | 0.5 | 1 | 4426 | 0.15 | 0.30119 | 0.32968 | 0.4996 | 468.3439
| 2 | 4 | 0.85 | 1 | 28 | 0.9 | 0.5 | 0.5 | 1 | 2927 | 0.15 | 0.44933 | 0.32968 | 0.4996 | 462.0553
| 3 | 4 | 0.85 | 1 | 28 | 0.9 | 0.5 | 0.5 | 1 | 5926.603 | 0.15 | 0.67032 | 0.32968 | 0.4996 | 1395.709
| 4 | 4 | 0.85 | 1 | 28 | 0.9 | 0.5 | 0.5 | 1 | 5279.775 | 0.15 | 1 | 0.32968 | 0.4996 | 1854.9075
01/01/2023 - 30/04/2023 | 4 | 4 | 0.85 | 1 | 28 | 0.9 | 0.5 | 0.5 | 1 | 1386.588 | 0.15 | 1 | 0.32968 | 0.4996 | 487.1405
[14 empty] | BEy=5 | 4668.1563
01/05/2023 - 30/11/2023 | 1 | 5 | 0.85 | 1 | 28 | 0.9 | 0.5 | 0.5 | 1 | 4426 | 0.15 | 0.2019 | 0.32968 | 0.4996 | 313.9403
| 2 | 5 | 0.85 | 1 | 28 | 0.9 | 0.5 | 0.5 | 1 | 2927 | 0.15 | 0.30119 | 0.32968 | 0.4996 | 309.7249
| 3 | 5 | 0.85 | 1 | 28 | 0.9 | 0.5 | 0.5 | 1 | 5926.603 | 0.15 | 0.44933 | 0.32968 | 0.4996 | 935.5717
| 4 | 5 | 0.85 | 1 | 28 | 0.9 | 0.5 | 0.5 | 1 | 6666.363 | 0.15 | 0.67032 | 0.32968 | 0.4996 | 1569.9217
| 5 | 5 | 0.85 | 1 | 28 | 0.9 | 0.5 | 0.5 | 1 | 3268.975 | 0.15 | 1 | 0.32968 | 0.4996 | 1148.4668
[14 empty] | BEy=5 | 4277.6255
Bio Methanation (Piduguralla):
Computation of Baseline Emissions - Bio-Methanation of Municipal Solid Waste
Monitoring Period | x | y | φy | (1-fy) | GWPCH4 | (1 - OX) | F | DOCf,y | MCFy | Wj,i | DOCj | e(-kj X (y-x)) | (1 - e-kj) | DFRATE,t,y | BECH4,SWDS,y
01/05/2019 - 30/04/2020 | 1 | 1 | 0.85 | 1 | 28 | 0.9 | 0.5 | 0.5 | 1 | 4510 | 0.15 | 1 | 0.32968 | 0.4996 | 1584.4677
[14 empty] | BEy=1 | 1584.4677
01/05/2020 - 30/04/2021 | 1 | 2 | 0.85 | 1 | 28 | 0.9 | 0.5 | 0.5 | 1 | 4510 | 0.15 | 0.67032 | 0.32968 | 0.4996 | 1062.1004
| 2 | 2 | 0.85 | 1 | 28 | 0.9 | 0.5 | 0.5 | 1 | 1823 | 0.15 | 1 | 0.32968 | 0.4996 | 640.4622
[14 empty] | BEy=2 | 1702.5626
01/05/2021 - 31/12/2021 | 1 | 3 | 0.85 | 1 | 28 | 0.9 | 0.5 | 0.5 | 1 | 4510 | 0.15 | 0.44933 | 0.32968 | 0.4996 | 711.9472
| 2 | 3 | 0.85 | 1 | 28 | 0.9 | 0.5 | 0.5 | 1 | 1823 | 0.15 | 0.67032 | 0.32968 | 0.4996 | 429.3147
| 3 | 3 | 0.85 | 1 | 28 | 0.9 | 0.5 | 0.5 | 1 | 3133 | 0.15 | 1 | 0.32968 | 0.4996 | 1100.6956
01/01/2022 - 30/04/2022 | 3 | 3 | 0.85 | 1 | 28 | 0.9 | 0.5 | 0.5 | 1 | 1468.91 | 0.15 | 1 | 0.32968 | 0.4996 | 516.0622
[14 empty] | BEy=3 | 2758.0196
01/05/2022 - 31/12/2022 | 1 | 4 | 0.85 | 1 | 28 | 0.9 | 0.5 | 0.5 | 1 | 4510 | 0.15 | 0.30119 | 0.32968 | 0.4996 | 477.2325
| 2 | 4 | 0.85 | 1 | 28 | 0.9 | 0.5 | 0.5 | 1 | 1823 | 0.15 | 0.44933 | 0.32968 | 0.4996 | 287.7782
| 3 | 4 | 0.85 | 1 | 28 | 0.9 | 0.5 | 0.5 | 1 | 4601.91 | 0.15 | 0.67032 | 0.32968 | 0.4996 | 1083.7451
| 4 | 4 | 0.85 | 1 | 28 | 0.9 | 0.5 | 0.5 | 1 | 3328.15 | 0.15 | 1 | 0.32968 | 0.4996 | 1169.2563
01/01/2023 - 30/04/2023 | 4 | 4 | 0.85 | 1 | 28 | 0.9 | 0.5 | 0.5 | 1 | 1720.09 | 0.15 | 1 | 0.32968 | 0.4996 | 604.3075
[14 empty] | BEy=4 | 3622.3197
01/05/2023 - 30/11/2023 | 1 | 5 | 0.85 | 1 | 28 | 0.9 | 0.5 | 0.5 | 1 | 4510 | 0.15 | 0.2019 | 0.32968 | 0.4996 | 319.8985
| 2 | 5 | 0.85 | 1 | 28 | 0.9 | 0.5 | 0.5 | 1 | 1823 | 0.15 | 0.30119 | 0.32968 | 0.4996 | 192.9035
| 3 | 5 | 0.85 | 1 | 28 | 0.9 | 0.5 | 0.5 | 1 | 4601.91 | 0.15 | 0.44933 | 0.32968 | 0.4996 | 726.4561
| 4 | 5 | 0.85 | 1 | 28 | 0.9 | 0.5 | 0.5 | 1 | 5048.24 | 0.15 | 0.67032 | 0.32968 | 0.4996 | 1188.8554
| 5 | 5 | 0.85 | 1 | 28 | 0.9 | 0.5 | 0.5 | 1 | 3089.12 | 0.15 | 1 | 0.32968 | 0.4996 | 1085.2795
[14 empty] | BEy=4 | 3513.3931
Bio Methanation (Adoni):
Computation of Baseline Emissions - Bio-Methanation of Municipal Solid Waste
Monitoring Period | x | y | φy | (1-fy) | GWPCH4 | (1 - OX) | F | DOCf,y | MCFy | Wj,i | DOCj | e(-kj X (y-x)) | (1 - e-kj) | DFRATE,t,y | BECH4,SWDS,y
01/05/2019 - 30/04/2020 | 1 | 1 | 0.85 | 1 | 28 | 0.9 | 0.5 | 0.5 | 1 | 2679 | 0.15 | 1 | 0.32968 | 0.4996 | 941.1949
[14 empty] | BEy=1 | 941.1949
01/05/2020 - 30/04/2021 | 1 | 2 | 0.85 | 1 | 28 | 0.9 | 0.5 | 0.5 | 1 | 2679 | 0.15 | 0.67032 | 0.32968 | 0.4996 | 630.9018
| 2 | 2 | 0.85 | 1 | 28 | 0.9 | 0.5 | 0.5 | 1 | 1680 | 0.15 | 1 | 0.32968 | 0.4996 | 590.223
[14 empty] | BEy=2 | 1221.1248
01/05/2021 - 31/12/2021 | 1 | 3 | 0.85 | 1 | 28 | 0.9 | 0.5 | 0.5 | 1 | 2679 | 0.15 | 0.44933 | 0.32968 | 0.4996 | 422.9061
| 2 | 3 | 0.85 | 1 | 28 | 0.9 | 0.5 | 0.5 | 1 | 1680 | 0.15 | 0.67032 | 0.32968 | 0.4996 | 395.6383
| 3 | 3 | 0.85 | 1 | 28 | 0.9 | 0.5 | 0.5 | 1 | 2948 | 0.15 | 1 | 0.32968 | 0.4996 | 1035.7008
01/01/2022 - 30/04/2022 | 3 | 3 | 0.85 | 1 | 28 | 0.9 | 0.5 | 0.5 | 1 | 1365.14 | 0.15 | 1 | 0.32968 | 0.4996 | 479.6054
[14 empty] | BEy=3 | 2333.8506
01/05/2022 - 31/12/2022 | 1 | 4 | 0.85 | 1 | 28 | 0.9 | 0.5 | 0.5 | 1 | 2679 | 0.15 | 0.30119 | 0.32968 | 0.4996 | 283.4824
| 2 | 4 | 0.85 | 1 | 28 | 0.9 | 0.5 | 0.5 | 1 | 1680 | 0.15 | 0.44933 | 0.32968 | 0.4996 | 265.2043
| 3 | 4 | 0.85 | 1 | 28 | 0.9 | 0.5 | 0.5 | 1 | 4313.14 | 0.15 | 0.67032 | 0.32968 | 0.4996 | 1015.7401
| 4 | 4 | 0.85 | 1 | 28 | 0.9 | 0.5 | 0.5 | 1 | 3000.14 | 0.15 | 1 | 0.32968 | 0.4996 | 1054.0188
01/01/2023 - 30/04/2023 | 4 | 4 | 0.85 | 1 | 28 | 0.9 | 0.5 | 0.5 | 1 | 1486.7 | 0.15 | 1 | 0.32968 | 0.4996 | 522.3122
[14 empty] | BEy=4 | 3140.7579
01/05/2023 - 30/11/2023 | 1 | 5 | 0.85 | 1 | 28 | 0.9 | 0.5 | 0.5 | 1 | 2679 | 0.15 | 0.2019 | 0.32968 | 0.4996 | 190.024
| 2 | 5 | 0.85 | 1 | 28 | 0.9 | 0.5 | 0.5 | 1 | 1680 | 0.15 | 0.30119 | 0.32968 | 0.4996 | 177.7717
| 3 | 5 | 0.85 | 1 | 28 | 0.9 | 0.5 | 0.5 | 1 | 4313.14 | 0.15 | 0.44933 | 0.32968 | 0.4996 | 680.871
| 4 | 5 | 0.85 | 1 | 28 | 0.9 | 0.5 | 0.5 | 1 | 4486.84 | 0.15 | 0.67032 | 0.32968 | 0.4996 | 1056.6463
| 5 | 5 | 0.85 | 1 | 28 | 0.9 | 0.5 | 0.5 | 1 | 2947.9 | 0.15 | 1 | 0.32968 | 0.4996 | 1035.6657
[14 empty] | BEy=5 | 3140.9786

## Project Emissions
Since, the bio-methanation project doesn’t include direct gasification, no association of RDF/SB and incineration at the project site.
Therefore PEGAS,y , PERDF,SB,y and PEINC,y are considered as zero. Hence,
Bio-Methanation- Aurangabad | [9 empty] | Bio-Methanation- Tirupati
From | To | Q CH4,y | PEEC,y | PEFC,y | PECH4,y | PEflare,y | PEAD,y | PEcomp,y | Toal | From | To | Q CH4,y | PEEC,y | PEFC,y | PECH4,y | PEflare,y | PEAD,y | PEcomp,y | Toal
2022-01-01 | 2022-12-31 | 115.3861 | 153.0019 | 0 | 90.4627 | 0 | 243.4646 | 372.3601 | 974.6753 | 2022-01-01 | 2022-12-31 | 133.3937 | 176.88 | 0 | 104.5806 | 0 | 281.4606 | 0 | 696.3149
2023-01-01 | 2023-11-30 | 178.7467 | 237.0181 | 0 | 140.1374 | 0 | 377.1555 | 165.6409 | 1098.6987 | 2023-01-01 | 2023-11-30 | 132.6258 | 175.8618 | 0 | 103.9786 | 0 | 279.8405 | 0 | 692.3068
Total |  |  | 390.02 | 0 | 230.6001 | 0 | 620.6201 | 538.001 | 2073.374 | Total |  |  | 352.7418 | 0 | 208.5593 | 0 | 561.3011 | 0 | 1388.6217
Bio-Methanation- Piduguralla | [9 empty] | Bio-Methanation- Adoni
From | To | Q CH4,y | PEEC,y | PEFC,y | PECH4,y | PEflare,y | PEAD,y | PEcomp,y | Toal | From | To | Q CH4,y | PEEC,y | PEFC,y | PECH4,y | PEflare,y | PEAD,y | PEcomp,y | Toal
2022-01-01 | 2022-12-31 | 28.06 | 37.2076 | 0 | 21.999 | 0 | 59.2066 | 539.3334 | 685.8066 | 2022-01-01 | 2022-12-31 | 5.0708 | 6.7239 | 0 | 3.9755 | 0 | 10.6994 | 586.0567 | 612.5264
2023-01-01 | 2023-11-30 | 28.0025 | 37.1313 | 0 | 21.954 | 0 | 59.0853 | 545.8751 | 692.0482 | 2023-01-01 | 2023-11-30 | 0 | 0 | 0 | 0 | 0 | 0 | 619.3362 | 619.3362
Total |  |  | 74.3389 | 0 | 43.953 | 0 | 118.2919 | 1085.2085 | 1377.8548 | Total |  |  | 6.7239 | 0 | 3.9755 | 0 | 10.6994 | 1205.3929 | 1231.8626
PEEC,y
PECH4,y
For some time period the project is doing composting so the project emissions from composting are determined tool 13.
As per para 13 of tool 13 The project emissions from composting are determined as follows:
1. PEEC,y | Project emissions from electricity consumption associated with composting
| Site | Vintages | 𝐸𝐶𝑃𝐽,𝑐𝑜𝑚𝑝,y | 𝐸𝐹𝐸𝐹,𝑗,y | PEEC,y
| Aurangabad | 2022 | 26.6619 | 0.83 | 26.5553
|  | 2023 | 11.8603 | 0.83 | 11.8129
| Piduguralla | 2022 | 38.6176 | 0.83 | 38.4631
|  | 2023 | 39.086 | 0.83 | 38.9297
| Tirupati | 2022 | 0 | 0.83 | 0
|  | 2023 | 0 | 0.83 | 0
| Adoni | 2022 | 41.9631 | 0.83 | 41.7952
|  | 2023 | 44.346 | 0.83 | 44.1686
2. PEFC,y | Project emissions from electricity consumption associated with composting
| Site | Vintages | PEFC,y
| Aurangabad | 2022 | 55.1901
|  | 2023 | 24.5508
| Piduguralla | 2022 | 79.9384
|  | 2023 | 80.908
| Tirupati | 2022 | 0
|  | 2023 | 0
| Adoni | 2022 | 86.8636
|  | 2023 | 91.7962
3. PEHC4,y | Project emissions of methane from the composting process
| Site | Vintages | PECH4,y
| Aurangabad | 2022 | 149.3066
|  | 2023 | 66.4177
| Piduguralla | 2022 | 216.2586
|  | 2023 | 218.8816
| Tirupati | 2022 | 0
|  | 2023 | 0
| Adoni | 2022 | 234.9934
|  | 2023 | 248.3376
4. PEN2O,y | Project emissions of nitrous oxide from the composting process
| Site | Vintages | PEN2O,y
| Aurangabad | 2022 | 141.3081
|  | 2023 | 62.8596
| Piduguralla | 2022 | 204.6733
|  | 2023 | 207.1558
| Tirupati | 2022 | 0
|  | 2023 | 0
| Adoni | 2022 | 222.4044
|  | 2023 | 235.0338
4. PERO,y
As per para 30 of tool 13 Project emissions of methane from run-off wastewater are calculated only for the case of co-composting. Moreover, if run-off wastewater is collected and re-circulated to the composting process, then PERO,y is assumed to be zero

## Default Values
Parameters as per ACM0022, V-2.0 | Values | Unit | Reference
φy | 0.85 | Correction Factor | Tool 04, Emissions from solid waste disposal site, Version 08.0, EB 94, Annex 7
fy | 0 | Fraction | Tool 04, Emissions from solid waste disposal site, Version 08.0, EB 94, Annex 7
GWPCH4 | 28 | t CO2e/t CH4 | IPCC Fifth Assessment Report
OX | 0.1 | Oxidation Factor | Tool 04, Emissions from solid waste disposal site, Version 08.0, EB 94, Annex 7
F | 0.5 | Fraction | Tool 04, Emissions from solid waste disposal site, Version 08.0, EB 94, Annex 7
DOCf,y | 0.5 | Fraction | Tool 04, Emissions from solid waste disposal site, Version 08.0, EB 94, Annex 7
MCFy | 1 | Correction Factor | Tool 04, Emissions from solid waste disposal site, Version 08.0, EB 94, Annex 7
DOCj | 0.15 | Fraction | Lab test report; Measured in a Loss on ignition, based on dry mass according to EN 15934
kj | 0.4 | Decay Rate | Tool 04, Emissions from solid waste disposal site, Version 08.0, EB 94, Annex 7
EFEF,j,y | 0.83 | tCO2/MWh | Weighted average emission factor, CO2 Baseline Database for the Indian Power Sector, Version 14.0
GWPN2O | 265 | t CO2e/t N2O | IPCC Fifth Assessment Report
fCH4,default | 0.6 | m3 CH4/m3 | Tool 14, Project and lekage emission from anaerobic digesters, Version 2.0, EB 96 Annex 7
φCH4 | 0.00067 | t CH4/m3 CH4 | Tool 14, Project and lekage emission from anaerobic digesters, Version 2.0, EB 96 Annex 7
FEC, default | 1.02 | MWh/ t CH4 produced | Tool 14, Project and lekage emission from anaerobic digesters, Version 2.0, EB 96 Annex 7
FEEL, default | 1.3 | t CO2/ MWh | Tool 14, Project and lekage emission from anaerobic digesters, Version 2.0, EB 96 Annex 7
EFCH4, default | 0.028 | t CH4 leaked/ t CH4 produced | Tool 14, Project and lekage emission from anaerobic digesters, Version 2.0, EB 96 Annex 7
NCVDiesel, y | 43 | TJ/Gg | IPCC
EFCO2, diesel, y | 74.1 | tCO2/TJ | IPCC
COEF | 3186.3 | tCO2/Gg | Calculated
COEF | 0.0031863 | tCO2/kg | Calculated
Density | 0.83 | kg/litre | (http://www.iocl.com/Products/DieselSpecifications.pdf)
EFDiesel | 0.0026446 | tCO2/litre | Calculated
DFRATE,t,y | 49.96% | 2020-21 | https://cpcb.nic.in/uploads/MSW/MSW_AnnualReport_2020-21.pdf
SECcomp,default | 0.01 | MWh / t | Tool 13, Project and leakage emission from composting, Version 2.0, EB 96, Annex 6
𝑇𝐷𝐿𝑗,y | 20% | - | Tool 5, Baseline, project and/or leakage emissions from electricity consumption and monitoring of electricity generation
EFFC,default | 0.0207 | t CO2 / t | Tool 13, Project and leakage emission from composting, Version 2.0, EB 96, Annex 6
EFCH4,default | 0.002 | t CH4 / t | Tool 13, Project and leakage emission from composting, Version 2.0, EB 96, Annex 6
EFN2O,default | 0.0002 | t N2O / t | Tool 13, Project and leakage emission from composting, Version 2.0, EB 96, Annex 6
F𝑤𝑤,𝐶𝐻4,𝑑𝑒𝑓𝑎𝑢l,y | 0.2 | Fraction | Tool 14, Project and lekage emission from anaerobic digesters, Version 2.0, EB 96 Annex 7

## Data Sheet
Project Name :- 30 TPD Bio Methanation Plant At Aurangabad | [8 empty] | Project Name :- 20 TPD Bio Methanation Plant At Adoni
Sr. No. | Month |  | Monthly Qty of Municipal Solid waste treated (In Ton) | Amount of Bio Gas collected (Nm3) | Monthly Qty of Bio CNG (In Ton) | Monthly Qty of Compost (In Ton) | Monthly Electricity Consumption | Monthly Diesel Consumption (In Ltr.) | Sr. No. | Month |  | Monthly Qty of Municipal Solid waste treated (In Ton) | Amount of Bio Gas collected (Nm3) | Monthly Qty of Bio CNG (In Ton) | Monthly Qty of Compost (In Ton) | Monthly Electricity Consumption | Monthly Diesel Consumption (In Ltr.)
| From | To |  |  | Producted | Producted | ( in KWh) |  |  | From | To |  |  | Producted | Producted | ( in KWh)
1 | 2022-01-01 | 2022-01-31 | 478.689 | 24876 | 10 | 5 | 33470 | 0 | 1 | 2022-01-01 | 2022-01-31 | 352.41 | 2488 | 1 | 70 | 4176 | 0
2 | 2022-02-01 | 2022-02-28 | 434.23 | 24876 | 10 | 10 | 31733 | 0 | 2 | 2022-02-01 | 2022-02-28 | 313 | 2488 | 1 | 70 | 4723 | 0
3 | 2022-03-01 | 2022-03-31 | 512.79 | 24876 | 10 | 10 | 23145 | 0 | 3 | 2022-03-01 | 2022-03-31 | 342.51 | 2488 | 1 | 70 | 3114 | 0
4 | 2022-04-01 | 2022-04-30 | 442.56 | 20398 | 8 | 15 | 21790 | 0 | 4 | 2022-04-01 | 2022-04-30 | 357.22 | 1741 | 0.7 | 70 | 8743 | 0
5 | 2022-05-01 | 2022-05-31 | 581.86 | 21072 | 8 | 10 | 23153 | 0 | 5 | 2022-05-01 | 2022-05-31 | 322.32 | 2488 | 1 | 75 | 12108 | 0
6 | 2022-06-01 | 2022-06-30 | 524.74 | 24876 | 10 | 15 | 26788 | 0 | 6 | 2022-06-01 | 2022-06-30 | 347.04 | 498 | 0.2 | 75 | 10250 | 0
7 | 2022-07-01 | 2022-07-31 | 560.35 | 24900 | 10 | 10 | 24120 | 0 | 7 | 2022-07-01 | 2022-07-31 | 352.56 | 398 | 0.16 | 81 | 15457 | 0
8 | 2022-08-01 | 2022-08-31 | 702.39 | 26134 | 11 | 13 | 25000 | 0 | 8 | 2022-08-01 | 2022-08-31 | 342.06 | 25 | 0.01 | 80 | 8435 | 0
9 | 2022-09-01 | 2022-09-30 | 388.68 | 24876 | 10 | 13 | 25003 | 0 | 9 | 2022-09-01 | 2022-09-30 | 341.15 | 0 | 0 | 120 | 2153 | 0
10 | 2022-10-01 | 2022-10-31 | 584.54 | 19900 | 8 | 13 | 19403 | 0 | 10 | 2022-10-01 | 2022-10-31 | 421.2 | 0 | 0 | 121 | 680.5 | 0
11 | 2022-11-01 | 2022-11-30 | 599.29 | 24915 | 10 | 13 | 24795 | 0 | 11 | 2022-11-01 | 2022-11-30 | 424.25 | 0 | 0 | 120 | 700 | 0
12 | 2022-12-01 | 2022-12-31 | 689.35 | 25331 | 10 | 13 | 24865 | 0 | 12 | 2022-12-01 | 2022-12-31 | 449.56 | 0 | 0 | 120 | 2000 | 0
13 | 2023-01-01 | 2023-01-31 | 560.8 | 25122 | 10.099 | 13 | 24420 | 0 | 13 | 2023-01-01 | 2023-01-31 | 402.2 | 0 | 0 | 135.15 | 666.48 | 0
14 | 2023-02-01 | 2023-02-28 | 612.88 | 27453 | 11.036 | 13 | 23248 | 0 | 14 | 2023-02-01 | 2023-02-28 | 344.09 | 0 | 0 | 125.22 | 711.52 | 0
15 | 2023-03-01 | 2023-03-31 | 566.6 | 24878 | 10.001 | 49 | 25725 | 0 | 15 | 2023-03-01 | 2023-03-31 | 368.72 | 0 | 0 | 144.12 | 681 | 0
16 | 2023-04-01 | 2023-04-30 | 500.69 | 27363 | 11 | 13 | 24745 | 0 | 16 | 2023-04-01 | 2023-04-30 | 371.69 | 0 | 0 | 123.51 | 784 | 0
17 | 2023-05-01 | 2023-05-31 | 372.03 | 24878 | 10.001 | 55 | 22290 | 0 | 17 | 2023-05-01 | 2023-05-31 | 349.47 | 0 | 0 | 120.1 | 1270 | 0
18 | 2023-06-01 | 2023-06-30 | 369.94 | 23241 | 9.343 | 95.5 | 21683 | 0 | 18 | 2023-06-01 | 2023-06-30 | 392.32 | 0 | 0 | 125.58 | 959.52 | 0
19 | 2023-07-01 | 2023-07-31 | 350.74 | 24898 | 10.009 | 42.85 | 21288 | 0 | 19 | 2023-07-01 | 2023-07-31 | 465.93 | 0 | 0 | 125.3 | 992 | 0
20 | 2023-08-01 | 2023-08-31 | 375.87 | 22388 | 9 | 91 | 21538 | 0 | 20 | 2023-08-01 | 2023-08-31 | 435.85 | 0 | 0 | 120.21 | 1026.98 | 0
21 | 2023-09-01 | 2023-09-30 | 333.99 | 22388 | 9 | 30.05 | 21438 | 0 | 21 | 2023-09-01 | 2023-09-30 | 418.07 | 0 | 0 | 125.99 | 942.98 | 0
22 | 2023-10-01 | 2023-10-31 | 369.1 | 20289 | 8.156 | 92 | 21550 | 0 | 22 | 2023-10-01 | 2023-10-31 | 452.11 | 0 | 0 | 120.24 | 885.52 | 0
23 | 2023-11-01 | 2023-11-30 | 329.28 | 18657 | 7.5 | 35 | 17668 | 0 | 23 | 2023-11-01 | 2023-11-30 | 434.15 | 0 | 0 | 125.11 | 830.48 | 0
|  |  | 11241.389 | 548585 | 220.145 | 669.4 | 548858 | 0 |  |  |  | 8799.88 | 12614 | 5.07 | 2462.53 | 82289.98 | 0
Project Name :- 20 TPD Bio Methanation Plant At Piduguralla* | [8 empty] | Project Name :- 40 TPD Bio Methanation Plant At Tirupati
Sr. No. | Month |  | Monthly Qty of Municipal Solid waste treated (In Ton) | Amount of Bio Gas collected (Nm3) | Monthly Qty of Bio CNG (In Ton) | Monthly Qty of Compost (In Ton) | Monthly Electricity Consumption | Monthly Diesel Consumption (In Ltr.) | Sr. No. | Month |  | Monthly Qty of Municipal Solid waste treated (In Ton) | Amount of Bio Gas collected (Nm3) | Monthly Qty of Bio CNG (In Ton) | Monthly Qty of Compost (In Ton) | Monthly Electricity Consumption | Monthly Diesel Consumption (In Ltr.)
| From | To |  |  | Producted | Producted | ( in KWh) |  |  | From | To |  |  | Producted | Producted | ( in KWh)
1 | 2022-01-01 | 2022-01-31 | 368.23 | 4229 | 1.7 | 100 | 8184 | 0 | 1 | 2022-01-01 | 2022-01-31 | 385.392 | 20381 | 8.193 | 0 | 19412 | 0
2 | 2022-02-01 | 2022-02-28 | 387.55 | 5597 | 2.25 | 100 | 7688 | 0 | 2 | 2022-02-01 | 2022-02-28 | 324.53 | 15423 | 6.2 | 10 | 11362 | 0
3 | 2022-03-01 | 2022-03-31 | 324.11 | 6219 | 2.5 | 125 | 6123 | 0 | 3 | 2022-03-01 | 2022-03-31 | 335.986 | 17413 | 7 | 25 | 20742 | 0
4 | 2022-04-01 | 2022-04-30 | 389.02 | 4353 | 1.75 | 101 | 7226 | 0 | 4 | 2022-04-01 | 2022-04-30 | 511.695 | 24876 | 10 | 0 | 24772 | 0
5 | 2022-05-01 | 2022-05-31 | 397.22 | 5597 | 2.25 | 101 | 6322 | 0 | 5 | 2022-05-01 | 2022-05-31 | 877.745 | 24876 | 10 | 0 | 26274 | 0
6 | 2022-06-01 | 2022-06-30 | 373.5 | 6219 | 2.5 | 100 | 6921 | 0 | 6 | 2022-06-01 | 2022-06-30 | 1104.9 | 31095 | 12.5 | 18 | 29936 | 0
7 | 2022-07-01 | 2022-07-31 | 421.83 | 5373 | 2.16 | 105 | 5900 | 0 | 7 | 2022-07-01 | 2022-07-31 | 962.275 | 34826 | 14 | 16 | 32410 | 0
8 | 2022-08-01 | 2022-08-31 | 338.93 | 5721 | 2.3 | 110 | 7879 | 0 | 8 | 2022-08-01 | 2022-08-31 | 625.1 | 27363 | 11 | 21 | 28660 | 0
9 | 2022-09-01 | 2022-09-30 | 450.53 | 6219 | 2.5 | 110 | 13344 | 0 | 9 | 2022-09-01 | 2022-09-30 | 634.9 | 27363 | 11 | 0 | 41726 | 0
10 | 2022-10-01 | 2022-10-31 | 408.41 | 7463 | 3 | 110 | 13344 | 0 | 10 | 2022-10-01 | 2022-10-31 | 457.01 | 37313 | 15 | 41 | 28971 | 0
11 | 2022-11-01 | 2022-11-30 | 462.69 | 6343 | 2.55 | 111 | 12559 | 0 | 11 | 2022-11-01 | 2022-11-30 | 455.4 | 34826 | 14 | 0 | 29214 | 0
12 | 2022-12-01 | 2022-12-31 | 475.04 | 6468 | 2.6 | 111 | 12000 | 0 | 12 | 2022-12-01 | 2022-12-31 | 162.445 | 36070 | 14.5 | 20 | 30000 | 0
13 | 2023-01-01 | 2023-01-31 | 440.13 | 6244 | 2.51 | 130.01 | 49776 | 0 | 13 | 2023-01-01 | 2023-01-31 | 128.123 | 39800.995 | 16 | 0 | 33835 | 0
14 | 2023-02-01 | 2023-02-28 | 388 | 6617 | 2.66 | 115 | 44262 | 0 | 14 | 2023-02-01 | 2023-02-28 | 249.745 | 29851 | 12 | 108 | 29530 | 0
15 | 2023-03-01 | 2023-03-31 | 441.78 | 6269 | 2.52 | 130 | 32361 | 0 | 15 | 2023-03-01 | 2023-03-31 | 549.05 | 29851 | 12 | 63 | 25126 | 0
16 | 2023-04-01 | 2023-04-30 | 450.18 | 4975 | 2 | 125 | 35326 | 0 | 16 | 2023-04-01 | 2023-04-30 | 459.67 | 24876 | 10 | 29 | 27220 | 0
17 | 2023-05-01 | 2023-05-31 | 462.81 | 5124 | 2.06 | 132 | 29636 | 0 | 17 | 2023-05-01 | 2023-05-31 | 363.4 | 31095 | 12.5 | 0 | 24639 | 0
18 | 2023-06-01 | 2023-06-30 | 466.56 | 7512 | 3.02 | 128 | 41955 | 0 | 18 | 2023-06-01 | 2023-06-30 | 652.65 | 34826 | 14 | 5 | 25687.06 | 0
19 | 2023-07-01 | 2023-07-31 | 477.74 | 8706 | 3.5 | 124 | 48590 | 0 | 19 | 2023-07-01 | 2023-07-31 | 618.285 | 37313 | 15 | 0 | 38963.94 | 0
20 | 2023-08-01 | 2023-08-31 | 458.54 | 6716 | 2.7 | 130 | 44189 | 0 | 20 | 2023-08-01 | 2023-08-31 | 452.16 | 29851 | 12 | 0 | 33065 | 0
21 | 2023-09-01 | 2023-09-30 | 380.31 | 4975 | 2 | 130.3 | 42009 | 0 | 21 | 2023-09-01 | 2023-09-30 | 496.83 | 24876 | 10 | 25 | 28380 | 0
22 | 2023-10-01 | 2023-10-31 | 397.28 | 4353 | 1.75 | 125.15 | 42002 | 0 | 22 | 2023-10-01 | 2023-10-31 | 378.35 | 22699 | 9.125 | 12 | 25299 | 0
23 | 2023-11-01 | 2023-11-30 | 445.88 | 8167 | 2.3 | 128.3 | 9584 | 0 | 23 | 2023-11-01 | 2023-11-30 | 307.3 | 24876 | 10 | 0 | 20186 | 0
|  |  | 9606.27 | 139459 | 55.08 | 2681.76 | 527180 | 0 |  |  |  | 11492.941 | 661739.995 | 266.018 | 393 | 635410 | 0
* waste is coming from Piduguralla,dachepalli,Narasarapet and satenapalli ULBs.
Quantity of waste composted
Sr. No. | Month |  | Aurangabad | Piduguralla | Adoni | Tirupati
|  |  | Quantity of waste composted (In Ton) | Quantity of waste composted (In Ton) | Quantity of waste composted (In Ton) | Quantity of waste composted (In Ton)
| From | To
1 | 2022-01-01 | 2022-01-31 | 145.36 | 311.57 | 319.08 | 0
2 | 2022-02-01 | 2022-02-28 | 100.9 | 312.55 | 279.67 | 0
3 | 2022-03-01 | 2022-03-31 | 179.46 | 240.78 | 309.18 | 0
4 | 2022-04-01 | 2022-04-30 | 175.9 | 330.69 | 333.89 | 0
5 | 2022-05-01 | 2022-05-31 | 315.2 | 322.22 | 288.99 | 0
6 | 2022-06-01 | 2022-06-30 | 191.41 | 290.17 | 340.38 | 0
7 | 2022-07-01 | 2022-07-31 | 227.02 | 349.83 | 347.23 | 0
8 | 2022-08-01 | 2022-08-31 | 335.73 | 262.27 | 341.73 | 0
9 | 2022-09-01 | 2022-09-30 | 55.35 | 367.2 | 341.15 | 0
10 | 2022-10-01 | 2022-10-31 | 317.88 | 308.41 | 421.2 | 0
11 | 2022-11-01 | 2022-11-30 | 265.96 | 377.69 | 424.25 | 0
12 | 2022-12-01 | 2022-12-31 | 356.02 | 388.38 | 449.56 | 0
13 | 2023-01-01 | 2023-01-31 | 224.17 | 356.47 | 402.2 | 0
14 | 2023-02-01 | 2023-02-28 | 245.02 | 299.34 | 344.09 | 0
15 | 2023-03-01 | 2023-03-31 | 233.24 | 357.78 | 368.72 | 0
16 | 2023-04-01 | 2023-04-30 | 134.03 | 383.52 | 371.69 | 0
17 | 2023-05-01 | 2023-05-31 | 38.67 | 394.15 | 349.47 | 0
18 | 2023-06-01 | 2023-06-30 | 58.51 | 365.9 | 392.32 | 0
19 | 2023-07-01 | 2023-07-31 | 0 | 361.08 | 465.93 | 0
20 | 2023-08-01 | 2023-08-31 | 75.87 | 368.54 | 435.85 | 0
21 | 2023-09-01 | 2023-09-30 | 0 | 313.65 | 418.07 | 0
22 | 2023-10-01 | 2023-10-31 | 97.24 | 338.95 | 452.11 | 0
23 | 2023-11-01 | 2023-11-30 | 79.28 | 369.22 | 434.15 | 0
Total |  |  | 3852.22 | 7770.36 | 8630.91 | 0
Duration |  | Total Qty of Municipal Solid waste treated (In Ton) | Amount of Bio Gas collected (Nm3) | Qty of Bio CNG (In Ton) | Qty of Compost (In Ton) | Monthly Electricity Consumption (In MWh) | Monthly Diesel Consumption (In Ltr.) | Quantity of waste composted (In Ton)
2022-01-01 | 2023-11-30 | 41140.48 | 1362397.995 | 546.313 | 6206.69 | 1793.738 | 0 | 20253.49

## Previous verification data
Project Name :- 30 TPD Bio Methanation Plant At Aurangabad
S.No. | Month |  | Monthly Qty of Municipal Solid waste treated (Tons)
1 | 2019-05-01 | 2020-04-30 | 4517
2 | 2020-05-01 | 2021-04-30 | 1661
3 | 2021-05-01 | 2021-12-31 | 3067
Project Name :- 40 TPD Bio Methanation Plant At Tirupati
S.No. | Month |  | Monthly Qty of Municipal Solid waste treated (Tons)
1 | 2019-05-01 | 2020-04-30 | 4426
2 | 2020-05-01 | 2021-04-30 | 2927
3 | 2021-05-01 | 2021-12-31 | 4369
Project Name :- 20 TPD Bio Methanation Plant At Piduguralla
S.No. | Month |  | Monthly Qty of Municipal Solid waste treated (Tons)
1 | 2019-05-01 | 2020-04-30 | 4510
2 | 2020-05-01 | 2021-04-30 | 1823
3 | 2021-05-01 | 2021-12-31 | 3133
Project Name :- 20 TPD Bio Methanation Plant At Adoni
S.No. | Month |  | Monthly Qty of Municipal Solid waste treated (Tons)
1 | 2019-05-01 | 2020-04-30 | 2679
2 | 2020-05-01 | 2021-04-30 | 1680
3 | 2021-05-01 | 2021-12-31 | 2948

## Leakage Emissions
As per Methodological tool 14: Project and leakage emissions from anaerobic digesters
Aurangabad
From | To | F𝑤𝑤,𝐶𝐻4,𝑑𝑒𝑓𝑎𝑢l,y | Q CH4,y | GWPCH4 | LE𝑠𝑡𝑜𝑟𝑎𝑔𝑒,y
2022-01-01 | 2022-12-31 | 0.2 | 115.3861 | 28 | 647
2023-01-01 | 2023-11-30 | 0.2 | 178.7467 | 28 | 1001
|  |  | 294.1327 |  | 1648
Tirupati
From | To | F𝑤𝑤,𝐶𝐻4,𝑑𝑒𝑓𝑎𝑢l,y | Q CH4,y | GWPCH4 | LE𝑠𝑡𝑜𝑟𝑎𝑔𝑒,y
2022-01-01 | 2022-12-31 | 0.2 | 133.3937 | 28 | 748
2023-01-01 | 2023-11-30 | 0.2 | 132.6258 | 28 | 743
|  |  | 266.0195 |  | 1491
Piduguralla
From | To | F𝑤𝑤,𝐶𝐻4,𝑑𝑒𝑓𝑎𝑢l,y | Q CH4,y | GWPCH4 | LE𝑠𝑡𝑜𝑟𝑎𝑔𝑒,y
2022-01-01 | 2022-12-31 | 0.2 | 28.06 | 28 | 158
2023-01-01 | 2023-11-30 | 0.2 | 28.0025 | 28 | 157
|  |  | 56.0625 |  | 315
Adoni
From | To | F𝑤𝑤,𝐶𝐻4,𝑑𝑒𝑓𝑎𝑢l,y | Q CH4,y | GWPCH4 | LE𝑠𝑡𝑜𝑟𝑎𝑔𝑒,y
2022-01-01 | 2022-12-31 | 0.2 | 5.0708 | 28 | 29
2023-01-01 | 2023-11-30 | 0.2 | 0 | 28 | 0
|  |  | 5.0708 |  | 29
Total
From | To | F𝑤𝑤,𝐶𝐻4,𝑑𝑒𝑓𝑎𝑢l,y | Q CH4,y | GWPCH4 | LE𝑠𝑡𝑜𝑟𝑎𝑔𝑒,y
2022-01-01 | 2022-12-31 | 0.2 | 281.9105 | 28 | 1582
2023-01-01 | 2023-11-30 | 0.2 | 339.375 | 28 | 1901
Total LE𝑠𝑡𝑜𝑟𝑎𝑔𝑒,y |  |  |  |  | 3483

## Error Adjustments
1. Calculation for PEEC,y
In registered PDMR, the values of Default factor for the electricity consumption associated with the anaerobic digester per ton of methane generated is considered 0 from Data / Parameter table 5 of tool 14 version 02.0 for Covered anaerobic lagoons (gravity fed) / conventional digesters instead of Conventional digesters with continuously stirred tank reactor type for wastewater so the value of FEC, default is 1.02 MWh/tCH4 produced. It has been identified during the verification process and now it has been corrected. This error also impacts the previous verifications and emission reduction calculations and the hence, the error part is adjusted in current monitoring.
Monitoring period 1
MP - 01/05/2019 to 31/12/2020
| Q CH4,y | PEEC,y | Q CH4,y | PEEC,y | Q CH4,y | PEEC,y | Q CH4,y | PEEC,y | Total
| As per ER sheet of MP1 | As per Eq.3 of tool 14 | As per ER sheet of MP1 | As per Eq.3 of tool 14 | As per ER sheet of MP1 | As per Eq.3 of tool 14 | As per ER sheet of MP1 | As per Eq.3 of tool 14
Vintage | For Aurangabad |  | Adoni |  | Tirupati |  | Piduguralla
2019 | 39.828 | 52.8119 | 0 | 0 | 0 | 0 | 1.225 | 1.6244 | 54.4363
2020 | 78.605 | 104.2302 | 0.825 | 1.0939 | 0 | 0 | 20.578 | 27.2864 | 132.6106
[8 empty] | Total for MP1 | 188
Monitoring period 2
MP - 01/01/2021 to 31/12/2021
| Q CH4,y | PEEC,y | Q CH4,y | PEEC,y | Q CH4,y | PEEC,y | Q CH4,y | PEEC,y | Total
| As per ER sheet of MP2 | As per Eq.3 of tool 14 | As per ER sheet of MP2 | As per Eq.3 of tool 14 | As per ER sheet of MP2 | As per Eq.3 of tool 14 | As per ER sheet of MP2 | As per Eq.3 of tool 14
Vintage | For Aurangabad |  | Adoni |  | Tirupati |  | Piduguralla
2021 | 95.6 | 126.7656 | 7.14 | 9.4676 | 134.255 | 178.0221 | 29.345 | 38.9115 | 354
| Error part of PEEC,y |  | 542
2. Calculation for LE𝑠𝑡𝑜𝑟𝑎𝑔𝑒,y
In Section 5.3 of the Joint PD-MR, leakage emissions are considered to be zero. However, some times the liquid digestate has been stored, the leakage emissions associated with its storage are calculated in accordance with Section 6.2.1 of Methodological Tool 14: Project and Leakage Emissions from Anaerobic Digesters. For this calculation, the relevant parameters Fww, CH₄,default are incorporated and considered in the calculations. It has been identified during the verification process and now it has been corrected. This error also impacts the previous verifications and emission reduction calculations and the hence, the error part is adjusted in current monitoring.
| Monitoring period | F𝑤𝑤,𝐶𝐻4,𝑑𝑒𝑓𝑎𝑢l,y | Q CH4,y | GWPCH4 | LE𝑠𝑡𝑜𝑟𝑎𝑔𝑒,y
| MP1 (2019) | 0.2 | 41.053 | 28 | 229.8968
| MP1 (2020) | 0.2 | 100.008 | 28 | 560.0448
| MP2 (2021) | 0.2 | 266.34 | 28 | 1491.504
| Error part of LE𝑠𝑡𝑜𝑟𝑎𝑔𝑒,y |  | 2282
3. Calculation for PEcomp,y
| MP |  | Quantity of waste composted
| Monitoring period 1 (01/05/2019 to 31/12/2020) |  | 2499
| Monitoring period 2 01/01/2021 to 31/12/2021 |  | 3796
1. PEEC,y | Project emissions from electricity consumption associated with composting
| MP |  | 𝐸𝐶𝑃𝐽,𝑐𝑜𝑚𝑝,y | 𝐸𝐹𝐸𝐹,𝑗,y | PEEC,y
| Monitoring period 1 (01/05/2019 to 31/12/2020) |  | 24.99 | 0.83 | 24.89
| Monitoring period 2 01/01/2021 to 31/12/2021 |  | 37.96 | 0.83 | 37.8082
62.6982
2. PEFC,y | Project emissions from electricity consumption associated with composting
| MP |  | PEFC,y
| Monitoring period 1 (01/05/2019 to 31/12/2020) |  | 51.7293
| Monitoring period 2 01/01/2021 to 31/12/2021 |  | 78.5772
130.3065
3. PEHC4,y | Project emissions of methane from the composting process
| MP |  | PECH4,y
| Monitoring period 1 (01/05/2019 to 31/12/2020) |  | 139.944
| Monitoring period 2 01/01/2021 to 31/12/2021 |  | 212.576
352.52
4. PEN2O,y | Project emissions of nitrous oxide from the composting process
| MP |  | PEN2O,y
| Monitoring period 1 (01/05/2019 to 31/12/2020) |  | 132.447
| Monitoring period 2 01/01/2021 to 31/12/2021 |  | 201.188
333.635
4. PERO,y
As per para 30 of tool 13 Project emissions of methane from run-off wastewater are calculated only for the case of co-composting. Moreover, if run-off wastewater is collected and re-circulated to the composting process, then PERO,y is assumed to be zero.
| Error part of PEcomp,y |  | 879.1597
4. Error adjustment of Baseline Emissions of MP1
During the second verification, the issue highlighted in Deviation 4 was identified and subsequently corrected. However, since this deviation has been applied starting from the second verification, and the first verification had already been approved prior to this correction, the impact of the deviation has not been incorporated in the first verification. As a result, it can be stated that the emission reduction calculations in the first verification contain some errors. These errors have not been adjusted or accounted for in the current (third) verification. The details are as follows:
Deviation 4 states that “The value of the monitoring parameter DOCf, y was mistakenly taken as 0.9 during registration of the project activity which is not in line with the default value present in the methodology. During 2nd verification, the value of DOCf, y is corrected as 0.5 which is a default value present in the tool04 ‘Emissions from solid waste disposal sites.” The formula of baseline emissions is as follows:
Means the multiplication factor DOCf, y of baseline emissions was taken 0.9 instead of 0.5 means the baseline emissions are calculated 1.8 times higher than actual so appropriate calculation are as follows:
| Monitoring period | Baseline Emissions as per MP 1 (BEy) | Appropriate Baseline Emissions (BEy) | Error Part
| Monitoring period 1 | 12963 | 7202 | 5761
(01-May-2019 to 31- December -2020)
Error part of PEEC,y |  | 542
Error part of LE𝑠𝑡𝑜𝑟𝑎𝑔𝑒,y |  | 2282
Error part of PEcomp,y |  | 880
Error part of BE of MP1 due to Deviation 4 |  | 5761
Total Error part |  | 9465